## Sheet1
TX SET Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 2022-04-20
Agenda Item: | Decision / Resolution | Action Items :
March and April 13 Meeting Notes
| Meeting Notes were approved as submitted. | The Vice Chair will have the notes posted as final versions to the respective meeting dates.
Retail Market Subcommittee (RMS) Update
Discussion Items
RMGRR168, Modify ERCOT Responsibilities During the Mass Transition--Texas SET Comments | The Texas SET Chair conducted a discussion On the RMGRR and agreed to support the PUCT comments; then made changes to the Business Case that were in line with the Texas SET comments created at the 4/13 WebEx meeting. | The Texas SET comments will be submitted for be reviewed at the next RMS meeting along with the Impact Analysis (IA). The RMGRR will go to the May Technical Advisory Committee (TAC) meeting for approval and will wait for the related NPRR to catch up. Then both will go to the Board and on to the PUCT Staff.
Draft NPRR to support RMGRR168, Modify ERCOT Responsibilities During the Mass Transition--Texas SET Comments | The Texas SET Chair conducted a discussion on the edits made to the NPRR at the 4/13 WebEx only meeting. Texas SET agreed that no more changes will be necessary. | To RMS May for a revote; then to PRS and catch up at the RMGRR at TAC. Delay the NPRR one month.
ERCOT Update
Market Flight Test | The ERCOT Flight Administrator presented the June Flight update. flight.
Flight 0222 Test delay discussion. | Texas SET agreed that the delay of the penny test in the last flight did not have a great effect on the flight as a whole. Therefore the ERCOT Flight Administrator and Texas SET meeting attendees agreed that no changes were needed to the Texas Market Test Plan (TMTP)
Other Business
Texas SET 5.0 | The Texas SET Chair conducted a discussion on the next steps needed by Texas SET to start creating a list of the changes that will be implemented for the 5.0 Release. The Centerpoint Energy meeting attendee directed the group to the Texas SET 4.0 Release MCT key documents to review what has been done in the past. | The Texas SET Chair will seek direction from RMS Leadership. https://www.ercot.com/committees/inactive/mct
Texas Flight Testing Schedule 2023 | ERCOT stated that Texas SET needs to start considering the schedule for next year given that the Lubbock territory will be coming on in 2023. | Texas SET will begin to look at this at the next meeting.
Next Meeting--WebEx Only | 5/18/2022--May cancel unless assigned something by RMS
Attendees F-T-F
Carolyn Reed Centerpoint Energy | Kyle Patrick NRG
Jeff Long CNP | Sam Pak ONCOR
Kathryn Thurman ERCOT
Attendees Webex
Austin | Jordan Troublefield ERCOT
Catherine Meiners ERCOT | Kathy Scott Centerpoint Energy
Carole Root AEP | Kim Wall Hansen Technologies
Dave Michaelson ERCOT | Mariah Benson PUCT
Deb Belin Earth Etch | Mark Ruane ERCOT
Diana Rehfeldt TNMP | Mark Pepdjonovic ESG
Eric Lotter GridMonitor | Paul Yockey ERCOT
Esther Kent CNP | Sheri Wiegand Vistra
Jeff Chen CNP | Stephen Wilson TXU Energy
Jesse O Macias AEP Texas