## Slide 1
Market Readiness Updates
NPRR1093 and FFRA
Matt Mereness
TAC Meeting
May 25, 2022

## Slide 2: Outline
Summary of Market Readiness Improvements
NPRR1093 Load Resource Participation in Non-Spinning Reserve
NPRR863/FFRA- Fast-Frequency Response Advancement Project

## Slide 3: Reminder of Improved Market Readiness concepts
Project process changes:
  Early development and delivery of changes to interface specifications
  Projects will assess the level of market interface impacts and incorporate into project plans to mitigate risks (example, MOTE duration).
Communication changes:
  Project team will publish interface changes earlier, posting to both the MIS and Technology Working Group (TWG) stakeholder forum.
  TWG review of MP interface changes and estimated key project dates:
    Interface specifications release date / Project/Business workshop date
    MOTE availability date / Go-Live date
Market Readiness changes:
  ERCOT is improving the MP feedback loop (for FFRA & ECRS implementations) since both projects affect all Ancillary Service submissions (creates reliability risk):
  Concept of early Market Notice to communicate risk and MOTE requirements.
  Concept of longer MOTE Duration (increase from 4 weeks to 7 weeks).
  Concept of requiring and publishing MOTE submissions by QSEs.
3

## Slide 4: NPRR1093 Load Resource Participation in Non-Spinning Reserve
NPRR1093 Market Readiness Dates (in addition to regular market notices) :
  Interface changes published and reviewed at February 10, 2022 TWG
  Provisional Qualification Market Notice April 21, 2022
    The Resource Entities for existing Load Resources that are currently qualified to provide Responsive Reserve Service (RRS) can submit a provisional qualification request for NSRS to LRQualification@ercot.com.
  Project/Business workshop date: April 25, 2022 1-3pm
  MOTE deployment date May 5, 2022
  MOTE support calls May 12, 2022
  Scheduled Release 3 Completion: May 26, 2022
  First use of NCLRs for Non-Spin in DAM: May 27, 2022
  First Operating Day that NCLRs can provide NSRS: May 28, 2022

## Slide 5: NPRR863/FFRA Fast-Frequency Response Advancement Project
FFRA Market Readiness Dates :
  Interface change review at December 7, 2021 workshop
  Market Notice concerning Market Readiness May 20, 2022
    All QSEs that are qualified providers of Responsive Reserve Service (RRS), Regulation Service, and/or Non-Spinning Reserve Service will be required to demonstrate their ability to submit offers for these Ancillary Services using the new interface prior to implementation of the FFRA project
    August-September 2022: MOTE availability for testing where MOTE participation will be required, monitored, and published by ERCOT.
      Weeks 1 & 2 - No submission summary published
      Weeks 3 & 4 - Publish submission summary by QSE (target 50% success)
      Weeks 5 & 6 - Publish submission summary by QSE (target 75% success)
      Week 7 - Publish submission summary by QSE (target 95% success)
  Project/Business workshop date- tentatively July 25, 2022
  FFRA MOTE deployment- mid-August 2022
  FFRA Go-Live in Release 5 (early October 2022)

## Slide 6: Next Steps and Questions
Next Steps
  ERCOT continues to work closely with TWG
  ERCOT will periodically update TAC with upcoming Market Readiness milestones
    NPRR863/FFRA (go-live October 2022)
    NPRR1120 Firm Fuel Supply Service (go-live 4Q2022)
    NPRR863/ECRS (go-live first half 2023)
Further comments or questions can be directed to Matt.Mereness@ercot.com