## Slide 1
Project Update
June 9, 2022
Troy Anderson
ERCOT Portfolio Management

## Slide 2
  Recent / Upcoming Project Highlights
  2022 Release Targets
  In-Flight Strategic Projects
    Fast-Frequency Response (FFR) Advancement
    BES Combo Model Implementation
  Priority/Rank Options for Revision Requests with Impacts
    NPRR1131 – Controllable Load Resource Participation in Non-Spin
  Technology Working Group
    Summary of 5/19/2022 meeting
  “Not Started” Revision Request List
    Continuing Discussion on Not Started and On Hold Revision Requests
Location of Revision Request Project Information: http://www.ercot.com/services/projects
Project Update Agenda

## Slide 3: Recent / Upcoming Project Highlights
2022 May Release – Off-cycle – 5/13/2022 Complete
  NPRR1092 – Reduce RUC Offer Floor and Limit RUC Opt-Out Provision (RUC Offer Floor portion)
2022 May Release – R3 – 5/24/2022-5/26/2022 Complete
  NPRR939 – Modification to Load Resources Providing RRS to Maintain Minimum PRC on Generators During Scarcity Conditions
  NPRR1093 – Load Resource Participation in Non-Spinning Reserve
    Other RRs related to NPRR1093 – NOGRR232, OBDRR032, ODBRR033, OBDRR035
  NPRR1101 – Create Non-Spin Deployment Groups made up of Generation Resources Providing Off-Line Non-Spinning Reserve & Load Resources that are Not Controllable Load Resources Providing Non-Spinning Reserve
  NPRR1113 – Clarification of Reg-Up Schedule for Controllable Load Resources in A/S Imbalance
  SCR800 – Addition of DC Tie Ramp to GTBD Calculation
  SCR809 – Changes to External Telemetry Validations in Resource Limit Calculator
  SCR814 – Point-to-Point (PTP) Obligation Bid Interval Limit
2022 June Release – Off-cycle – 6/23/2022 In Flight
  NPRR935 – Post All Wind and Solar Forecasts (new solar forecasts and reports – see 5/4/2022 notice)
2022 July Release – R4 – 7/26/2022-7/28/2022 In Flight
  NPRR1108 – ERCOT Shall Approve or Deny All Resource Outage Requests
2022 October Release – R5 – 10/4/2022-10/6/2022 In Flight
  FFR Advancement (FFRA portion of NPRR863)
  NPRR987 – BESTF-3 Energy Storage Resource Contribution to Physical Responsive Capability portion
  NPRR1002 – BESTF-5 Charging Restrictions in Emergency Conditions portion
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2022 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February Various Dates | April 4/5 – 4/7 | May 5/24 – 5/26 | July 7/26 – 7/28 | October 10/4 – 10/6 | December 12/6 – 12/8
LPGRR068 NPRR1054(a) NPRR1005 NOGRR210 RRGRR025 NPRR917 NPRR1052 NPRR1065 NPRR1073 NPRR1016 PGRR082 NOGRR212 | None NPRR1092(a) | NPRR939 NPRR1093 NPRR1101 NPRR1113 NOGRR232 OBDRR032 OBDRR033 OBDRR035 SCR800 SCR809 SCR814 MarkeTrak User Interface Refresh | NPRR1108 NPRR935(b) | FFR Advancement (NPRR863 FFR) NPRR987(a) NPRR1002(a) | NPRR1097
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
ü
ü
ü
ü
Securitization Subchapter N March Go-Live
ECRS project started in 1/2022 with a go-live target prior to the EMS Freeze
1/1
EMS Freeze
Mid-2023 – Mid-2024
E
E
E
ü
ü
ü
ü
DGR/DESR
NPRR1054(a) – Portion of gray box
NPRR935(b) – New solar forecasts and reports
NPRR987(a) – ESR Contribution to PRC
NPRR1002(a) – Charging Restrictions in Emergency Conditions
NPRR1092(a) – RUC offer floor change
SCR789 Ph2
Late 2022
TBD Items | NPRRs: 484,825(b),826,829,841,857,879,885,904,918,930,936,941,945,962,963,965,975,995,1004,1006,1019,1023,1026,1030,1032,1034,1040, 1057,1063,1077,1090,1092(b),1105 SCRs: 799,805,807,810,812,813,816,818,819 PGRRs: 066,076,088,091,094,099 Other: OBDRR009,RRGRR028
E
ü
ü
ü
ü
NPRR1120 Firm Fuel Supply Service RFP
Issue no later than 8/1/2022
NPRR1120 Firm Fuel Supply Service
Contracts start in November
6/4 – 6/6
6/23
5/13
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü

## Slide 5: In-Flight Strategic Projects
  PR325-01 Fast-Frequency Response (FFR) Advancement (Gated to Execution on 6/22/2021)
    Planned go-live for 2022-R5 (Oct 2022)
    NPRR863, NPRR1015, NPRR1079, NOGRR187
  PR353-01 BES Combo Model Implementation – decoupled into separate efforts below
    NPRR987 – BESTF-3 ESR Contribution to Physical Responsive Capability and RT On-Line Reserve Capacity Calcs
    TARGETING IMPLEMENTATION IN 2022-R5
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    TARGETING IMPLEMENTATION IN 2022-R5
    NPRR989 – BESTF-1 ESR Technical Requirements
    NPRR1038 – BESTF-8 Limited Exemption from Reactive Power Requirements for Certain ESRs
    POTENTIAL IMPLEMENTATION IN 2022
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    RUN IN PARALLEL WITH RARF REPLACEMENT – TARGET GO-LIVE 2023
    NPRR963 – Base Point Deviation Settlement & Deployment Performance Metrics for ESRs (Combo Model)
    NPRR987 – BESTF-3 ESR Contribution to Physical Responsive Capability and RT On-Line Reserve Capacity Calcs
    NPRR1069 – Align Ancillary Service Responsibility for ESRs with NPRR987
    EXPECTED IMPLEMENTATION AFTER ECRS IN 2023 (re-assessing delivery options in September)
    NPRR1026 – BESTF-7 Self-Limiting Facilities and Self-Limiting Resources
    IMPLEMENTATION TIMELINE TBD
ESR: Energy Storage Resource
DGR: Distributed Generation Resource
BES: Battery Energy Storage

## Slide 6: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR1131 | Controllable Load Resource Participation in Non-Spin | 2023 | 3720 | $100k-$150k, 6-9 months Impacted Systems: MMS, S&B, EMS, Reporting Conflicts with FFRA and ECRS Recommend a target 2023 start after ECRS implementation Revisit if we see an increase in the number of CLRs that are qualified to participate in Non-Spin
SCR820 | Operator Real-Time Messaging During Emergency | TBD | TBD | Additional time requested to complete IA Extra time has been needed due to: Outreach to other ISOs Time to research potential solutions (build vs. buy) Estimation team involved in critical in-flight projects Time to estimate takes longer when a new system is to being contemplated Targeting IA for July PRS meeting
PPL Rank Information
Next available 2022 Rank in Business Strategy = 3610
Next available 2023 Rank in Business Strategy = 3720
Next available Rank in Regulatory = 340
Options for…

## Slide 7: ERCOT Technology Working Group (TWG)
Protocol Projects with Upcoming Market-Facing Changes
  NPRR1093 Loads in Non-Spin
  NPRR863 / FFRA Scope Delivery
  NPRR1120 Create Firm Fuel Service
  NPRR863 / ECRS Scope Delivery
CIM 16 Upgrade
PVGR Forecasts / Reports
NERC EMSWG Update
Retiring Legacy MIS Public Report Functionality
ERCOT WAN Infrastructure Update
Information Only Topics for Awareness
  Operator Real-Time Messaging SCR820
  Public API and API Improvements
  TLS 1.2 Certification
  IE11 EOL and Multiple Cert Workaround in Chromium Browsers
  MarkeTrak System Updates
  Retail API Redesign
  TEXAS SET 5.0 Project
05/19/2022 TWG meeting topics

## Slide 8: “Not Started” Revision Request List
The “Not Started” Revision Requests is being revised to include ERCOT comments and recommendations
  Will be posted on 6/6/2022
Discussion at June PRS will be the review of:
  Items that conflict with critical in-flight initiatives
  Items that may have a pathway to implementation in the next 6-12 months
  Market feedback on priority of the items in #2 above