## Timeline 2022
ERCOT & TDSP AV 2022 Progress Report
Due Date* | 2022 Annual Validation Task List | ERCOT | AEP | CNP | Nueces | ONCOR | TNMP
2022-03-30 | ERCOT to provide list of BUS ESI IDs to TDSPs | 2022-03-31 | 3482745 | 3482739 | 3482759 | 3482729 | 3482752
2022-03-31 | ERCOT Provides Additional Validation Lists to TDSPs | 2022-03-30 | 3494709 | 3494712 | 3494716 | 3494718 | 3494720
2022-04-10 | TDSPs to provide finalized list of BUS ESI IDs to ERCOT | n/a
2022-04-15 | Market Notice announcing lists are available to CR of record | 2022-04-15
2022-04-15 | TDSPs to begin submitting 814_20 transactions | n/a
2022-09-30 | Complete Annual and Additional Validations | n/a | Comp Date | Comp Date | Comp Date | Comp Date | Comp Date
2022-10-03 | ERCOT to review database for expected changes | Comp Date | n/a
2022-10-10 | TDSPs have submitted at least 99% of changes | n/a | Comp Date | Comp Date | Comp Date | Comp Date | Comp Date
Due Date* | 2022 Weather Responsiveness Report Task List | ERCOT | AEP | CNP | Nueces | ONCOR | TNMP
2022-11-02 | ERCOT provide list of ESI IDs to TDSPs requiring changes to Weather Sensitivity (Initial Weather Responsiveness Report) | Comp Date | n/a
Monthly | Monthly Weather Responsiveness Report Produced by ERCOT | Comp Date | n/a
2023-02-02 | TDSPs have submitted at least 99% of changes | n/a | Comp Date | Comp Date | Comp Date | Comp Date | Comp Date
* If the due date falls on a weekend or holiday, please use the next business day as the deadline. | [5 empty] | Updated on | 2022-06-14

## Status
Profile Validation Status as of: |  | 2022-06-13
| AEP |  |  | CNP |  |  | NUECES |  |  | ONCOR |  |  | TNMP
| RES | BUS | Total | RES | BUS | Total | RES | BUS | Total | RES | BUS | Total | RES | BUS | Total
Initial List of Changes |  | 12301 | 12301 |  | 13077 | 13077 |  | 411 | 411 |  | 19068 | 19068 |  | 1811 | 1811
Exceptions |  |  | 151 |  |  | 3 |  |  | 4 |  |  | 0 |  |  | 0
Net Subject to Change |  |  | 12150 |  |  | 13074 |  |  | 407 |  |  | 19068 |  |  | 1811
Updated (As of 6/25/2021) |  |  | 11 |  |  | 12932 |  |  | 3 |  |  | 19068 |  |  | 1163
Remaining |  | 12139 | 12139 |  | 142 | 142 |  | 404 | 404 |  | 0 | 0 |  | 648 | 648
% Completion |  |  | 0.09053% |  |  | 98.91% |  |  | 0.7371% |  |  | 100% |  |  | 64.22%