## Approach - Structure
Contents of this Spreadsheet: |  |  |  | Summary Counts |  | Sub-Totals
| 5 tabs |  |  | Previous List - Complete or In-Flight | 10 | Complete or In-Flight | 22
| 1 | Explanatory information |  | Previous List - Not Started | 29 | Not Started | 63
| 2 | Previous List - Complete or In-Flight |  | New List - Complete or In-Flight | 12
| 3 | Previous List - Not Started (and On Hold) |  | New List - Not Started | 34
| 4 | New List - Complete or In-Flight |  | Total | 85 | Total | 85
| 5 | New List - Not Started (and On Hold)
"Regulatory" sorts to the top of each list
Other items are sorted by Rank
Definitions
"Previous List" = "Not Started" project list reviewed at August 2020 PRS meeting
"New Items" = Items added to the project list after August 2020 (essentially items approved by the Board from October 2020 through April 2022)
Review Timeline:
May PRS
Explanation of project list (contents, definitions, approach to review, etc.)
General discussion - no deep dive into the lists this month
June PRS
Discuss "Not Started" items that ERCOT sees as candidates to be worked in the next 6-12 months
As needed, answer questions on why other items conflict with current critical in-flight projects
PRS discussion on any priority revisions
July PRS
Review updates to the data in this spreadsheet
Added and populated a "Revised Prioritization Recommendation" column in the "Prev List - Not Started" tab
Populated the "Prioritization Category Recommendation" column in the "New Items - Not Started" tab
Populated the "High / Medium / Low" column in the "New Items - Not Started" tab
Updated "ERCOT Recommendation" column to group related scenarios
Highlighted noteworthy changes in yellow
Review ERCOT category recommendations
Resolve any open questions from the June PRS discussion
Homework for June PRS meeting:
Market Participants
Refamiliarize yourself with the contents of the "Previous List" and the "Prioritization Category" assignment made to each item - consider whether any changes should be made
Review the contents of the "New Items - Not Started" list and consider which items need to be moved up the priority order
Consider whether any "Not Started" items may not longer be necessary based on developments since the time of their original approval
ERCOT
Continue populating the "ERCOT Comments" column on the two "Not Started" tabs
Highlight projects that have conflicts with critical in-flight efforts and therefore are candidates to be worked 12 months (or more) in the future
Highlight projects that have limited conflicts with critical in-flight efforts and therefore are candidates to start in upcoming months

## Prev List - Complete or Active
REVISION REQUEST PRIORITIZATION - Previous List - Projects Complete or In-Flight | [14 empty] | Count = 10
Category | Priority | Rank | Prioritization Category | High / Medium / Low | Source Doc | Approval Status | Approval Date | Project Name | Project Status | IA Budget Range | IA Duration Range | Major Impacted System | Major Impacted System % | % Vendor Required | Impacted Systems (Listed on IA) | ERCOT Comments | PRS Comments
Regulatory | 2020 | 300 | 1 - Regulatory | 1 - High | NOGRR195 | PPL | 2020-08-01 | Generator Voltage Control Tolerance Band | Complete | $30k-$50k | 4-6 months | EMS | 67% | 0% | EMS, BI & Data Analytics | Implemented 2021-R1
Revision Requests | 2017 | 1820 | 4 - Consider When Resources are Available | 1 - High | SCR789 | PPL | 2016-08-01 | Update NMMS Topology Processor to PSSE 34 Capability - Phase 1 | Complete | $300k-$450k | 9-12 months | NMMS | 100% | 76% | NMMS | Single IA - split into multiple projects Phase 1 implemented in July 2021
Revision Requests | 2017 | 1820 | 4 - Consider When Resources are Available | 1 - High | SCR789 | PPL | 2016-08-01 | Update NMMS Topology Processor to PSSE 34 Capability - Phase 2 | Planning | $300k-$450k | 9-12 months | NMMS | 100% | 76% | NMMS | Single IA - split into multiple projects Phase 2 target implementation in late 2022
Revision Requests | 2019 | 2700 | 4 - Consider When Resources are Available | 1 - High | NPRR917 | PPL | 2019-08-01 | Nodal Pricing for Settlement Only Distribution Generators (SODGs) and Settlement Only Transmission Generators (SOTGs) | Complete | $300k-$400k | 9-12 months | S&B | 30% | 0% | S&B, Integration, MMS, DAIP, NMMS, CMM, REG, Data Access & Transparency, External Public, BI & Data Analytics | DGR/DESR Implementation - 2022-R1
Revision Requests | 2019 | 2770 | 2 - High Priority | 1 - High | NPRR939 | PPL | 2019-10-01 | Modification to Load Resources Providing RRS to Maintain Minimum PRC on Generators During Scarcity Conditions | Complete | $70k-$100k | 5-7 months | MMS | 70% | 0% | MMS, DAIP, Integration | Implemented 2022-R3 Currently in Stabilization
Revision Requests | 2020 | 2910 | 5 - Consider When Efficiencies Exist With Another Effort | 1 - High | SCR800 | PPL | 2019-12-01 | Addition of DC Tie Ramp to GTBD Calculation | Complete | $30k-$50k | 3-5 months | EMS | 38% | 0% | EMS, Data Management, MMS, BI & Data Analytics | Implemented 2022-R3 Currently in Stabilization
Revision Requests | 2020 | 2980 | 2 - High Priority | 1 - High | NPRR974 | PPL | 2020-02-01 | Capacity Insufficiency Operating Condition Notice (OCN) Transparency | Complete | $50k-$80k | 5-7 months | DAIP | 62% | 0% | DAIP, MMS, External Public | Implemented 2021-R3 | Can NPRR975 be worked alongside NPRR974?
Revision Requests | 2020 | 3040 | 5 - Consider When Efficiencies Exist With Another Effort | 2 - Medium | SCR809 | PPL | 2020-06-01 | Changes to External Telemetry Validations in Resource Limit Calculator | Complete | $40k-$60k | 4-6 months | EMS | 83% | 0% | EMS, BI & Data Analytics | Implemented 2022-R3 Currently in Stabilization
Revision Requests | 2020 | 3070 | 3 - Needed prior to RTC | 1 - High | NPRR1016 | PPL | 2020-08-01 | Clarify Requirements for Distribution Generation Resources (DGRs) and Distribution Energy Storage Resources (DESRs) | Complete | $400k-$550k | 12-18 months | OS | 41% | 16% | OS, EMS, BI & Data Analytics, DAIP, MMS, REG, NMMS, Integration | DGR/DESR Implementation - 2022-R1
Revision Requests | 2021 | 3220 | 4 - Consider When Resources are Available | 2 - Medium | NPRR1020 | PPL | 2020-08-01 | Allow Some Integrated Energy Storage Designs to Calculate Internal Loads - EPS Metering | Execution | $175k-$225k | 8-12 months | EPS Meter | 86% | 0% | EPS Meter | Single IA - split into multiple projects Specific resources were available for this portion of NPRR1020

## Prev List - Not Started
REVISION REQUEST PRIORITIZATION - Previous List - Projects Not Started | [15 empty] | Count = 29
Category | Priority | Rank | Prioritization Category | Revised Prioritization Recommendation | High / Medium / Low | Source Doc | Approval Status | Approval Date | Project Name | Project Status | IA Budget Range | IA Duration Range | Major Impacted System | Major Impacted System % | % Vendor Required | Impacted Systems (Listed on IA) | ERCOT Recommendation | ERCOT Comments / Additional Detail | PRS Comments
Revision Requests | 2018 | 2090 | 6 - Dependent on Other Project | 5 - Dependent on Other Project | 2 - Medium | NPRR825 | PPL | 2017-12-01 | Require ERCOT to Issue a DC Tie Curtailment Notice Prior to Curtailing any DC Tie Load | Not Started | $200k-$300k | 8-12 months | MMS | 82% | 0% | MMS, Data Access & Transparency, DAIP, Integration | 9 - TBD | Dependent on internal ERCOT project with no clear timeline Partial delivery in Oct. 2018
Revision Requests | 2019 | 2510 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 1 - High | NPRR829 | PPL | 2017-10-01 | Incorporate Real-Time Non-Modeled Telemetered Net Generation by Load Zone into the Estimate of RTL | On Hold | $200k-$300k | 5-10 months | CMM | 26% | 0% | CMM, NMMS, EMS, REG, Integration, DAIP, Data Access & Transparency | 9 - TBD | We would like to get this On Hold effort going again in 2022 but we need to figure out resource constraints with Securitization and the Treasury Management project first
Revision Requests | 2020 | 2515 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 1 - High | NPRR1030 | PPL | 2020-08-01 | Modify Allocator for CRR Auction Revenue Distribution | Not Started | $175k-$225k | 8-12 months | S&B | 74% | 0% | S&B, DAIP, CMM, Integration | 5 - After EMS Upgrade, which has a target go-live of mid-2024 | Lower priority then Securitization Manual workaround in place to monitor market activity
Revision Requests | 2019 | 2520 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 3 - Low | NPRR841 | PPL | 2018-02-01 | Real-Time Adjustments to Day-Ahead Make Whole Payments due to Ancillary Services Infeasibility Charges | Not Started | $60k-$80k | 4-6 months | S&B | 88% | 0% | S&B, Integration, Data Access & Transparency, CRM & Registration System | 6 - Candidate for deletion |  | Consider filing an NPRR to strike the grey-boxes for NPRR841 (or let RTC NPRRs strike it)
Revision Requests | 2019 | 2530 | 6 - Dependent on Other Project | 5 - Dependent on Other Project | 2 - Medium | NPRR857 | PPL | 2018-10-01 | Creation of Direct Current Tie Operator Market Participant Role | Not Started | $500k-$700k | 12-18 months | OS | 53% | 25% | OS, EMS, OTS, WAN, NMMS, External Public, Integration, BI & Data Analytics, REG, Data Access & Transparency, DAIP | 4 - Begin project upon satisfaction of required Southern Cross provisions | Southern Cross funding
Revision Requests | 2019 | 2580 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 3 - Low | PGRR066 | PPL | 2018-12-01 | Interconnection Request Cancellation and Creation of Inactive Status | Not Started | $100k-$150k | 4-6 months | RIOO | 100% | 0% | Resource Integration | 3 - 2023 project candidate | Potential inclusion in a RIOO enhancement project after RARF Replacement is complete ERCOT can keep the existing manual workaround until resources are available
Revision Requests | 2019 | 2710 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 1 - High | SCR799 | PPL | 2019-06-01 | ERCOT Outage Study Cases in the System Operations Test Environment (SOTE) | Not Started | $150k-$250k | 5-7 months | SOTE | 100% | 0% | SOTE | 5 - After EMS Upgrade, which has a target go-live of mid-2024 | Material impact on EMS Production Support team Low probability of fitting this into the plan in advance of the EMS Upgrade system freeze
Revision Requests | 2019 | 2720 | 2 - High Priority | 2 - High Priority | 1 - High | NPRR904 | PPL | 2019-08-01 | Revisions to Real-Time On-Line Reliability Deployment Price Adder for ERCOT-Directed Actions Related to DC Ties and to Correct Design Flaws | On Hold | $200k-$300k | 6-9 months | MMS | 85% | 41% | MMS, EMS, BI & Data Analytics, DAIP | 3 - 2023 project candidate | Preference has been to try and bundle changes impacting RDPA. Need to be aware of making a project too large such that it can't fit into a release window.
Revision Requests | 2019 | 2720 | 2 - High Priority | 2 - High Priority | 1 - High | OBDRR009 | PPL | 2019-08-01 | ORDC OBD Revisions for ERCOT-Directed Actions Related to DC Ties | On Hold | $30k-$50k | 4-6 months | MMS | 40% | 0% | MMS, DAIP, BI & Data Analytics | 3 - 2023 project candidate | Preference has been to try and bundle changes impacting RDPA. Need to be aware of making a project too large such that it can't fit into a release window.
Revision Requests | 2020 | 2800 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 2 - Medium | NPRR879 | PPL | 2018-12-01 | SCED Base Point, Base Point Deviation, and Performance Evaluation Changes for IRRs that Carry Ancillary Services | Not Started | $200k-$250k | 6-9 months | DAIP | 46% | 0% | DAIP, S&B, BI & Data Analytics, EMS, NMMS, Integration | 3 - 2023 project candidate | Moved to 2023 - this cleared resources for higher priority reporting efforts such as NPRR1097, NPRR1040, and SCR812
Revision Requests | 2020 | 2815 | 2 - High Priority | 2 - High Priority | 1 - High | NPRR963 | PPL | 2020-02-01 | Base Point Deviation Settlement and Deployment Performance Metrics for Energy Storage Resources (Combo Model) | On Hold | $150k-$200k | 8-12 months | DAIP | 31% | 0% | DAIP, S&B, EMS, BI & Data Analytics, Integration | 3 - 2023 project candidate | Battery Energy Storage (BES) PR353-01 component This work that can't be fit into the plan until after ECRS implementation
Revision Requests | 2020 | 2840 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 2 - Medium | NPRR918 | PPL | 2019-10-01 | Validation for PTP Obligations with Links to an Option | Not Started | $30k-$50k | 4-6 months | MMS | 57% | 0% | MMS, DAIP, Integration | 3 - 2023 project candidate | This NPRR introduces hourly submission validation versus current peak load value based validation.
Revision Requests | 2020 | 2850 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 3 - Low | NPRR936 | PPL | 2019-10-01 | CRR Account Holder Limits | Not Started | $150k-$250k | 8-10 months | CRR | 90% | 51% | CRR, DAIP | 3 - 2023 project candidate | CRR items: NPRR936, NPRR1023, SCR807, SCR816 Too large and risky to run all 4 RRs as a single project Highest impact/value are SCR807 and SCR816 (CRR Proj 1) NPRR936 and NPRR1023 could follow in 2023 (CRR Proj 2)
Revision Requests | 2020 | 2855 | 4 - Consider When Resources are Available | 2 - High Priority | 1 - High | SCR807 | PPL | 2020-06-01 | Increase CRR Transaction Capability | Not Started | $50k-$100k | 5-7 months | CRR | 95% | 60% | CRR, Integration | 1 - Planned for 2022 start | Q3 2022 start CRR items: NPRR936, NPRR1023, SCR807, SCR816 Too large and risky to run all 4 RRs as a single project Highest impact/value are SCR807 and SCR816 (CRR Proj 1) NPRR936 and NPRR1023 could follow in 2023 (CRR Proj 2)
Revision Requests | 2020 | 2860 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 3 - Low | NPRR941 | PPL | 2019-12-01 | Create a Lower Rio Grande Valley Hub | Not Started | $250k-$350k | 6-8 months | MMS | 91% | 75% | MMS, DAIP, EMS, External Public | 7 - Market input requested | Consistent with the August 2020 discussion, this is lower priority and can be reconsidered when critical efforts are complete
Revision Requests | 2020 | 2870 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 2 - Medium | NPRR962 | PPL | 2019-10-01 | Publish Approved DC Tie Schedules | Not Started | $15k-$30k | 3-4 months | DAIP | 86% | 0% | DAIP, BI & Data Analytics | 7 - Market input requested | Impact is relatively low and limited to reporting. Data seems useful but the usefulness is dependent on the market participants' points of view.
Revision Requests | 2020 | 2890 | 2 - High Priority | 2 - High Priority | 1 - High | NPRR930 | PPL | 2019-10-01 | Process Pricing and Cost Recovery for Delayed Resource Outages | On Hold | $100k-$200k | 5-7 months | MMS | 74% | 39% | MMS, OS, DAIP, Data Access & Transparency, External Public | 7 - Market input requested | Partially implemented. Remaining component has a work-around that's a behavior rule for QSEs.
Revision Requests | 2020 | 2900 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 1 - High | NPRR965 | PPL | 2019-12-01 | GREDP Shutdown Exemption | Not Started | $10k-$20k | 3-5 months | BI & Data Analytics | 100% | 0% | BI & Data Analytics | 9 - TBD | Consider bundling this with NPRR879 which also has a BI & Data Analytics portion that impacts GREDP.
Revision Requests | 2020 | 2920 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 2 - Medium | SCR805 | PPL | 2019-12-01 | Provide Early Access to Certain 60-Day Reports to TSPs Upon Request | Not Started | $40k-$60k | 4-6 months | DAIP | 97% | 0% | DAIP, Data Access & Transparency | 7 - Market input requested
Revision Requests | 2020 | 2970 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 2 - Medium | NPRR826 | PPL | 2020-02-01 | Mitigated Offer Caps for RMR Resources | Not Started | $100k-$200k | 6-8 months | MMS | 70% | 68% | MMS, DAIP, External Public, Data Access & Transparency | 7 - Market input requested | Priority is less clear due to not currently having any RMR contracts in place.
Revision Requests | 2020 | 3000 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 2 - Medium | NPRR975 | PPL | 2020-06-01 | Load Forecast Model Transparency | Not Started | $75k-$100k | 6-9 months | EMS | 58% | 0% | EMS, DAIP, BI & Data Analytics | 9 - TBD | ERCOT is evaluating options for replacing the A3 and A6 models.
Revision Requests | 2020 | 3010 | 2 - High Priority | 2 - High Priority | 1 - High | NPRR987 | PPL | 2020-06-01 | BESTF-3 Energy Storage Resource Contribution to Physical Responsive Capability and Real-Time On-Line Reserve Capacity Calculations | On Hold | $150k-$200k | 6-9 months | MMS | 34% | 9% | MMS, S&B, EMS, Integration, BI & Data Analytics, DAIP | 3 - 2023 project candidate | Battery Energy Storage (BES) PR353-01 component "ESR Contribution to PRC" already in-flight targeting 2022-R5 This row represents the remaining work that can't be fit into the plan until after ECRS implementation
Revision Requests | 2020 | 3020 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 1 - High | NPRR1006 | PPL | 2020-06-01 | Update Real-Time On-Line Reliability Deployment Price Adder Inputs to Match Actual Data | On Hold | $140k-$180k | 6-9 months | MMS | 62% | 29% | MMS, DAIP, EMS, S&B, BI & Data Analytics | 3 - 2023 project candidate | Preference has been to try and bundle changes impacting RDPA. Need to be aware of making a project too large such that it can't fit into a release window.
Revision Requests | 2020 | 3030 | 2 - High Priority | 2 - High Priority | 1 - High | NPRR1019 | PPL | 2020-06-01 | Pricing and Settlement Changes for Switchable Generation Resources (SWGRs) Instructed to Switch to ERCOT | On Hold | $100k-$140k | 5-7 months | MMS | 98% | 44% | MMS, BI & Data Analytics | 7 - Market input requested | Partially implemented. Remaining component has a work-around that's a behavior rule for QSEs.
Revision Requests | 2020 | 3050 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 2 - Medium | SCR810 | PPL | 2020-08-01 | EMS System Change to Count DC Ties towards the 2% Constraint Activation Criterion | Not Started | $15k-$25k | 3-5 months | EMS | 100% | 0% | EMS | 9 - TBD | This SCR adds logic to ERCOT’s EMS system to remove the flag that indicates to the ERCOT Operator that a unit representing a DC Tie does not count toward the 2% criterion for activating transmission constraints
Revision Requests | 2020 | 3060 | 3 - Needed prior to RTC | 3 - Consider When Resources are Available | 1 - High | NPRR1002 | PPL | 2020-08-01 | BESTF-5 Energy Storage Resource Single Model Registration and Charging Restrictions in Emergency Conditions | On Hold | $100k-$200k | 7-10 months | RIOO | 83% | 0% | Resource Integration, Integration, DAIP | 2 - Seek opportunity to deliver this in 2022/2023 without negatively impacting critical in-flight projects | Battery Energy Storage (BES) PR353-01 component "Charging Restrictions in Emergency Conditions" already in-flight targeting 2022-R5 This row is a potential stand-alone project to run alongside RARF Replacement to leverage resources as they become free for development and testing by end of 2022
Revision Requests | 2021 | 3200 | 5 - Consider When Efficiencies Exist With Another Effort | 4 - Consider When Efficiences Exist With Another Effort | 1 - High | PGRR076 | PPL | 2020-08-01 | Improvements to Generation Resource Interconnection or Change Request (GINR) Process | Not Started | $50k-$75k | 6-9 months | RIOO | 57% | 0% | Resource Integration, Integration, Data Access & Transparency | 3 - 2023 project candidate | Potential inclusion in a RIOO enhancement project after RARF Replacement is complete
Revision Requests | 2021 | 3210 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 2 - Medium | NPRR1004 | PPL | 2020-08-01 | Load Distribution Factor Process Update | Not Started | $45k-$65k | 5-7 months | MMS | 41% | 0% | MMS, Integration, DAIP, External Public | 2 - Seek opportunity to deliver this in 2022/2023 without negatively impacting critical in-flight projects | IMM has asked about the status of this RR MMS impacts
Revision Requests | 2021 | 3220 | 4 - Consider When Resources are Available | 3 - Consider When Resources are Available | 2 - Medium | NPRR1020 | PPL | 2020-08-01 | Allow Some Integrated Energy Storage Designs to Calculate Internal Loads - Data Agg | Not Started | $175k-$225k | 8-12 months | EPS Meter | 86% | 0% | S&B | 5 - After EMS Upgrade, which has a target go-live of mid-2024 | Data Agg portion of NPRR1020 Same solution is available with current EPS meter configuration schemes EPS Metering portion is already in-flight

## New Items - Complete or Active
REVISION REQUEST PRIORITIZATION - New Items - Projects Complete or In-Flight | [14 empty] | Count = 12
Category | Priority | Rank | Prioritization Category | High / Medium / Low | Source Doc | Approval Status | Approval Date | Project Name | Project Status | IA Budget Range | IA Duration Range | Major Impacted System | Major Impacted System % | % Vendor Required | Impacted Systems (Listed on IA) | ERCOT Comments | PRS Comments
Regulatory | 2022 | 310 | 1 - Regulatory |  | PGRR099 | PPL | 2022-03-31 | Revise GIM Process to Ensure Compliance with the Lone Star Infrastructure Protection Act | Execution | $20k - $30k | 3 - 5 months | RIOO | 100% | 0% | Resource Integration and Ongoing Operations
Securitization | 2021 | 320 | 1 - Regulatory |  | NPRR1103 | PPL | 2021-12-16 | Securitization – PURA Subchapter M Default Charges | Execution | $1.5M - $2M | 18 - 26 months | S&B | 74% | 0% | Credit Management Systems (CMM), Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems, Financial Management Systems, Integration Systems | Manual solution implemented Automation project expected to start later in 2022
Securitization | 2022 | 320 | 1 - Regulatory |  | NPRR1114 | PPL | 2022-03-31 | Securitization – PURA Subchapter N Uplift Charges | Execution | $1.8M - $2.4M | 18 - 24 months | S&B | 62% | 0% | Credit Management Systems (CMM), Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems, Financial Management Systems, Integration Systems | Implemented late March 2022 Currently in Stabilization Included NPRR1122, NPRR1123, and NPRR1125
Regulatory | 2022 | 320 | 1 - Regulatory |  | NPRR1108 | PPL | 2022-04-28 | ERCOT Shall Approve or Deny All Resource Outage Requests | Execution | $275k-$375k | 7-10 months | OS | 58% | 27% | Content Delivery Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems, Grid Decision Support Systems, Outage Management Systems | Target implementation - 2022-R4
Regulatory | 2022 | 330 | 1 - Regulatory |  | NPRR1120 | PPL | 2022-03-31 | Create Firm Fuel Supply Service | Planning | $250k-$400k | 9-12 months | S&B | 70% | 0% | Channel Management Systems, Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, Integration Systems, Market Operation Systems | Expected implementation in Q4 2022
Revision Requests | 2021 | 2705 |  |  | NPRR1051 | PPL | 2021-02-09 | Removal of the Price Floor Applied to Day-Ahead Settlement Point Prices | Complete | $10k-$20k | 3-5 months | MMS | 100% | 0% | Market Operation Systems | Implemented 2021-R3
Revision Requests | 2020 | 3010 |  |  | NPRR1026 | PPL | 2020-12-08 | BESTF-7 Self-Limiting Facilities | Execution | $200k-$250k | 7-10 months | RIOO | 58% | 0% | RIOO-RS, EMS, OTS, DAIP, External Public | RIOO portion is in progress
Revision Requests | 2020 | 3070 |  |  | PGRR082 | PPL | 2020-12-08 | Revise Planning Guide Section 5 and Establish Small Generation Interconnection Process | Complete | $700k-$900k | 18-24 months | RIOO | 92% | 0% | RIOO-RS, NMMS, DAIP | DGR/DESR Implementation - 2022-R1
Revision Requests | 2020 | 3080 |  |  | SCR811 | PPL | 2020-10-13 | Integrate Solar (PVGR) Forecasts and Addition of Intra-Hour PhotoVoltaic Power Forecast to GTBD Calculation | Complete | $60k-$90k | 5-7 months | MMS | 76% | 35% | MMS, EMS | Implemented 2021-R3
Revision Requests | 2021 | 3195 |  |  | NPRR1093 | PPL | 2021-10-28 | Load Resource Participation in Non-Spinning Reserve | Complete | $480k - $700k | 9 - 12 months | MMS | 68% | 29% | Content Delivery Systems, Credit Settlements & Billing Systems, Data Management & Analytic Systems, Energy Management Systems, ERCOT Website and MIS Systems, Grid Decision Support Systems, Integration Systems, Market Operation Systems | Implemented 2022-R3 Currently in Stabilization
Revision Requests | 2021 | 3340 |  |  | NPRR1081 | PPL | 2021-06-28 | Revisions to Real-Time Reliability Deployment Price Adder to Consider Firm Load Shed | Complete | $25k - $45k | 2 - 3 months | MMS | 45% | 0% | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems | Manual solution implemented on 7/1/2021 Automation completed in September 2021
Revision Requests | 2021 | 3350 |  |  | SCR814 | PPL | 2021-10-28 | Point-to-Point (PTP) Obligation Bid Interval Limit | Complete | $10k-$25k | 3 - 5 months | MMS | 100% | 0% | Market Operation Systems | Implemented 2022-R3 Currently in Stabilization

## New Items - Not Started
REVISION REQUEST PRIORITIZATION - New Items - Projects Not Started | [14 empty] | Count = 34
Category | Priority | Rank | Prioritization Category Recommendation | High / Medium / Low | Source Doc | Approval Status | Approval Date | Project Name | Project Status | IA Budget Range | IA Duration Range | Major Impacted System | Major Impacted System % | % Vendor Required | Impacted Systems (Listed on IA) | ERCOT Recommendation | ERCOT Comments / Additional Details | PRS Comments
Regulatory | 2020 | 235 | 1 - Regulatory | 1 - High | NPRR1007 | PPL | 2020-12-08 | Real-Time Co-Optimization (RTC) | On Hold | $50M-$55M | 3.5-4.5 years | MMS | 53% | 24% | MMS, EMS, Integration, DAIP, S&B, NMMS, CMM, OTS, Registration | 9 - TBD | Pending further direction from PUCT Represents NPRRs 1007-1013, NOGRR211, and OBDRR020
Regulatory | 2022 | 325 | 1 - Regulatory | 1 - High | NPRR1097 | PPL | 2022-03-31 | Create Resource Forced Outage Report | Not Started | $20k-$40k | 3-5 months | DAIP | 90% | 0% | Data Management & Analytic Systems, ERCOT Website and MIS Systems | 1 - Planned for 2022 start | Q3 2022 start Need to implement by end of 2022 to meet PUCT target Reporting priorities adjusted to make capacity available for this report (see NPRR879 on 3rd tab)
Revision Requests | 2022 | 2530 | 9 - No Action Needed | 2 - Medium | NPRR1098 | PPL | 2022-03-31 | DC Tie Reactive Power Capability Requirements | Not Started | $10k - $20k | 3 - 5 months | BI & Data Analytics | 100% | 0% | Grid Decision Support Systems | 4 - Begin project upon satisfaction of required Southern Cross provisions | Southern Cross funding
Revision Requests | 2022 | 2650 | 2 - High Priority | 1 - High | NPRR1096 | PPL | 2022-03-31 | Require Sustained Two-Hour Capability for ECRS and Four-Hour Capability for Non-Spin | Not Started | $30k - $50k | 3 - 5 months | NDCRC | 65% | 0% | Energy Management Systems, Grid Decision Support Systems, Grid Modeling Systems | 2 - Seek opportunity to deliver this in 2022/2023 without negatively impacting critical in-flight projects | ECRS portion - 2023 Non-Spin portion - 2022 candidate
Revision Requests | 2022 | 2855 | 4 - Consider When Efficiences Exist With Another Effort | 1 - High | SCR816 | PPL | 2022-03-31 | CRR Auction Bid Credit Enhancement | Not Started | $50k - $80k | 4 - 6 months | CRR | 100% | 52% | Congestion Revenue Rights (CRR) | 1 - Planned for 2022 start | Q3 2022 start CRR items: NPRR936, NPRR1023, SCR807, SCR816 Too large and risky to run all 4 RRs as a single project Highest impact/value are SCR807 and SCR816 (CRR Proj 1) NPRR936 and NPRR1023 could follow in 2023 (CRR Proj 2)
Revision Requests | 2022 | 3005 | 2 - High Priority | 1 - High | NPRR1092 | PPL | 2022-04-28 | Reduce RUC Offer Floor and Limit RUC Opt-Out Provision | Not Started | $50k - $100k | 4 - 6 months | MMS | 100% | 0% | Channel Management Systems, Content Delivery Systems, Credit Settlements & Billing Systems, Data Management & Analytic Systems, Energy Management Systems, ERCOT Website and MIS Systems, Market Operation Systems | 2 - Seek opportunity to deliver this in 2022/2023 without negatively impacting critical in-flight projects | "Reduce RUC Offer Floor" change implemented on 5/13/2022 This project implements the "Limit RUC Opt-Out Provision" portion
Revision Requests | 2020 | 3015 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1014 | PPL | 2020-12-08 | BESTF-4 Energy Storage Resource Single Model | Not Started | $3.5M-$4.5M | 2-3 years | EMS | 60% | 49% | EMS, MMS, DAIP, S&B, OS, Integration, NMMS, RIOO, Registration | 5 - After EMS Upgrade, which has a target go-live of mid-2024 | NPRR was written with RTC design. This work can't be fit in to the plan until after EMS upgrade.
Revision Requests | 2020 | 3015 | 9 - No Action Needed | 2 - Medium | NPRR1029 | PPL | 2020-12-08 | BESTF-6 DC-Coupled Resources | Not Started | $800k-$1.2M | 16-24 months | EMS | 33% | 36% | EMS, OS, S&B, MMS, RIOO, Integration, DAIP, OTS, NMMS, Registration | 5 - After EMS Upgrade, which has a target go-live of mid-2024 | NPRR was written with RTC design. This work can't be fit in to the plan until after EMS upgrade.
Revision Requests | 2022 | 3020 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1105 | PPL | 2021-12-16 | Option to Deploy Distribution Voltage Reduction Measures Prior to Energy Emergency Alert (EEA) - Phase 2 | Not Started | $80k - $120k | 6 - 9 months | MMS | 55% | 27% | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems | 3 - 2023 project candidate | Preference has been to try and bundle changes impacting RDPA. Need to be aware of making a project too large such that it can't fit into a release window.
Revision Requests | 2022 | 3195 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1091 | PPL | 2021-12-16 | Changes to Address Market Impacts of Additional Non-Spin Procurement | Not Started | $120k - $160k | 7 - 10 months | MMS | 73% | 40% | Data Management & Analytic Systems, Energy Management Systems, Market Operation Systems | 3 - 2023 project candidate | Preference has been to try and bundle changes impacting RDPA. Need to be aware of making a project too large such that it can't fit into a release window.
Revision Requests | 2021 | 3230 | 4 - Consider When Efficiences Exist With Another Effort | 2 - Medium | NPRR1035 | PPL | 2020-10-13 | DC Tie Schedules Protected Information Expiry and Posting | Not Started | $20k-$40k | 3-5 months | DAIP | 83% | 0% | DAIP, External Public | 7 - Market input requested | Impact is relatively low and limited to reporting. Data seems useful but the usefulness is dependent on the market participants' points of view.
Revision Requests | 2021 | 3250 | 3 - Consider When Resources are Available | 1 - High | SCR812 | PPL | 2020-12-08 | Create Intermittent Renewable Generation Integration Report | Not Started | $30k-$60k | 5-7 months | DAIP | 68% | 0% | DAIP, Reporting | 1 - Planned for 2022 start | Q3 2022 start Reporting priorities adjusted to make capacity available for this report (see NPRR879 on 3rd tab)
Revision Requests | 2021 | 3260 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1032 | PPL | 2020-12-08 | Consideration of Physical Limits of DC Ties in RUC Optimization and Settlements | Not Started | $100k-$150k | 5-8 months | MMS | 64% | 32% | MMS, S&B, DAIP, Integration | 3 - 2023 project candidate | Addresses a known operational issue/inefficiency
Revision Requests | 2021 | 3270 | 3 - Consider When Resources are Available | 2 - Medium | NPRR945 | PPL | 2020-12-08 | Net Metering Requirements | Not Started | $10k-$20k | 3-4 months | RIOO | 64% | 0% | RIOO-RS, External Public | 3 - 2023 project candidate | Potential inclusion in a RIOO enhancement project after RARF Replacement is complete
Revision Requests | 2021 | 3280 | 9 - No Action Needed | 2 - Medium | NPRR1034 | PPL | 2021-02-09 | Frequency-Based Limits on DC Tie Imports or Exports | Not Started | $50k-$70k | 5-7 months | Pi | 64% | 0% | Pi, EIS, NoticeBuilder, MIS | 4 - Begin project upon satisfaction of required Southern Cross provisions | Southern Cross funding
Revision Requests | 2021 | 3290 | 3 - Consider When Resources are Available | 1 - High | NPRR1040 | PPL | 2021-02-09 | Compliance Metrics for Ancillary Service Supply Responsibility | Not Started | $20k-$30k | 3-5 months | BI & Data Analytics | 90% | 0% | Data Management & Analytic Systems | 1 - Planned for 2022 start | Q3 2022 start Reporting priorities adjusted to make capacity available for this report (see NPRR879 on 3rd tab)
Revision Requests | 2021 | 3300 | 9 - No Action Needed | 3 - Low | NPRR1054 | PPL | 2021-02-09 | Removal of Oklaunion Exemption Language | Not Started | $10k-$15k | 3-4 months | S&B | 50% | 0% | Credit Settlements & Billing Systems, Integration Systems | 8 - Work into other projects where possible | Not urgent Work this into other projects where possible
Revision Requests | 2021 | 3310 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1057 | PPL | 2021-04-13 | Modification to Real-Time Hub Price Formulas for Fully De-Energized Hubs | Not Started | $20k - $30k | 3 - 5 months | MMS | 100% | 0% | Market Operation Systems | 3 - 2023 project candidate | Impact is relatively low and would like to address this issue, even though it's a low probability event
Revision Requests | 2021 | 3330 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1063 | PPL | 2021-08-19 | Dynamic Rating Transparency | Not Started | $15k - $25k | 3 - 4 months | MIS | 100% | 0% | ERCOT Website and MIS Systems | 1 - Planned for 2022 start | Q4 2022 start Posting the proposed information will increase transparency of these changes and thereby improve Market Participants’ ability to assess and hedge risk
Revision Requests | 2021 | 3360 | 2 - High Priority | 1 - High | NPRR1090 | PPL | 2021-10-28 | ERS Winter Storm Uri Lessons Learned Changes and Other ERS Items | Not Started | $15k - $25k | 3 - 5 months | MMS | 71% | 0% | Data Management & Analytic Systems, Market Operation Systems | 2 - Seek opportunity to deliver this in 2022/2023 without negatively impacting critical in-flight projects | Impact is relatively low and would like to address this issue.
Revision Requests | 2022 | 3500 | 3 - Consider When Resources are Available | 1 - High | NPRR1023 | PPL | 2021-04-13 | Change to CRR Repossession Process | Not Started | $250k - $350k | 10 - 14 months | CRR | 100% | 65% | Congestion Revenue Rights (CRR) | 3 - 2023 project candidate | CRR items: NPRR936, NPRR1023, SCR807, SCR816 Too large and risky to run all 4 RRs as a single project Highest impact/value are SCR807 and SCR816 (CRR Proj 1) NPRR936 and NPRR1023 could follow in 2023 (CRR Proj 2)
Revision Requests | 2022 | 3510 | 3 - Consider When Resources are Available | 2 - Medium | PGRR088 | PPL | 2021-06-08 | Include Financial Security Amount in the Monthly Generator Interconnection Status Report | Not Started | $20k- $40k | 3 - 5 months | RIOO | 53% | 0% | Data Management & Analytic Systems, Resource Integration and Ongoing Operations | 3 - 2023 project candidate | Desired to start after completion of NMMS Tech Health project - Q1 2023
Revision Requests | 2022 | 3510 | 3 - Consider When Resources are Available | 2 - Medium | SCR813 | PPL | 2021-10-28 | NMMS Jointly-Rated Equipment Coordination Confirmation | Not Started | $100k - $150k | 5 - 7 months | NMMS | 100% | 40% | Network Management Systems | 3 - 2023 project candidate | Desired to start after completion of NMMS Tech Health project - Q1 2023
Revision Requests | 2022 | 3520 | 3 - Consider When Resources are Available | 2 - Medium | RRGRR028 | PPL | 2021-08-19 | Transformer Impedance Clarifications | Not Started | $100k - $150k | 7 - 10 months | RIOO | 93% | 0% | Data Management & Analytic Systems, Resource Integration and Ongoing Operations | 3 - 2023 project candidate | Potential inclusion in a RIOO enhancement project after RARF Replacement is complete
Revision Requests | 2022 | 3530 | 3 - Consider When Resources are Available | 2 - Medium | PGRR091 | PPL | 2021-08-19 | FIS Application Completion 60-Day Limit | Not Started | $15k - $30k | 3 - 5 months | RIOO | 100% | 0% | Resource Integration and Ongoing Operations | 3 - 2023 project candidate | Potential inclusion in a RIOO enhancement project after RARF Replacement is complete
Revision Requests | 2022 | 3540 | 3 - Consider When Resources are Available | 2 - Medium | PGRR094 | PPL | 2021-10-28 | Clarify Notification Requirement for Generator Construction Commencement or Completion | Not Started | $10k - $20k | 1 - 2 months | RIOO | 100% | 0% | Resource Integration and Ongoing Operations | 3 - 2023 project candidate | Potential inclusion in a RIOO enhancement project after RARF Replacement is complete
Revision Requests | 2022 | 3550 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1077 | PPL | 2021-12-16 | Extension of Self-Limiting Facility Concept to Settlement Only Generators (SOGs) and Telemetry Requirements for SOGs | Not Started | $100k - $160k | 7 - 10 months | RIOO | 46% | 0% | Energy Management Systems, Grid Modeling Systems, Resource Integration and Ongoing Operations | 3 - 2023 project candidate | Potential inclusion in a RIOO enhancement project after RARF Replacement is complete
Revision Requests | 2022 | 3570 | 2 - High Priority | 2 - Medium | SCR819 | PPL | 2022-03-31 | Improving IRR Control to Manage GTC Stability Limits | Not Started | $40k - $60k | 4 - 6 months | EMS | 70% | 0% | Energy Management Systems, Market Operation Systems | 2 - Seek opportunity to deliver this in 2022/2023 without negatively impacting critical in-flight projects | This SCR will improve the dispatch of Base Points to Resources to account for the ramping of uncurtailed IRRs and will reduce the chance of violating Generic Transmission Limits (GTLs)
Revision Requests | 2022 | 3590 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1121 | Pending PUCT Approval |  | Add a Posting Requirement to the Exceptional Fuel Cost Submission Process | Not Started | $25k - $45k | 3 - 5 months | DAIP | 85% | 0% | Channel Management Systems, Data Management & Analytic Systems, ERCOT Website and MIS Systems | 2 - Seek opportunity to deliver this in 2022/2023 without negatively impacting critical in-flight projects | Impact is relatively low and limited to reporting. Would like to address this manual process.
Revision Requests | 2023 | 3700 | 3 - Consider When Resources are Available | 1 - High | NPRR1095 | PPL | 2022-03-31 | Texas SET V5.0 Changes | Not Started | $1.0M - $1.5M | 16 - 20 months | Registration | 80% | 0% | CRM & Registration Systems, Data Management & Analytic Systems, Integration Systems, Retail Systems | 1 - Planned for 2022 start | Q3 2022 start Align with restart of MCT Requirement defining in 2022 Development underway in 2023 Testing and Go-live expected in first half of 2024
Revision Requests | 2023 | 3700 | 3 - Consider When Resources are Available | 1 - High | SCR817 | PPL | 2022-03-31 | Related to NPRR1095 MarkeTrak Validation Revisions Aligning with Texas SET V5_0 | Not Started | $400k - $600k | 10 - 15 months | Retail | 65% | 0% | CRM & Registration Systems, Integration Systems, Retail Systems | 1 - Planned for 2022 start | Q3 2022 start Align with restart of MCT Requirement defining in 2022 Development underway in 2023 Testing and Go-live expected in first half of 2024
Revision Requests | 2023 | 3710 | 3 - Consider When Resources are Available | 1 - High | SCR818 | PPL | 2022-04-28 | Changes to Incorporate GIC Modeling Data into Existing Modeling Applications | Not Started | $300k - $500k | 9 - 12 months | NMMS | 100% | 64% | Grid Modeling Systems | 1 - Planned for 2022 start | Q4 2022 start Desired to be split into two efforts: 1 - NMMS data collection (Q4 2022 start) 2 - MOD data collection and software enhancements (Q2 2023 start)
Revision Requests | 2023 | 3720 | 3 - Consider When Resources are Available | 2 - Medium | NPRR1131 | Pending Board Approval |  | Controllable Load Resource Participation in Non-Spin | Not Started | $100k - $150k | 6 - 9 months | MMS | 40% | 0% | Credit Settlements & Billing Systems, Energy Management Systems, Grid Decision Support Systems, Market Operation Systems | 3 - 2023 project candidate | Target 2023 start after ECRS implementation Revisit if there is an increase in the number of CLRs that are qualified to participate in Non-Spin
Revision Requests | 2025 | 4500 | 9 - No Action Needed | 2 - Medium | NPRR995 | PPL | 2021-08-19 | RTF-6 Create Definition and Terms for Settlement Only Energy Storage | Not Started | $800k-$1.2M | 20-30 months | RIOO | 44% | 4% | Credit Settlements & Billing Systems, CRM & Registration Systems, Data Management & Analytic Systems, Energy Management Systems, Integration Systems, Market Operation Systems, Network Management Systems, Resource Integration and Ongoing Operations | 9 - TBD | 2025 Priority