## Slide 1
Project Update
July 13, 2022
Troy Anderson
ERCOT Portfolio Management

## Slide 2
  Recent / Upcoming Project Highlights
  2022 Release Targets
  In-Flight Strategic Projects
    Fast-Frequency Response (FFR) Advancement
    NPRR1120 Create Firm Fuel Supply Service
  Priority/Rank Options for Revision Requests with Impacts
    NPRR1085 – Ensuring Continuous Validity of PRC and Dispatch through Timely Changes to Resource Telemetry and COPs
    NPRR1135 – Add On-Line Status Check for Resources Telemetering OFFNS for AS Imbalance Settlements
    NPRR1136 – Updates to Language Regarding a QSE Moving AS Responsibility Between Resources
    SCR820 – Operator Real-Time Messaging During Emergency
    SCR822 – Create Daily Energy Storage Integration Report & Dashboard
  Technology Working Group
    Next meeting expected in August
  “Not Started” Revision Request List
    Continuing Discussion on “Not Started” and “On Hold” Revision Requests
  Appendix
    BES Combo Model Implementation
Location of Revision Request Project Information: http://www.ercot.com/services/projects
Project Update Agenda

## Slide 3: Recent / Upcoming Project Highlights
2022 July Release – Off-cycle – 7/1/2022 Complete
  NPRR935 – Post All Wind and Solar Forecasts (new solar forecasts and reports – see 5/4/2022 notice)
  NOGRR239 – WAN Data Protection Responsibilities
2022 July Release – R4 – 7/26/2022-7/28/2022 In Flight
  NPRR1108 – ERCOT Shall Approve or Deny All Resource Outage Requests
2022 October Release – R5 – 10/4/2022-10/6/2022 In Flight
  NPRR987 – BESTF-3 Energy Storage Resource Contribution to Physical Responsive Capability portion
  NPRR1002 – BESTF-5 Charging Restrictions in Emergency Conditions portion
2022 October Release – Off-Cycle – 10/13/2022 In Flight
  FFR Advancement (FFRA portion of NPRR863)
  NPRR1120 – Create Firm Fuel Supply Service
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2022 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February Various Dates | April 4/5 – 4/7 | May 5/24 – 5/26 | July 7/26 – 7/28 | October 10/4 – 10/6 | December 12/6 – 12/8
LPGRR068 NPRR1054(a) NPRR1005 NOGRR210 RRGRR025 NPRR917 NPRR1052 NPRR1065 NPRR1073 NPRR1016 PGRR082 NOGRR212 | None NPRR1092(a) | NPRR939 NPRR1093 NPRR1101 NPRR1113 NOGRR191 NOGRR198 NOGRR232 OBDRR032 OBDRR033 OBDRR035 SCR800 SCR809 SCR814 MarkeTrak User Interface Refresh | NPRR1108 NPRR935(b) NOGRR239 | NPRR987(a) NPRR1002(a) FFRA FFR Advancement (NPRR863 FFR) NPRR1120 | NPRR1097
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
ü
ü
ü
ü
Securitization Subchapter N March Go-Live
ECRS project started in 1/2022 with a go-live target prior to the EMS Freeze
1/1
EMS Freeze
May 2023 – Jan. 2024
E
E
E
P
ü
ü
ü
ü
DGR/DESR
NPRR1054(a) – Portion of gray box
NPRR935(b) – New solar forecasts and reports
NPRR987(a) – ESR Contribution to PRC
NPRR1002(a) – Charging Restrictions in Emergency Conditions
NPRR1092(a) – RUC offer floor change
SCR789 Ph2
Late 2022
TBD Items | NPRRs: 484,825(b),826,829,841,857,879,885,904,918,930,936,941,945,962,963,965,975,995,1004,1006,1007,1019,1023,1026,1030,1032,1034,1040, 1057,1063,1077,1090,1092(b),1105 SCRs: 799,805,807,810,812,813,816,818,819 PGRRs: 066,076,088,091,094,099 Other: OBDRR009,RRGRR028
E
ü
ü
ü
ü
NPRR1120 Firm Fuel Supply Serv
Issue RFP no later than 8/1/2022
Contracts start in November
6/4 – 6/6
7/1
5/13
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
NS
10/13
ü
ü
ü

## Slide 5: In-Flight Strategic Projects
  PR325-01 Fast-Frequency Response (FFR) Advancement (gated to Execution on 6/22/2021)
    Planned go-live for 2022-R5 (Oct 2022)
    NPRR863, NPRR1015, NPRR1079, NOGRR187
    FFRA readiness meeting on July 25 (will be market notice next week with details)
    Reminder of market submission impacts
      All AS Offers affected by changes
      Testing/MOTE dates Aug 15 – Oct 7 (publish metrics for submissions for QSEs with AS)
      More discussion at July 25 meeting and August TWG meeting
  PR394-01 NPRR1120 Create Firm Fuel Supply Service (gating to Execution in mid-July 2022)
    Planned go-live for 2022-R5 (Oct 2022)
    Market submission impacts:
      QSEs with FFSS will need to submit Availability Plans with new Availability Type (FFSS)
      XSD specifications were posted 7/6/22 and will be discussed at August TWG
      Changes will be in MOTE with FFRA (Aug 15 – Oct 7)

## Slide 6: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR1058 | Resource Offer Modernization | TBD | TBD | Additional month needed to complete IA
NPRR1085 | Ensuring Continuous Validity of PRC & Dispatch Through Timely Changes to Resource Telemetry and COPs | 2022 | 2525 | $100k-$150k, 4-6 months Impacted Systems: S&B, EMS, MMS
NPRR1135 | Add On-Line Status Check for Resources Telemetering OFFNS for AS Imbalance Settlements | 2022 | 3610 | $15k-$25k, 3-4 months Impacted Systems: EMS
NPRR1136 | Updates to Language Regarding a QSE Moving AS Responsibility Between Resources | 2023 | 3720 | $15k-$25k, 3-5 months Impacted Systems: MMS
SCR820 | Operator Real-Time Messaging During Emergency | 2023 | 3730 | IA near completion – may be posted on 7/12/2022 Impacted Systems: Grid Ops Support Systems
SCR822 | Create Daily Energy Storage Integration Report & Dashboard | 2022 | 3620 | $60k-$90k, 4-6 months Impacted Systems: Dashboards/reporting, EMS
Options for…
PPL Rank Information
Next available 2022 Rank in Business Strategy = 3610
Next available 2023 Rank in Business Strategy = 3720
Next available Rank in Regulatory = 340

## Slide 7: ERCOT Technology Working Group (TWG)
Next meeting expected in August

## Slide 8: “Not Started” Revision Request List
The “Not Started” Revision Requests is being revised to include ERCOT comments and recommendations
  Posted on 7/1/2022
Discussion at July PRS will be the review of:
  Items that conflict with critical in-flight initiatives
  Items that may have a pathway to implementation in the next 6-12 months
  Market feedback on priority of the items in #2 above

## Slide 9: Appendix

## Slide 10: BES Combo Model Implementation
  PR353-01 BES Combo Model Implementation – decoupled into separate efforts below
    NPRR987 – BESTF-3 ESR Contribution to Physical Responsive Capability and RT On-Line Reserve Capacity Calcs
    TARGETING IMPLEMENTATION IN 2022-R5
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    TARGETING IMPLEMENTATION IN 2022-R5
    NPRR989 – BESTF-1 ESR Technical Requirements
    NPRR1038 – BESTF-8 Limited Exemption from Reactive Power Requirements for Certain ESRs
    POTENTIAL IMPLEMENTATION IN 2022
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    RUN IN PARALLEL WITH RARF REPLACEMENT – TARGET GO-LIVE 2023
    NPRR963 – Base Point Deviation Settlement & Deployment Performance Metrics for ESRs (Combo Model)
    NPRR987 – BESTF-3 ESR Contribution to Physical Responsive Capability and RT On-Line Reserve Capacity Calcs
    NPRR1069 – Align Ancillary Service Responsibility for ESRs with NPRR987
    EXPECTED IMPLEMENTATION AFTER ECRS IN 2023 (re-assessing delivery options in September)
    NPRR1026 – BESTF-7 Self-Limiting Facilities and Self-Limiting Resources
    IMPLEMENTATION TIMELINE TBD
ESR: Energy Storage Resource
BES: Battery Energy Storage