## Issues
MCT Issues Log TX SET V5.0
Issue # | Issue Type | Affected Txn | Change Control Affected | Issue Statement | Issue Status | Date added | Owner | Date of Status Change | Notes
1 | Change Control | 814_18 | CC2021-828 | Update new DTM segements. DTM*150 is only required for an Add. DTM*151 is required for both Add and Change. | New | 2022-06-16 | Texas SET |  | KThuman - updated change control
2 | Change Control | 814_19 | New CC | Add 001 (Change) to the ASI for the 814_19 transaction | New | 2022-06-16 | Texas SET |  | KThurman started change control for 814_19
3 | RMGRR | NA | NA | RMGRR 11.2.5.12 (a) and (b) should be updated to send 814_18 Outbound | New | 2022-06-16 | Texas SET
4 | Change Control | 814_19 | New CC | Reject code for an 814_18 Add missing DTM*150 and DTM*151 | New | 2022-06-16 | Texas SET
5 | Change Control | 814_18 | New CC | Determine how far out we can have the End Date of the CSA | New | 2022-06-16 | CRs
6 | Change Control | 814_19 | New CC | If the 814_18 Change is missing end date, what reject code should we use? | New | 2022-06-16 | Texas SET
7 | Change Control | 814_19 | New CC | 814_18 Change sent on a CSA that does not have an active CSA row. What reject will we use? | New | 2022-06-16 | Texas SET
8 | Change Control | 814_19 | New CC | 814_18 Change sent on a CSA row that is Inactive. What reject code will we use? | New | 2022-06-16 | Texas SET
9 | Change Control | 814_19 | New CC | If the 814_18 delete includes DTM*150 and/or DTM*151. What reject code will we use? | New | 2022-06-16 | Texas SET |  | DTM*150 can use SNR.
10 | NPRR | NA | NA | Update NPRR with CSA clarifications - Section 15.1.9.1 (2) (see requirements document) | New | 2022-06-16 | Texas SET
11 | NPRR | NA | NA | Update NPRR with clarifications for MVO - Section 15.1.5.1(2)(a) and (3) (see requirements document) | New | 2022-06-16 | Texas SET
12 | RMGRR | NA | NA | Update RMGRR 11.2.5.13 (a) (see requirements documents) | New | 2022-06-16 | Texas SET
13 | Change Control | 814_19 | CC 2020-833 | SNR reject code should be updated to remove 'for the 814_18 Delete CSA Request'. This will allow SNR to be used on an 814_20 change if the Start Date is submitted and not just the 814_18 delete. | New | 2022-06-16 | Texas SET |  | KThurman started change control for 814_19
14 | Change Control | 814_20 | CC2020-819 | NMM109 listed in change control instead of NM109 in the REF~4P