## Slide 1
Market Readiness Updates
FFR and Firm Fuel Services
Matt Mereness
TAC Meeting
July 27, 2022

## Slide 2: Outline
Both FFRA and Firm Fuel planned for delivery in October 2022
  NPRR863/Fast-Frequency Response Advancement (FFRA) Project
  NPRR1020/Firm Fuel Supply Service Project

## Slide 3: NPRR863/FFRA Fast-Frequency Response Advancement Project
FFRA Market Readiness Dates :
  Interface changes reviewed at December 7, 2021 workshop
    ERCOT continues to support IT discussion at TWG meetings (next is Aug 4, 2022).
  Market Notice concerning Market Readiness May 20, 2022
    Interface changes are not backward compatible.
    All QSEs that are qualified providers of Responsive Reserve Service (RRS), Regulation Service, and/or Non-Spinning Reserve Service will be required to demonstrate their ability to submit offers for these Ancillary Services using the new interface prior to implementation of the FFRA project
  Project/Business workshop date- July 25, 2022
  MOTE deployment- August 15, 2022
    MOTE participation required, monitored, and published by ERCOT.
      Weeks 1 & 2 (Aug 15 – Aug 26): No submission summary published
      Weeks 3 & 4 (Aug 29 – Sep 9): Publish weekly submission summary by QSE (target 50% success)
      Weeks 5 & 6 (Sep 12 – Sep 23): Publish weekly submission summary by QSE (target 75% success)
      Week 7 & 8 (Sept 26 – Oct 7): Publish weekly submission summary by QSE (target 95% success)
  FFRA Go-Live October 13, 2022

## Slide 4: NPRR1020 Firm Fuel Supply Service Project
Firm Fuel Service Market Readiness Dates :
  Interface changes are backward compatible
    ERCOT posted XSD and External Interfaces Spec document on July 6, 2022
    Changes limited to QSEs awarded FirmFuel that will submit Availability Plans
    Technical Q&A discussion will occur at Aug 4, 2022 TWG
  MOTE deployment is August 15, 2022
    QSEs will have ability to submit Availability Plans with FFSS type
    Since backward compatible, no MOTE testing requirements
  Firm Fuel deployment is October 13, 2022 for Nov 15, 2022 Operating Day

## Slide 5: Questions
ERCOT continues to work closely with TWG
ERCOT will periodically update TAC with upcoming Market Readiness milestones
  NPRR863/FFRA (go-live October 2022)
  NPRR1120 Firm Fuel Supply Service (go-live October 2022)
  NPRR863/ECRS (go-live first half 2023)
Further comments or questions can be directed to Matt.Mereness@ercot.com

## Slide 6: Appendix

## Slide 7: Reminder of Improved Market Readiness concepts
Project process changes:
  Early development and delivery of changes to interface specifications
  Projects will assess the level of market interface impacts and incorporate into project plans to mitigate risks (example, MOTE duration).
Communication changes:
  Project team will publish interface changes earlier, posting to both the MIS and Technology Working Group (TWG) stakeholder forum.
  TWG review of MP interface changes and estimated key project dates:
    Interface specifications release date / Project/Business workshop date
    MOTE availability date / Go-Live date
Market Readiness changes:
  ERCOT is improving the MP feedback loop (for FFRA & ECRS implementations) since both projects affect all Ancillary Service submissions (creates reliability risk):
  Concept of early Market Notice to communicate risk and MOTE requirements.
  Concept of longer MOTE Duration (increase from 4 weeks to 7 weeks).
  Concept of requiring and publishing MOTE submissions by QSEs.
7