## Sheet1
TX SET Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 2022-05-18
Agenda Item: | Decision / Resolution | Action Items :
Meeting Notes 04/20/2022
| No changes were made. | The Texas SET Chair will have the notes posted to the April meeting page key documents as a final version.
ERCOT Update
Market Flight Test | The Texas SET Chair presented the Flight Update as provided by ERCOT.
Texas Flight Testing Schedule 2023 | Texas SET Leadership conducted a discussion on the 2023 Flight Schedule and determined that further discussions will take place when ERCOT and Lubbock Power & Light (LPL) have a better idea of what testing requirements they need to enter the Market. It was noted that testing scripts will need to be reviewed in order to include LPL's testing requirements in addition to adding needed scripts for the Texas SET V5.0 Release. ERCOT also reminded the group that consideration needs to be given when determine what scripts need to be added to the FlighTrak tool and which will be ad hoc. | The Texas SET Chair will seek feedback from the Retail Market Subcommittee (RMS) Chair how they might want to have a separate discussion of LPL's timeline for process development. Texas SET will
RMGRR168 | ERCOT and the Texas SET Chair reviewed the approval timeline.
NPRR1134 | ERCOT and the Texas SET Chair reviewed the approval timeline.
Market Coordination Team (MCT) Discussion
Development of the Market Coordination Team (MCT) for Texas SET v5.0 Release. | ERCOT stated that there are certain processes, including the developing of a requirements document, that will take some time to create. ERCOT also stated that the draft is under development but will be more complete in time for the next meeting.
Other Business
Texas SET Meeting Schedule for Rest of the Year. | The Texas SET Chair conducted a discussion related to next month's meeting and how much time will be needed for the MCT discussions. It as determined that MCT will meet WebEx only on June 15; Texas SET and TDTMS will keep the June 16th date via WebEx only. The Centerpoint representative suggested that MCT take the Texas SET meeting time slots for future meetings; then Texas SET can determine alternative times/dates for their meetings. | ERCOT will provide their needs for future MCT meetings.
Next Meeting--WebEx Only | 2022-06-16
Attendees F-T-F
Attendees Webex
Bill Snyder | Kathryn Thurman ERCOT
Birdie Cobb | Kathy Scott Centerpoint Energy
Carole Root AEP | Kim Wall Hansen Technologies
Carolyn Reed Centerpoint Energy | Kyle Patrick NRG
Catherine Meiners ERCOT | Mark Pepdjonovic ESG
Darice Taipalus TNMP | Pam Shaw LPL
Dave Michaelson ERCOT | Paula Shadle NEC
Deb Belin Earth Etch | Sam Pak ONCOR
Diana Rehfeldt TNMP | Sheri Wiegand Vistra
Eric Lotter GridMonitor | Stephen Wilson TXU Energy
Esther Kent CNP | Steve Pliler Vistra
Jamie Wood LPL | Tammy Stewart
Jordan Troublefield ERCOT