## Issues
MCT Issues Log TX SET V5.0
Issue # | Issue Type | FR Number | Affected Txn | Change Control Affected | Issue Statement | Issue Status | Date added | Owner | Date of Status Change | Notes
1 | Change Control | FR1.1 | 814_18 | CC2021-828 | Update new DTM segements. DTM*150 is only required for an Add. DTM*151 is required for both Add and Change. | Closed | 2022-06-16 | Texas SET | 2022-09-13 | Kathryn T. - updated change control 9/13/2022 - RMS approved Change Control
2 | Change Control | FR1.25 | 814_19 | CC2022-838 | Add 001 (Change) to the ASI for the 814_19 transaction | Closed | 2022-06-16 | Texas SET | 2022-09-13 | Kathryn T. started change control for 814_19 9/13/2022 - RMS approved Change Control
3 | RMGRR | Req 2.2 | NA | NA | RMGRR 11.2.5.12 (a) and (b) should be updated to send 814_18 Outbound | In Progress | 2022-06-16 | Texas SET | 2022-07-20 | Kathryn T. drafted
4 | Change Control | FR1.2 | 814_19 | CC2022-838 | Reject code for an 814_18 Add missing DTM*150 and DTM*151 | Closed | 2022-06-16 | Texas SET | 2022-09-13 | Kyle will draft -- add to CC for 814_19 9/13/2022 - RMS approved Change Control
5 | Change Control | FR1.4 FR1.20 | 814_18 | CC2022-838 | Determine how far out we can have the End Date of the CSA What reject code will be used if exceed | Closed | 2022-06-16 | ERCOT | 2022-09-13 | CRs would like to put as far of an End Date in the future as they can, and not to have to maintain dates every year. ERCOT to see if we can put these out farther in the future (with no validation on date example 12/31/9999). Add requirement to have - Montly CSA report with Start and End Date. Agreed on 800 days (just over 2 years)
6 | Change Control | FR1.19 | 814_19 | CC2022-838 | If the 814_18 Change is missing end date, what reject code should we use? | Closed | 2022-06-16 | Texas SET | 2022-09-13 | pending item 5. EDR - End Date Required 9/13/2022 - RMS approved Change Control
7 | Change Control | FR1.21 | 814_19 | CC2022-838 | 814_18 Change sent on a CSA that does not have an active CSA row. What reject will we use? | Closed | 2022-06-16 | Texas SET | 2022-09-13 | Kyle will draft -- NAC - No Active CSA 9/13/2022 - RMS approved Change Control
8 | Change Control | FR1.22 | 814_19 | CC2022-838 | 814_18 Change sent on a CSA row that is Inactive. What reject code will we use? | Closed | 2022-06-16 | Texas SET | 2022-09-13 | Same reject code as line 7 --- NAC - No Active CSA 9/13/2022 - RMS approved Change Control
9 | Change Control | FR1.31 | 814_19 | CC2022-838 | If the 814_18 delete includes DTM*150 and/or DTM*151. What reject code will we use? | Closed | 2022-06-16 | Texas SET | 2022-09-13 | DTM*150 can use SNR. Strike for 814_18 Delete CSA Request from Change Control 833 9/13/2022 - RMS approved Change Control
10 | NPRR | Req 2.1 | NA | NA | Update NPRR with CSA clarifications - Section 15.1.9.1 (2) (see requirements document) | In Progress | 2022-06-16 | Texas SET | 2022-07-20 | Kathryn T. drafted
11 | NPRR | Req 2.2 | NA | NA | Update NPRR with clarifications for MVO - Section 15.1.5.1(2)(a) and (3) (see requirements document) | In Progress | 2022-06-16 | Texas SET | 2022-07-20 | Kathryn T. drafted
12 | RMGRR | Req 2.2 | NA | NA | Update RMGRR 11.2.5.13 (a) (see requirements documents) | In Progress | 2022-06-16 | Texas SET | 2022-07-20 | Kathryn T. drafted
13 | Change Control | FR1.18 | 814_19 | CC2020-833 CC2022-838 | SNR reject code should be updated to remove 'for the 814_18 Delete CSA Request'. This will allow SNR to be used on an 814_18 change if the Start Date is submitted and not just the 814_18 delete. | Closed | 2022-06-16 | Texas SET | 2022-09-13 | Kathryn T. started change control for 814_19 9/13/2022 - RMS approved Change Control
14 | NA | FR4.9 | NA | NA | ERCOT to review request for loading a flat file for County and Meter Service Type | Closed | 2022-07-20 | Texas SET | 2022-11-03 | SCR will need to be submitted in order for ERCOT to do an IA. Kathy will draft SCR for SET to review in August. SET reviewed SCR and will submit to RMS SCR 823 has been submitted SCR was approved
15 | Change Control | FR8.14 | 814_20 | CC2020-819 | NMM109 listed in change control instead of NM109 in the REF~4P | Closed | 2022-07-20 | Texas SET | 2022-09-13 | Kathryn T. will draft this update. TX SET recommended CC to RMS for Approval 9/13/2022 - RMS approved Change Control
16 | Change Control | FR6.23 | 814_25 | CC2022-837 | Write new change control to remove the ERCOT only from the 814_25 for NFI | Closed | 2022-07-20 | Texas SET | 2022-08-25 | Kathryn T. will draft this update. TX SET recommended CC to RMS for Approval 9/13/2022 - RMS approved Change Control
17 | Change Control | FR6.28 | 814_09 |  | Add DUP to 814_09 (update info) | Closed | 2022-07-20 | K. Thurman | 2022-07-26 | Kathryn T. will draft this update. 07.26.2022 - Determined this was only to remove reference to MIMO Rules. No new Change Control is needed.
18 | RMGRR | FR1.30 | NA | NA | In order for a CR to end a pending CSA request, a MarkeTrak issue will need to be submitted. ERCOT to determine what type of MarkeTrak | In Progress | 2022-08-15 | K. Thurman |  | ERCOT recommends Market Rule subtype. Which will require an RMGRR. Recommended to use CSACAN in RMG
19 | RMGRR | FR3.1 |  |  | Update the RMGRR for Standard Switches to be rejected for a second standard Switch | In Progress | 2022-09-01 | K. Thurman |  | Kathryn T. drafted
20 | Change Control | FR1.22 FR1.23 FR1.30 FR6.16 | 814_19 | TXSETCC830 TXSETCC838 | We created 2 Reject Codes for the 814_19 that are basically the same thing. NCC - No Current CSA (1.30 & 6.16) NAC - No Active CSA (1.22 & 1.23) Recommend keeping NCC | In Progress | 2022-11-02 | K. Thurman | 2023-01-18 | Agreed to keep NCC and remove NAC. Requirements updated. Change Control submitted 01.18.23 - TX SET Recommended Change Control to be approved