## Slide 1
Weekly Market Readiness for
FFRA and Firm-Fuel Release
(Go-Live October 13, 2022)
Matt Mereness
September 6, 2022

## Slide 2: Outline
Purpose and scope of weekly Market Readiness meetings
Required testing and scorecard for QSEs in MOTE
Other supplemental information as needed or requested
  High level review of transaction changes
Summary and Q&A

## Slide 3: Purpose and scope of weekly Market Readiness meetings
ERCOT’s release for October 13, 2022 carries more risk and complexity than releases in recent years:
  Required system design changes to Ancillary Service (AS) Offers that structurally impacted all QSE AS Offers and is not backward compatible.
    Risk- inability to submit AS Offers due to interface issues would affect ERCOT reliability
  Other transactions for RRS-related submissions are also impacted:
    Current Operating Plan (COP)
    AS Self-Arrangement
    AS Trades
  On the day of implementation/cutover, QSEs may be required to cancel and re-submit certain transactions (still being evaluated and target release of cutover plan for Sep 13, 2022)
  ERCOT will host these weekly calls with SMEs to answer technical and business questions, or to follow up with additional information as needed.
    Note- although not as high risk, the MOTE deployment also supports changes to Firm Fuel awarded providers (Availability Plan). Firm Fuel software deployment is October 13, 2022 for Nov 15, 2022 Operating Day.

## Slide 4: Purpose and scope of weekly Market Readiness meetings (continued)
Progression of Market Readiness:
  FFRA Interface changes reviewed at December 7, 2021 workshop
    Updates at every TWG meeting
  Market Notice concerning Market Readiness May 20, 2022
    Interface changes are not backward compatible.
    All QSEs that are qualified providers of Responsive Reserve Service (RRS), Regulation Service, and/or Non-Spinning Reserve Service will be required to demonstrate their ability to submit offers for these Ancillary Services using the new interface prior to implementation of the FFRA project
  Project/Business review at July 25, 2022 workshop
  MOTE deployment- August 15, 2022
    MOTE participation required, monitored, and published by ERCOT.
      Weeks 1 & 2 (Aug 15 – Aug 26): No submission summary published
      Weeks 3 & 4 (Aug 29 – Sep 9): Publish weekly submission summary by QSE (target 50% success)
      Weeks 5 & 6 (Sep 12 – Sep 23): Publish weekly submission summary by QSE (target 75% success)
      Week 7 & 8 (Sept 26 – Oct 7): Publish weekly submission summary by QSE (target 95% success)
  Weekly Market Readiness- every Tuesday, 10am Aug 30-Oct 4, 2022
  FFRA Go-Live October 13, 2022

## Slide 5: Required testing and scorecard for QSEs in MOTE
  All QSEs highly encouraged to test in MOTE at their own pace
  Required participation for QSEs that submitted AS Offers May 15 through Aug 15, 2022 will be monitored and published to TAC.
  MOTE participation targets for required QSE AS Offers:
    Weeks 1 & 2 (Aug 15 – Aug 28): No submission summary published
    Weeks 3 & 4 (Aug 29 – Sep 11): Publish weekly submission summary by QSE (target 50% success)
    Weeks 5 & 6 (Sep 12 – Sep 25): Publish weekly submission summary by QSE (target 75% success)
    Week 7 & 8 (Sept 26 – Oct 9): Publish weekly submission summary by QSE (target 95% success)
  First report will be published Tuesday, September 6 to assess participation for week of Monday Aug 29 through Sunday Sep 4
  The list of QSEs to be scored is posted with this presentation
    For 56 QSEs ERCOT is tracking each QSE that submitted submit at least one AS Offer during the week for each service that they offered in the 90-day window.
      Green = All AS types historically offered were submitted at least once during week
      Yellow = Some, but not all, types of AS Offers submitted
      Red = No AS Offers submitted
  If you need assistance identifying which Ancillary Services your company submitted May 15 – Aug 15, please contact Matt.Mereness@ercot.com

## Slide 6: Required testing and scorecard for QSEs in MOTE
Weekly posting on TAC homepage: https://www.ercot.com/committees/tac
Review live scorecard- goal is 50% by end of Week 2 (Sep 5- Sep 11)

## Slide 7: Other Supplemental Information High level review of transaction changes
Reminder: New RRS Subtypes implemented October 13, 2022
RRS – Primary Frequency Response (RRSPF)
  Analogous to previous RRSGN + RRSLD
RRS – Load Resources controlled by high-set under-frequency relays (RRSUF)
  Analogous to previous RRSNC
RRS - Fast Frequency Response (RRSFF)
  Responds within 15 cycles after frequency meets or drops below a preset threshold (59.85 HZ)
  Sustained for at least 15 minutes, recovers in 15 minutes
  Can be offered by qualifying Energy Storage (ESR) GEN and CLR, GEN (non ESR), CLR (non ESR), and NCLR.

## Slide 8: Other Supplemental Information: COP Changes
COP AS Resource Responsibility
  RRS
Will be replaced by the new RRS subtypes:
  RRSPF
  RRSFF
  RRSUF
  Note: Submit OD +2

## Slide 9: Other Supplemental Information: Self-Arranged AS Changes
Previous RRS AS Self Arrangement types:
RRSGN, RRSLD, and RRSNC
Will be replaced by new RRS subtypes:
RRSPF, RRSFF, and RRSUF
Note: AS Obligation for RRS will continue being reported as “RRS” obligation, not by new subtypes.
Note: Submit OD +2

## Slide 10: Other Supplemental Information: AS Trades
RRS AS Trade types
RRSGN, RRSLD, and RRSNC
will be replaced by
RRSPF, RRSFF, and RRSUF.
RRSFF responsibility can be replaced by any other RRS subtype.
RRSUF responsibility can be replaced by RRSPF or RRSUF.
RRSPF responsibility can only be replaced with other RRSPF.
Note: Submit OD +2

## Slide 11: Other Supplemental Information: AS Offer Changes
For Online Reserves (ONRES), RRS price will be removed and replaced a separate price column for each RRS Subtype. The price columns for ONRES will be as follows:
  REGUP Price (e.g. PRICE1_REGUP, PRICE2_REGUP…PRICE5_REGUP)
  RRSPF Price (e.g. PRICE1_RRSPF, PRICE2_RRSPF…PRICE5_RRSPF)
  RRSFF Price (e.g. PRICE1_RRSFF, PRICE2_RRSFF…PRICE5_RRSFF)
  RRSUF Price (e.g. PRICE1_RRSUF, PRICE2_RRSUF…PRICE5_RRSUF)
  ONNS Price (e.g. PRICE1_ONNS, PRICE2_ONNS…PRICE5_ONNS)
NCLR Flag option will be removed
Note: Submit OD +2

## Slide 12: Other Supplemental Information: AS Awards Changes
DAM and SASM RRS awards will now be reported by subtype (RRSPF, RRSFF and RRSUF) instead of by RRS.
UPDATE: ERCOT plans to provide a sample XML Award at next week’s meeting
Note: RRS MCPC will remain as “RRS”.

## Slide 13: Other Supplemental Information: Telemetry changes
Extra telemetry points have already been added into production supporting AS Responsibility and AS Schedule for RRS-FFR
    Existing Ancillary Service Responsibility and Ancillary Service Schedule telemetry for RRS-PFR and RRS-UFR will continue to be used (no change)
    New points added for RRS-FFR
      Table 19- Non Controllable Load Resource / LR / FFR Deployed / FDPL (status)
      Table 20- Generation Unit / UN / FFR Responsibility / FFRS
      Table 20- Generation Unit / UN / FFR Schedule / FFSC
      Table 20- Non-Controllable Load Resource / LR / FFR Responsibility / FFRS
      Table 20- Non-Controllable Load Resource / LR / FFR Schedule / FFSC
  ICCP Handbook: https://www.ercot.com/gridinfo/transmission (Bottom of the webpage)
  Email: ErcotICCPSupport@ercot.com

## Slide 14: Other Supplemental Information: Firm Fuel Supply Service Change
Changes limited to QSEs awarded FirmFuel that will submit Availability Plans
  New Availability Plan type = FFSS
  Note that Firm Fuel software deployment is October 13, 2022 for Nov 15, 2022 Operating Day

## Slide 15: Summary and Q&A
Weekly meetings (ERCOT calendar)
  Tuesdays 10am Aug 30-Oct 4, 2022
  Detailed business changes posted at July 25, 2022 workshop
MOTE Scorecard to be published to TAC homepage
  Periodic emails to TAC
Cutover Plan in development
  Plan to provide to QSEs one month before cutover and will leverage this WebEx forum to discuss plan and take questions.
ERCOT open to feedback/questions for this or next meeting
  Feedback can be directed to Matt.Mereness@ercot.com
  MOTE set-up questions go through your ERCOT Account Manager or email ClientServices@ercot.com
Questions?