## Sheet1
| 2022 | [25 empty] | 2023
| 2022-07-04 |  |  |  | 2022-08-01 |  |  |  |  | 2022-09-05 |  |  |  | 2022-10-03 |  |  |  |  | 2022-11-07 |  |  |  | 2022-12-05 |  |  |  | 2023-01-02 |  |  |  |  | 2023-02-06 |  |  |  | 2023-03-06 |  |  |  | 2023-04-03 |  |  |  | 2023-05-01 |  |  |  |  | 2023-06-05 |  |  |  | 2023-07-03 |  |  |  |  | 2023-08-07 |  |  |  | 2023-09-04 |  |  |  | 2023-10-02 |  |  |  |  | 2023-11-06 |  |  |  | 2023-12-04
 | time axis 2022-07-04 to 2023-12-25
Delivery Service Pricing | 2022-09-05: Delivery Service Pricing; 2023-01-02: EUB & City Council Approval
POLR/Default REPs | 2022-09-26: POLR / Default REP RFP; 2023-01-02: EUB & City Council Approval
AMI Meters | 2022-07-04: Final Transition to AMI Meters (< 400 meters)
Transfer Remaining 30% of Customer Load Into ERCOT | 2022-07-04: Construction; 2023-05-22: Transfer Load to ERCOT
| Develop Switching Plan | [8 empty] | Modelling | [20 empty] | PUCT Approves Transfer of Load
Transactions | 2022-07-04: Establish EDI Gateway; 2022-12-05: System Testing; 2023-03-13: Flight Testing; 2023-07-17: Customer Choice - Selection of REPs; 2023-09-11: Assign Default REPs; 2023-10-02: Transition ESI IDs to REPs on their billing cycle day
System Configuration and Process Changes
Customer Education | 2022-09-05: Fall Ad Campaigns to Announce Competition; 2023-01-02: Spring Ad Campaigns; 2023-03-06: Hold Public Informational Workshops About Shopping for REPs