## Slide 1
Weekly Market Readiness for
FFRA and Firm-Fuel Release
(Go-Live October 13, 2022)
Matt Mereness
September 13, 2022

## Slide 2: Outline
Purpose and scope of weekly Market Readiness meetings
Required testing and scorecard for QSEs in MOTE
Other supplemental information as needed or requested
  High level review of transaction changes
Data Cutover Approach
Summary and Q&A

## Slide 3: Purpose and scope of weekly Market Readiness meetings
ERCOT’s release for October 13, 2022 carries more risk and complexity than releases in recent years:
  Required system design changes to Ancillary Service (AS) Offers that structurally impacted all QSE AS Offers and is not backward compatible.
    Risk- inability to submit AS Offers due to interface issues would affect ERCOT reliability
  Other transactions for RRS-related submissions are also impacted:
    Current Operating Plan (COP)
    AS Self-Arrangement
    AS Trades
  On the day of implementation/cutover, QSEs may be required to cancel and re-submit certain transactions (later agenda item)
  ERCOT will host these weekly calls with SMEs to answer technical and business questions, or to follow up with additional information as needed.
    Note- although not as high risk, the MOTE deployment also supports changes to Firm Fuel awarded providers (Availability Plan). Firm Fuel software deployment is October 13, 2022 for Nov 15, 2022 Operating Day.

## Slide 4: Purpose and scope of weekly Market Readiness meetings (continued)
Progression of Market Readiness:
  FFRA Interface changes reviewed at December 7, 2021 workshop
    Updates at every TWG meeting
  Market Notice concerning Market Readiness May 20, 2022
    Interface changes are not backward compatible.
    All QSEs that are qualified providers of Responsive Reserve Service (RRS), Regulation Service, and/or Non-Spinning Reserve Service will be required to demonstrate their ability to submit offers for these Ancillary Services using the new interface prior to implementation of the FFRA project
  Project/Business review at July 25, 2022 workshop
  MOTE deployment- August 15, 2022
    MOTE participation required, monitored, and published by ERCOT.
      Weeks 1 & 2 (Aug 15 – Aug 26): No submission summary published
      Weeks 3 & 4 (Aug 29 – Sep 9): Publish weekly submission summary by QSE (target 50% success)
      Weeks 5 & 6 (Sep 12 – Sep 23): Publish weekly submission summary by QSE (target 75% success)
      Week 7 & 8 (Sept 26 – Oct 7): Publish weekly submission summary by QSE (target 95% success)
  Weekly Market Readiness- every Tuesday, 10am Aug 30-Oct 4, 2022
  FFRA Go-Live October 13, 2022

## Slide 5: Required testing and scorecard for QSEs in MOTE
  All QSEs highly encouraged to test in MOTE at their own pace
  Required participation for QSEs that submitted AS Offers May 15 through Aug 15, 2022 will be monitored and published to TAC.
  MOTE participation targets for required QSE AS Offers:
    Weeks 1 & 2 (Aug 15 – Aug 28): No submission summary published
    Weeks 3 & 4 (Aug 29 – Sep 11): Publish weekly submission summary by QSE (target 50% success)
    Weeks 5 & 6 (Sep 12 – Sep 25): Publish weekly submission summary by QSE (target 75% success)
    Week 7 & 8 (Sept 26 – Oct 9): Publish weekly submission summary by QSE (target 95% success)
  The list of required QSEs is in scorecard and posted with presentation
    For 56 QSEs, ERCOT is tracking each QSE that submitted submit at least one AS Offer during the week for each service that they offered in the 90-day window May15-Aug15.
      Green = All AS types historically offered were submitted at least once during week
      Yellow = Some, but not all, types of AS Offers submitted
      Red = No AS Offers submitted
  If you need assistance identifying which Ancillary Services your company submitted May 15 – Aug 15, please contact Matt.Mereness@ercot.com

## Slide 6: Required testing and scorecard for QSEs in MOTE
Weekly posting on TAC homepage: https://www.ercot.com/committees/tac
Review live scorecard- goal is 50% by end of Week 2 (Sep 5- Sep 11)
Good news that progress is on-track at 59%

## Slide 7: Other Supplemental Information High level review of transaction changes
Reminder: New RRS Subtypes implemented October 13, 2022
RRS – Primary Frequency Response (RRSPF)
  Analogous to previous RRSGN + RRSLD
RRS – Load Resources controlled by high-set under-frequency relays (RRSUF)
  Analogous to previous RRSNC
RRS - Fast Frequency Response (RRSFF)
  Responds within 15 cycles after frequency meets or drops below a preset threshold (59.85 HZ)
  Sustained for at least 15 minutes, recovers in 15 minutes
  Can be offered by qualifying Energy Storage (ESR) GEN and CLR, GEN (non ESR), CLR (non ESR), and NCLR.

## Slide 8: Other Supplemental Information: COP Changes
COP AS Resource Responsibility
  RRS
Will be replaced by the new RRS subtypes:
  RRSPF
  RRSFF
  RRSUF
  Note: Submit OD +2

## Slide 9: Other Supplemental Information: Self-Arranged AS Changes
Previous RRS AS Self Arrangement types:
RRSGN, RRSLD, and RRSNC
Will be replaced by new RRS subtypes:
RRSPF, RRSFF, and RRSUF
Note: AS Obligation for RRS will continue being reported as “RRS” obligation, not by new subtypes.
Note: Submit OD +2

## Slide 10: Other Supplemental Information: AS Trades
RRS AS Trade types
RRSGN, RRSLD, and RRSNC
will be replaced by
RRSPF, RRSFF, and RRSUF.
RRSFF responsibility can be replaced by any other RRS subtype.
RRSUF responsibility can be replaced by RRSPF or RRSUF.
RRSPF responsibility can only be replaced with other RRSPF.
Note: Submit OD +2

## Slide 11: Other Supplemental Information: AS Offer Changes
For Online Reserves (ONRES), RRS price will be removed and replaced a separate price column for each RRS Subtype. The price columns for ONRES will be as follows:
  REGUP Price (e.g. PRICE1_REGUP, PRICE2_REGUP…PRICE5_REGUP)
  RRSPF Price (e.g. PRICE1_RRSPF, PRICE2_RRSPF…PRICE5_RRSPF)
  RRSFF Price (e.g. PRICE1_RRSFF, PRICE2_RRSFF…PRICE5_RRSFF)
  RRSUF Price (e.g. PRICE1_RRSUF, PRICE2_RRSUF…PRICE5_RRSUF)
  ONNS Price (e.g. PRICE1_ONNS, PRICE2_ONNS…PRICE5_ONNS)
NCLR Flag option will be removed
Note: Submit OD +2

## Slide 12: Other Supplemental Information: AS Awards Changes
DAM and SASM RRS awards will now be reported by subtype (RRSPF, RRSFF and RRSUF) instead of by RRS.
UPDATE: ERCOT plans to provide a sample XML Award at next week’s meeting
Note: RRS MCPC will remain as “RRS”.

## Slide 13: Other Supplemental Information: Telemetry changes
Extra telemetry points have already been added into production supporting AS Responsibility and AS Schedule for RRS-FFR
    Existing Ancillary Service Responsibility and Ancillary Service Schedule telemetry for RRS-PFR and RRS-UFR will continue to be used (no change)
    New points added for RRS-FFR
      Table 19- Non Controllable Load Resource / LR / FFR Deployed / FDPL (status)
      Table 20- Generation Unit / UN / FFR Responsibility / FFRS
      Table 20- Generation Unit / UN / FFR Schedule / FFSC
      Table 20- Non-Controllable Load Resource / LR / FFR Responsibility / FFRS
      Table 20- Non-Controllable Load Resource / LR / FFR Schedule / FFSC
  ICCP Handbook: https://www.ercot.com/gridinfo/transmission (Bottom of the webpage)
  Email: ErcotICCPSupport@ercot.com

## Slide 14: Other Supplemental Information: Firm Fuel Supply Service Change
Changes limited to QSEs awarded FirmFuel that will submit Availability Plans
  New Availability Plan type = FFSS
  Note that Firm Fuel software deployment is October 13, 2022 for Nov 15, 2022 Operating Day

## Slide 15: Data Cutover Approach
High-level expectations today, more details on specifics/timing next week
Planned cutover is evening of October 13, 2022 (time TBD)
Before October 13 evening upgrade:
  On morning of October 13, DAM completes and publish awards at 1330 for OD Oct 14 (current system and RRS). DRUC, HRUC, SASM continue to run on old code most of day.
  QSE action before evening of cutover on October 13:
    After cutover, queries and cancels are not backward compatible for AS Trades, AS Offers, AS SelfArrangement, therefore…..
      If exists where QSE submitted OD+2 (Oct 15), then QSE must cancel ASOffers and AS Self-Arrangement with RRS for OD 10/15 and forward before the upgrade (some QSEs submit OD+2 and beyond).
      QSEs will not be able to Query AS Trades in old format after upgrade, if needed then recommend QSE query AS Trades for snapshot of confirmed trades before upgrade.
After upgrade on Oct 13 evening:
  Immediately QSEs will need to refresh COP submissions that contain RRS
  QSE AS Trades submitted after cutover will be new RRS types
  QSE AS Offers and AS Self-Arrangement after cutover for morning of 10/14 for DAM OD 10/15 will be new RRS types
More detailed graphics and timing next week

## Slide 16: Summary and Q&A
Weekly meetings (ERCOT calendar)
  Tuesdays 10am Aug 30-Oct 4, 2022
  Detailed business changes posted at July 25, 2022 workshop
MOTE Scorecard to be published to TAC homepage
  Periodic emails to TAC
Cutover details
  ERCOT will provide more graphical and precise timeline next week and continue to leverage this WebEx forum to discuss cutover and take questions.
ERCOT open to feedback/questions for this or next meeting
  Feedback can be directed to Matt.Mereness@ercot.com
  MOTE set-up questions go through your ERCOT Account Manager or email ClientServices@ercot.com
Questions?