## Slide 1
2022 Annual Validation
PWG Meeting
October 14, 2022

## Slide 2: 2022 Annual BUS Validation Progress Report
 |  | ERCOT & TDSP AV 2022 Progress Report |  |  |  |  | 
Due Date* | 2022 Annual Validation Task List | ERCOT | AEP | CNP | Nueces | ONCOR | TNMP
03/30/2022 | ERCOT to provide list of BUS ESI IDs to TDSPs | 3/31/2022 | 3482745 | 3482739 | 3482759 | 3482729 | 3482752
03/31/2022 | ERCOT Provides Additional Validation Lists to TDSPs | 3/30/2022 | 3494709 | 3494712 | 3494716 | 3494718 | 3494720
04/10/2022 | TDSPs to provide finalized list of BUS ESI IDs to ERCOT | n/a |  |  |  |  | 
04/15/2022 | Market Notice announcing lists are available to CR of record | 4/15/2022 |  |  |  |  | 
04/15/2022 | TDSPs to begin submitting 814_20 transactions | n/a |  |  |  |  | 
09/30/2022 | Complete Annual and Additional Validations | n/a | Comp Date | Comp Date | Comp Date | Comp Date | Comp Date
10/03/2022 | ERCOT to review database for expected changes | Comp Date | n/a |  |  |  | 
10/10/2022 | TDSPs have submitted at least 99% of changes | n/a | Comp Date | Comp Date | Comp Date | Comp Date | Comp Date
Due Date* | 2022 Weather Responsiveness Report Task List | ERCOT | AEP | CNP | Nueces | ONCOR | TNMP
11/02/2022 | ERCOT provide list of ESI IDs to TDSPs requiring changes to Weather Sensitivity (Initial Weather Responsiveness Report) | Comp Date | n/a |  |  |  | 
Monthly | Monthly Weather Responsiveness Report Produced by ERCOT | Comp Date | n/a |  |  |  | 
02/02/2023 | TDSPs have submitted at least 99% of changes | n/a | Comp Date | Comp Date | Comp Date | Comp Date | Comp Date
* If the due date falls on a weekend or holiday, please use the next business day as the deadline. |  |  |  |  |  | Updated on | 16-Aug-22

## Slide 3: 2022 AV BUS Status Update
 | AEP |  |  | CNP |  |  | NUECES |  |  | ONCOR |  |  | TNMP |  | 
 | RES | BUS | Total | RES | BUS | Total | RES | BUS | Total | RES | BUS | Total | RES | BUS | Total
Initial List of Changes |  | 12,301 | 12,301 |  | 13,077 | 13,077 |  | 411 | 411 |  | 19,068 | 19,068 |  | 1,811 | 1,811
Exceptions |  |  | 151 |  |  | 3 |  |  | 4 |  |  | 0 |  |  | 0
Net Subject to Change |  |  | 12,150 |  |  | 13,074 |  |  | 407 |  |  | 19,068 |  |  | 1,811
Updated, as of Oct-12-2022 |  |  | 12,148 |  |  | 13,074 |  |  | 407 |  |  | 19,068 |  |  | 1,692
Remaining |  | 2 | 2 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 119 | 119
% Completion |  |  | 100.0% |  |  | 100.0% |  |  | 100.0% |  |  | 100.0% |  |  | 93.4%