## Slide 1
Project Update
October 13, 2022
Troy Anderson
ERCOT Portfolio Management

## Slide 2
  Recent / Upcoming Project Highlights
  2022 Release Targets
  In-Flight Strategic Projects
    Fast-Frequency Response (FFR) Advancement
    NPRR1120 Create Firm Fuel Supply Service
  Additional Project Status Information
  Potential Outage Scheduler (OS) Enhancement
    Verbal Update / Q&A
  Impact Analysis Statistics Follow-Up
  Priority/Rank Options for Revision Requests with Impacts
    NPRR1128 – Allow FFR Procurement up to FFR Limit Without Proration
  Technology Working Group (TWG)
    9/29/2022 Meeting Summary
  Appendix
    BES Combo Model Implementation
    Impact Analysis Statistics (presented at September PRS)
Location of Revision Request Project Information: http://www.ercot.com/services/projects
Project Update Agenda

## Slide 3: Recent / Upcoming Project Highlights
2022 October Release – R5 – 10/4/2022-10/6/2022 Complete
  None (items moved to off-cycle release on 10/13/2022)
2022 October Release – Off-Cycle – 10/13/2022 In Flight
  FFR Advancement (FFRA portion of NPRR863)
  NPRR1120 – Create Firm Fuel Supply Service
  OBDRR039 – ORDC Changes Related to NPRR1120
  NPRR987(a) – BESTF-3 ESR Contribution to Physical Responsive Capability portion
  NPRR1002(a) – BESTF-5 Charging Restrictions in Emergency Conditions portion
2022 November Release – Off-Cycle – 11/2/2022 In Flight
  NPRR1063 – Dynamic Rating Transparency
2022 December Release – Off-Cycle – 12/1/2022 In Flight
  NPRR1142 – ERS Changes to Reflect Updated PUCT Rule Changes re SUBST. R. 25.507
2022 December Release – R6 – 12/6/2022-12/8/2022 In Flight
  NPRR1084 – Improvements to Reporting of Resource Outages, Derates, & Startup Loading Failures
  NPRR1096(a) – Require Sustained Four-Hour Capability for Non-Spin portion
    See 9/30/2022 Market Notice
  NPRR1097 – Create Resource Forced Outage Report
  SCR812 – Create Intermittent Renewable Generation Integration Report
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2022 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February Various Dates | April 4/5 – 4/7 | May 5/24 – 5/26 | July 7/26 – 7/28 | October 10/4 – 10/6 | December 12/6 – 12/8
LPGRR068 NPRR1054(a) NPRR1005 NOGRR210 RRGRR025 NPRR917 NPRR1052 NPRR1065 NPRR1073 NPRR1016 PGRR082 NOGRR212 | None NPRR1092(a) | NPRR939 NPRR1093 NPRR1101 NPRR1113 NOGRR191 NOGRR198 NOGRR232 OBDRR032 OBDRR033 OBDRR035 SCR800 SCR809 SCR814 MarkeTrak User Interface Refresh | NPRR1108(a) NPRR935(b) NOGRR239 NPRR1129 NPRR1108(b) | None FFR Advancement (NPRR863 FFR) NPRR1120 OBDRR039 NPRR987(a) NPRR1002(a) NPRR1063 | NPRR1084 NPRR1096(a) NPRR1097 SCR812 NPRR1142 RIOO
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
ü
ü
ü
ü
Securitization Subchapter N March Go-Live
1/1
EMS Freeze
May 2023 – Jan. 2024
E
E
E
E
E
E
ü
ü
ü
ü
DGR/DESR
NPRR935(b) – New solar forecasts and reports
NPRR987(a) – ESR Contribution to PRC
NPRR1002(a) – Charging Restrictions in Emergency Conditions
NPRR1054(a) – Portion of gray box
NPRR1092(a) – RUC offer floor change
NPRR1096(a) – Non-Spin portion
TBD | NPRRs: 484,825(b),826,829,841,857,879,885,904,918,930,936,941,945,962,963,965,975,987,995,1004,1006,1007,1019,1023,1026,1030,1032,1034,1057, 1077,1090,1092(b),1105 SCRs: 799,805,807,810,813,816,818,819 PGRRs: 066,076,088,091,094,099 Other: OBDRR009,OBDRR017,RRGRR028
ü
ü
ü
ü
6/4 – 6/6
7/1
5/13
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
E
E
E
P
E
E
10/13
ü
ü
ü
7/15
ü
8/16
ü
11/2
ü
12/1
12/9

## Slide 5: In-Flight Strategic Projects
  PR325-01 Fast-Frequency Response (FFR) Advancement (gated to Execution on 6/22/2021)
    Market Notice sent 10/11/2022 with details of timing, summary and changes, and 24-hour support for all impacted transactions.
      Off-cycle go-live scheduled on 10/13/2022 between 7pm-9pm
      QSE Hotline call when upgrade starts and when complete
      Operations Message after upgrade advising QSEs to update COP carrying RRS
    Supporting details in last Market Readiness meeting: https://www.ercot.com/calendar/event?id=1663856312722
    Excellent QSE/vendor support and participation- achieved 96% readiness on QSE AS Offers
  PR394-01 NPRR1120 Create Firm Fuel Supply Service (gated to Execution on 7/13/2022)
    System changes go-live on 10/13/2022
    Progression of changes:
      Availability Plan system changes are currently in MOTE environment for testing
      September 23, 2022 - FFSS Award Procurement results were posted
      October 13, 2022 - FFSS system changes will be implemented
      November 14, 2022 - Availability Plans for an FFSSR due for all Operating Days within the next 14 days, with continuing daily obligation to provide Availability Plans thereafter
      November 15, 2022 - First Operating Day for start of FFSS Obligation Period

## Slide 6: Additional Project Status Information
Revision Request | Description | Project Phase | Additional Detail
NPRR863 | ECRS portion of NPRR863 | Execution | Go-Live Target = 2023-R3
NPRR1096 | Require Sustained Two-Hour Capability for ECRS | Execution | ECRS portion of NPRR1096 Go-Live Target = 2023-R3 w/ECRS
NPRR1020 | Allow Some Integrated Energy Storage Designs to Calculate Internal Loads | Execution | EPS Metering portion of NPRR1020 Go-Live Target = 2023-R1
SCR789 | Update NMMS Topology Processor – Phase 2 | Execution | Go-Live Target = Early 2023
NPRR1040 | Compliance Metrics for Ancillary Service Supply Responsibility | Planning | Go-Live Target = 2023-R1
NPRR1095 SCR817 | Texas SET V5.0 Changes MarkeTrak Validation Revisions Aligning with Texas SET V5.0 | Planning | Expected completion in 2024 SCR823 at Oct. Board for approval
SCR807 SCR816 | Increase CRR Transaction Capability CRR Auction Bid Credit Enhancement | Initiation | Initiated on 10/5/2022 Go-Live Target = 2023-R4
SCR819 NPRR1111 | Improving IRR Control to Manage GTC Stability Limits | Not Started | Target start TBD
NPRR1004 | Load Distribution Factor Process Update | Not Started | Early 2023 candidate
NPRR1092 | Limit RUC Opt-Out Provision | Not Started | Early 2023 candidate
Red Text: New additions and updates
Sorted by Project Phase

## Slide 7: Potential Outage Scheduler (OS) Enhancement
Items considered for OS changes
  User interface
  Allow modification of outage causes and other fields as needed
  Linking outage extensions and deratings; managing overlap outages
  Flexibility to support group recurring outage requests
  Easier reporting and analysis of outages
  Retaining original outage type
  Others
Need stakeholders’ feedback and comments on the changes to the OS
  Send to OCSupv@ercot.com by October 14, 2022
Verbal Update from Fred Huang
Q&A

## Slide 8: Impact Analysis Statistics Follow-Up
Question from September PRS meeting:
  Where did projects that had actuals within the IA range fall within their respective ranges?
    Cost 21 of 38 projects within cost range
    Duration 15 of 38 projects within duration range
Cost Range RR PROJECTS | Within IA Range
75%–100% (top quartile) | 6
50%–75% (mid/high quartile) | 7
25%–50% (mid/low quartile) | 5
0%–25% (bottom quartile) | 3
Total | 21
Duration Range RR PROJECTS | Within IA Range
75%–100% (top quartile) | 2
50%–75% (mid/high quartile) | 6
25%–50% (mid/low quartile) | 5
0%–25% (bottom quartile) | 2
Total | 15
See Appendix for related information presented at September 2022 PRS meeting

## Slide 9: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR1128 | Allow FFR Procurement up to FFR Limit Without Proration | 2023 | 3760 | $30k-$50k, 3-5 months Impacted Systems: MMS, Data Management, EMIL 2023 candidate when MMS resources are available
SCR821 | Voltage Set Point Target Information for DGR / DESR | TBD | TBD | Additional month needed to post IA
Options for…
PPL Rank Information
Next available 2023 Rank in Business Strategy = 3760
Next available Rank in Regulatory = 340

## Slide 10: ERCOT Technology Working Group (TWG)
9/29/2022 TWG meeting discussion points:

## Slide 11: Appendix

## Slide 12: BES Combo Model Implementation
  PR353-01 BES Combo Model Implementation – decoupled into separate efforts below
    NPRR987 – BESTF-3 ESR Contribution to Physical Responsive Capability and RT On-Line Reserve Capacity Calcs
    TARGETING IMPLEMENTATION IN 2022-R5
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    TARGETING IMPLEMENTATION IN 2022-R5
    NPRR989 – BESTF-1 ESR Technical Requirements
    NPRR1038 – BESTF-8 Limited Exemption from Reactive Power Requirements for Certain ESRs
    IMPLEMENTATION TIMELINE TBD
    NPRR1002 – BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions
    RUN IN PARALLEL WITH RARF REPLACEMENT – TARGET GO-LIVE 2023
    NPRR963 – Base Point Deviation Settlement & Deployment Performance Metrics for ESRs (Combo Model)
    NPRR987 – BESTF-3 ESR Contribution to Physical Responsive Capability and RT On-Line Reserve Capacity Calcs
    NPRR1069 – Align Ancillary Service Responsibility for ESRs with NPRR987
    IMPLEMENTATION TIMELINE TBD
    NPRR1026 – BESTF-7 Self-Limiting Facilities and Self-Limiting Resources
    IMPLEMENTATION TIMELINE TBD
ESR: Energy Storage Resource
BES: Battery Energy Storage

## Slide 13: Variance from IA Cost Range – Revision Request Projects
Exceeds IA Range
10 Projects
Below IA Range
7 Projects
Within IA Range
21 Projects
If actual spend falls within the IA range the variance is 0
2019
33 Projects
19 Revision Requests
2020
26 Projects
9 Revision Requests
2021
18 Projects
9 Revision Requests
Note: Graph compares the posted IA cost range with the actual project spend
2022
4 Projects
1 Revision Request
Chart: 
| NOGRR174 - AVR and PSS Testing Requirements | NPRR809 - GTC or GTL for New Generation Interconnection | NPRR817, NPRR847, VCMRR021 - Create a Panhandle Hub | NPRR821 - Elimination of the CRR Deration Process | NPRR833, NPRR749 - Modify PTP Obligation Bid Clearing Change | NPRR842 - Study Area Load Information | NPRR845 - RMR Process and Agreement Revisions | NPRR858 - Provide Complete Current Operating Plan (COP) Data | NPRR865, NPRR880 - Publish RTM Shift Factors for Hubs, Load Zones, and DC Ties | NPRR866, RRGRR017 - RRGRR Related to NPRR866, Mapping Registered Distributed Generation and Load Resources to Transmission Loads in the Network Operations Model | NPRR877 - Use of Actual Interval Data for IDR ESI IDs for Initial Settlement - Phase 2 | NPRR899 - Digital Certificate and User Security Administrator Clarifications and Opt Out Procedure | NPRR901, NPRR910, OBDRR010 - Switchable Generation Resource Status Code | NPRR914 - Addition of Controllable Load Resources to 60-Day Reports | NPRR925, SCR798 - PTP Obligation Bid ID Limit | SCR793 - SSR Related Telemetry for Transmission Service Provider (TSP) Operators | SCR794 - Update SCED Limit Calculation | SCR796, OBDRR003, OBDRR014 - Change Validation Rules to Preclude Certain Transactions at Resource Nodes within Private Use Networks | VCMRR022 - Determination of Fuel Adder Price for Coal and Lignite Resources | NPRR856, NPRR884 - Treatment of OFFQS Status in Day-Ahead Make Whole and RUC Settlements Adjustments to Pricing and Settlement for Reliability Unit Commitments (RUCs) of On-Line Combined Cycle Generation Resources | NPRR873 - Posting of the ERCOT Wide Intra-Hour Wind Power and Load Forecast on the MIS Public | NPRR929 - PTP Obligations with Links to an Option DAM Award Eligibility | NPRR935 - Post All Wind and Solar Forecasts | NPRR951 - Active and Inactive SCED Constraint Reporting | PGRR057 - Responsibilities for Performing Geomagnetic Disturbance (GMD) Vulnerability | SCR797 - Provide IRR Current Operating Plan (COP) to TSPs | SCR802 - Enhance Communications of System Inertia | SCR803 - Enhance Wind Integration Report and Create Solar Integration Report and Solar Dashboard | NOGRR195 - NOGRR195 Generator Voltage Control Tolerance Band | NPRR1081 - NPRR1081 Revisions to Real-Time Reliability Deployment Price Adder to Consider Firm Load Shed | NPRR902 - NPRR902 ERCOT Critical Energy Infrastructure Information | NPRR905 - NPRR905 CRR Balancing Account Resettlement | NPRR974, NPRR978, NPRR1048, SCR806 - NPRR974 NPRR978 NPRR1048 SCR806 - Alignmt w Amndmnt PUCT SubsRule 25_505_Schedule | NPRR986, NPRR971, NPRR1043 - Implementation of NPRR986 BESTF-2 and NPRR971 | NPRR998 - NPRR998 ERS Deployment and Recall Messages | SCR804 - SCR804 ERCOT GridGeo Access for Transmission Operators | SCR811 - Integrate Solar Forecasts and SCR811 Implementation | SCR800, SCR809 - SCR800 and SCR809 Implementation
 | -4343 | 39855 | 0 | 0 | 257360 | 0 | 6585 | -2703 | -7490 | 0 | -3392 | 0 | 0 | 0 | 0 | 0 | -17092 | -4770 | 0 | 0 | 11061.14 | 0 | 6282.25 | 0 | 0 | 0 | 0 | 0 | 0 | -1329 | 57087 | 23505 | 0 | 190914 | 7621 | 0 | 31678 | 0
Actual $ Variance from IA Range
1
35
2
36
10
3
4
5
6
7
8
9
11
12
13
14
15
16
17
18
19
20
21
23
24
25
26
27
28
29
37
38
34
31
32
33
30
22

## Slide 14: Variance from IA Duration Range – Revision Request Projects
Exceeds IA Range
17 Projects
Below IA Range
6 Projects
Within IA Range
15 Projects
2019
33 Projects
19 Revision Requests
2020
26 Projects
9 Revision Requests
2021
18 Projects
9 Revision Requests
If actual duration falls within the IA range the variance is 0.
Note: Graph compares the posted IA duration range with the actual project duration
2022
4 Projects
1 Revision Request
Number of Months from IA Range
Chart: 
| NOGRR174 - AVR and PSS Testing Requirements | NPRR809 - GTC or GTL for New Generation Interconnection | NPRR817, NPRR847, VCMRR021 - Create a Panhandle Hub | NPRR821 - Elimination of the CRR Deration Process | NPRR833, NPRR749 - Modify PTP Obligation Bid Clearing Change | NPRR842 - Study Area Load Information | NPRR845 - RMR Process and Agreement Revisions | NPRR858 - Provide Complete Current Operating Plan (COP) Data | NPRR865, NPRR880 - Publish RTM Shift Factors for Hubs, Load Zones, and DC Ties | NPRR866, RRGRR017 - RRGRR Related to NPRR866, Mapping Registered Distributed Generation and Load Resources to Transmission Loads in the Network Operations Model | NPRR877 - Use of Actual Interval Data for IDR ESI IDs for Initial Settlement - Phase 2 | NPRR899 - Digital Certificate and User Security Administrator Clarifications and Opt Out Procedure | NPRR901, NPRR910, OBDRR010 - Switchable Generation Resource Status Code | NPRR914 - Addition of Controllable Load Resources to 60-Day Reports | NPRR925, SCR798 - PTP Obligation Bid ID Limit | SCR793 - SSR Related Telemetry for Transmission Service Provider (TSP) Operators | SCR794 - Update SCED Limit Calculation | SCR796, OBDRR003, OBDRR014 - Change Validation Rules to Preclude Certain Transactions at Resource Nodes within Private Use Networks | VCMRR022 - Determination of Fuel Adder Price for Coal and Lignite Resources | NPRR856, NPRR884 - Treatment of OFFQS Status in Day-Ahead Make Whole and RUC Settlements Adjustments to Pricing and Settlement for Reliability Unit Commitments (RUCs) of On-Line Combined Cycle Generation Resources | NPRR873 - Posting of the ERCOT Wide Intra-Hour Wind Power and Load Forecast on the MIS Public | NPRR929 - PTP Obligations with Links to an Option DAM Award Eligibility | NPRR935 - Post All Wind and Solar Forecasts | NPRR951 - Active and Inactive SCED Constraint Reporting | PGRR057 - Responsibilities for Performing Geomagnetic Disturbance (GMD) Vulnerability | SCR797 - Provide IRR Current Operating Plan (COP) to TSPs | SCR802 - Enhance Communications of System Inertia | SCR803 - Enhance Wind Integration Report and Create Solar Integration Report and Solar Dashboard | NOGRR195 - NOGRR195 Generator Voltage Control Tolerance Band | NPRR1081 - NPRR1081 Revisions to Real-Time Reliability Deployment Price Adder to Consider Firm Load Shed | NPRR902 - NPRR902 ERCOT Critical Energy Infrastructure Information | NPRR905 - NPRR905 CRR Balancing Account Resettlement | NPRR974, NPRR978, NPRR1048, SCR806 - NPRR974 NPRR978 NPRR1048 SCR806 - Alignmt w Amndmnt PUCT SubsRule 25_505_Schedule | NPRR986, NPRR971, NPRR1043 - Implementation of NPRR986 BESTF-2 and NPRR971 | NPRR998 - NPRR998 ERS Deployment and Recall Messages | SCR804 - SCR804 ERCOT GridGeo Access for Transmission Operators | SCR811 - Integrate Solar Forecasts and SCR811 Implementation | SCR800, SCR809 - SCR800 and SCR809 Implementation
 | 1.0667 | 3.0667 | 0 | 0.4 | 6.4667 | 0.7 | 0 | 0 | 0 | 0.033333 | 0 | 1.4667 | 0 | 0 | 0 | 1.1667 | 0.93333 | 1.6 | 0 | -0.36667 | 6.4667 | -0.1 | 1.6667 | 0 | 11.3 | 4.9333 | 0 | -1 | -1.1667 | -0.26667 | 9.7333 | 10.8333 | 0 | 1.1667 | 0 | 4.1333 | -0.26667 | 0
2
1
34
12
3
4
5
8
6
9
10
11
13
14
15
16
18
17
19
22
20
21
23
24
25
26
27
28
29
30
31
32
33
35
36
37
38
7

## Slide 15: Revision Request Project Legend
NOGRR174, AVR and PSS Testing Requirements
NPRR809, GTC or GTL for New Generation Interconnection
NPRR817, NPRR847, VCMRR021, Create a Panhandle Hub
NPRR821, Elimination of the CRR Deration Process
NPRR833, NPRR749, Modify PTP Obligation Bid Clearing Change
NPRR842, Study Area Load Information
NPRR845, RMR Process and Agreement Revisions
NPRR858, Provide Complete Current Operating Plan (COP) Data
NPRR865, NPRR880, Publish RTM Shift Factors for Hubs, Load Zones, and DC Ties
NPRR866, RRGRR017, RRGRR Related to NPRR866, Mapping Registered Distributed Generation and Load Resources to Transmission Loads in the Network Operations Model
NPRR877, Use of Actual Interval Data for IDR ESI IDs for Initial Settlement - Phase 2
NPRR899, Digital Certificate and User Security Administrator Clarifications and Opt Out Procedure
NPRR901, NPRR90, OBDRR010, Switchable Generation Resource Status Code
NPRR914, Addition of Controllable Load Resources to 60-Day Reports
NPRR925, SCR798, PTP Obligation Bid ID Limit
SCR793, SSR Related Telemetry for Transmission Service Provider (TSP) Operators
SCR794, Update SCED Limit Calculation
SCR796, OBDRR003, OBDRR014, Change Validation Rules to Preclude Certain Transactions at Resource Nodes within Private Use Networks
VCMRR022, Determination of Fuel Adder Price for Coal and Lignite Resources
NPRR856, NPRR884, Treatment of OFFQS Status in Day-Ahead Make Whole and RUC Settlements
NPRR873, Posting of the ERCOT Wide Intra-Hour Wind Power and Load Forecast on the MIS Public
NPRR929, PTP Obligations with Links to an Option DAM Award Eligibility
NPRR935, Post All Wind and Solar Forecasts
NPRR951, Active and Inactive SCED Constraint Reporting
PGRR057, Responsibilities for Performing Geomagnetic Disturbance (GMD) Vulnerability
SCR797, Provide IRR Current Operating Plan (COP) to TSPs
SCR802, Enhance Communications of System Inertia
SCR803, Enhance Wind Integration Report and Create Solar Integration Report and Solar Dashboard
NOGRR195, NOGRR195 Generator Voltage Control Tolerance Band
NPRR1081, NPRR1081 Revisions to Real-Time Reliability Deployment Price Adder to Consider Firm Load Shed
NPRR902, NPRR902 ERCOT Critical Energy Infrastructure Information
NPRR905, NPRR905 CRR Balancing Account Resettlement
NPRR974,NPRR978, NPRR1048, SCR806, NPRR974 NPRR978 NPRR1048 SCR806 - Alignment w Amendment PUCT Substantive Rule 25_505_Schedule
NPRR986, NPRR971, NPRR1043, Implementation of NPRR986 BESTF-2 and NPRR971
NPRR998, NPRR998 ERS Deployment and Recall Messages
SCR8004, SCR804 ERCOT GridGeo Access for Transmission Operators
SCR811, Integrate Solar Forecasts and SCR811 Implementation
SCR800, SCR809, SCR800 and SCR809 Implementation

## Slide 16: Impact Analysis Statistics Summary
Cost Range RR PROJECTS | Below IA Range | Within IA Range | Exceed IA Range | Total
2019 | 6 | 10 | 3 | 19
2020 | 0 | 7 | 2 | 9
2021 | 1 | 3 | 5 | 9
2022 (½ yr.) | 0 | 1 | 0 | 1
Total | 7 | 21 | 10 | 38
Duration Range RR PROJECTS | Below IA Range | Within IA Range | Exceed IA Range | Total
2019 | 0 | 10 | 9 | 19
2020 | 3 | 2 | 4 | 9
2021 | 3 | 2 | 4 | 9
2022 (1/2 yr.) | 0 | 1 | 0 | 1
Total | 6 | 15 | 17 | 38