## Sheet1
Joint TX SET / MCT Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 2022-09-21
Agenda Item: | Decision / Resolution | Action Items :
Meeting Notes
Texas SET 08/25/2022 MCT 09/14/2022 | No Changes were made. | The Vice Chair will have these final versions posted to meeting pages.
Texas SET Change Control Call 10 AM
Change Control Number: 2022-839 Add new SAC04 code of “MSC057” for AMS Temporary Emergency Electric Energy Facilities (TEEEF) | Texas SET agreed to recommend to the Retail Market Subcommittee (RMS) to approve as an Emergency for Texas SET V4.0A and Redline Versions of the Implementation Guide.
RMS Update
System Change Request (SCR) 823: County Upload | RMS endorsed the move to submit the SCR to Protocol Revision Subcommittee (PRS) PRS approved and sent to the Technical Advisory Committee (TAC) for approval at their next meeting September 28.
2023 Flight Schedule | RMS approved the flight schedule
Change Controls | All Submitted were approved.
Lubbock Power and Light (LP&L) topics
Timeline | The Texas SET chair reviewed the timeline and allowed time for questions from the group.
Testing Scripts | ERCOT Staff reviewed the plan for testing and allowed time for questions.
MCT Continuous Service Agreement (CSA) | LPL is registered as a Muni, but will operate motr as an IOU TDSP.
Centerpoint Energy and ERCOT Staff Working on Changes to protocols and guides. | Centerpoint reviewed what proposed changes have been completed to date. Protocols, Retail Market Guide and Texas SET Guides need to be reviewed to determine if they have to be updated. PUCT needs to review any requirements from their side. CSA agreements have to be working by the time LPL goes live. | ERCOT will take over the review of the documents and provide feedback to the group if time allows. Given the need to provide a solution quickly ERCOT may take their feedback directly to RMS.
Texas SET V5.0 Testing document
The Texas SET Chair reviewed the draft document and made changes where needed. | Several meeting attendees agreed to meet to continue discussions outside of the regularly scheduled meeting. | The Texas SET Chair will send in invitation to those who volunteered to attend.
ERCOT Update
Market Test Flight 1022 update | ERCOT presented the 1022 Market Flight Test update.
Other Business
No Other Business was conducted.
Next Meeting-- WebEx Only | 2022-10-19
Attendees F-T-F
Attendees Webex
Bill Snyder AEP | Jamie Wood LPL
Brittney Albracht ERCOT | Jesse O Macias AEP
Carole Root AEP | Jim Lee Centerpoint Energy
Carolyn Reed Centerpoint Energy | Kathryn Thurman ERCOT
Casandra Jenkins/ Centpoint Energy | Kathy Scott Centerpoint Energy
Catherine Meiners ERCOT | Kim Se TNMP
Chris Dominguez | Lee Doehring Centerpoint Energy
Kyle Patrick NRG | Mark Pepdjonovic ESG
Dailey Smith - LPL | Melissa LP&L
Dave Michaelson ERCOT | Monica Jones Centerpoint
Deb Belin Earth Etch | Pam Shaw LPL
Diana Rehfeldt TNMP | Paul Williams ePsolutions, Inc
Eric Lotter GridMonitor | Paul Yockey ERCOT
Esther ? | Sheri Wiegand Vistra
Frank Nunes VertexOne | Stephen Wilson TXU Energy
Paula Shadle NEC | Steve Pliler Vistra
Sam Pak ONCOR | Tyler Krueger BDE