## Slide 1
LUBBOCK RETAIL INTEGRATION TASK FORCE
Nov 01, 2022
TEXAS SET: LPL0423

## Slide 2: LPL0423 key dates
Jan 11
Feb 03
Mar 08
Mar 13
Mar 14
Apr 24
May 05
May 08
Jun 23
Notice to market announcing 0427
Flight Administrator emails to MP Admins notifying them of necessary steps prior to sign up deadline
Sign up deadline
Testing specs are submitted in FlighTrak
Connectivity and Penny Testing begins (~96 MPs will perform these tasks)
Day 1 transactions flow
Flight scheduled to conclude
Contingency period begins
Contingency period ends

## Slide 3: TESTING
Flight is only for certified CRs
All Stand Alone or Parent Companies perform Connectivity and Penny Test (~96)
Seven of those Stand Alone or Parent Companies will participate in end-to-end testing with LPL
Two Scripts were created by TEXAS SET for LPL0423
Long contingency period after scripts are completed will allow for any other testing LPL would like or can be used to finish up Connectivity or Penny Tests