## Sheet1
Joint TX SET / MCT Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 2022-10-20
Agenda Item: | Decision / Resolution | Action Items :
Meeting Notes
| The notes were approved as written. | The Vice Chair will have the final version posted to the September meeting page key documents.
Retail Market Subcommittee (RMS) Update
Change Control 2022-839: Add new SAC04 code of “MSC057” for AMS Temporary Emergency Electric Energy Facilities (TEEEF). Approved | The Texas SET Chair provided the RMS update.
ERCOT Update
Market Test Flight 1022 update | The ERCOT Test Flight Administrator presented the 1022 Flight Test Update
Lubbock Power and Light (LP&L) topics
Timeline | Discussion was delay until the next meeting.
Testing Scripts | Discussion was delay until the next meeting.
MCT Continuous Service Agreement (CSA) | Discussion was delay until the next meeting.
Texas SET V5.0 Testing document
Testing Scripts | The Texas SET Chair reviewed the scripts developed and made changes where needed.
Flight Schedule | The Texas V5.0 Test Flight will be the first flight in 2024. The Texas SET Chair reviewed the current first flight schedule and made changes to allow more time for steps to be completed since the testing population will be greater than usual. Discussions were held related to how many flights will be held in 2024 as well as if new entrants into the market should test in the V5.0 flight. | More discussion will be held at future meetings.
650_02, 650_04 and 814_28, 09 New Reject Code Clarification | Centerpoint reviewed some of the reject codes that were added for V5.0 and clarified when these could be used.
Other Business
No Other Business was conducted.
Next Meeting-- WebEx Only | 2022-10-27
Attendees F-T-F
Attendees Webex
Bill Snyder AEP | Kim Wall Hansen Technologies
Catherine Meiners ERCOT | Kyle Patrick NRG
Connie Hermes NEC | Melissa Maldonado LP&L
Dailey Smith - LPL | Pam Shaw LPL
Darrell Miller, ESG | Paul Yockey ERCOT
Dave Michaelson ERCOT | Sam Pak ONCOR
Diana Rehfeldt TNMP | Sheri Wiegand Vistra
Eric Lotter GridMonitor | Sherry Clark ONCOR
Frank Nunes VertexOne | Stephen Wilson TXU Energy
Jeff Chen Centerpoint Energy | Steve Pliler Vistra
Jordon Troublefield ERCOT | Tyler Krueger BDE
Kathy Scott Centerpoint Energy