## Wind Chart
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Approved for Synchronization | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 17INR0061 | Capricorn IV repower | Sterling | 2022-05-31 | 2008-01-15 | 2020-08-19 | Wind | WT | 9 | 2022 | No
[6 empty] | 17INR0054 | Capricorn I & III repower | Sterling | 2022-07-30 | 2006-11-14 | 2021-03-04 | Wind | WT | 32 | 2022 | No
[6 empty] | 17INR0070 | Desert Sky repower | Pecos | 2022-08-31 | 2018-10-18 | 2019-09-06 | Wind | WT | 7.2 | 2022 | Yes
[6 empty] | 21INR0467 | Apogee Wind | Haskell | 2022-09-17 | 2022-05-13 | 2022-01-11 | Wind | WT | 393.24 | 2022 | Yes
[6 empty] | 19INR0120 | Sherbino II Wind repower | Pecos | 2022-09-24 | 2008-02-28 | 2020-06-09 | Wind | WT | -18 | 2022 | Yes
[6 empty] | 17INR0035 | Las Majadas Wind | Willacy | 2022-09-30 | 2018-04-13 | 2020-10-21 | Wind | WT | 272.6 | 2022 | Yes
[6 empty] | 21INR0539 | Anchor Wind II | Eastland | 2022-10-07 | 2020-11-30 | 2022-02-11 | Wind | WT | 128.7 | 2022 | Yes
[6 empty] | 22INR0562 | Anchor Wind IV | Eastland | 2022-10-07 | 2020-11-30 | 2022-05-05 | Wind | WT | 19.32 | 2022 | Yes
[6 empty] | 18INR0064 | Silver Star repower | Eastland | 2022-10-13 | 2018-10-16 | 2020-07-28 | Wind | WT | -7.2 | 2022 | Yes
[6 empty] | 20INR0019 | Trinity Hills Wind repower | Young | 2022-10-15 | 2018-10-17 | 2020-05-22 | Wind | WT | -27 | 2022 | No
[6 empty] | 17INR0027b | Coyote Wind | Scurry | 2022-10-29 | 2016-08-09 | 2020-11-25 | Wind | WT | 242.6 | 2022 | Yes
[6 empty] | 18INR0031 | Maryneal Wind | Nolan | 2022-10-31 | 2020-01-31 | 2021-04-23 | Wind | WT | 182.4 | 2022 | Yes
[6 empty] | 20INR0068 | Blackjack Creek Wind | Bee | 2022-11-01 | 2019-10-24 | 2022-02-15 | Wind | WT | 240.5 | 2022 | Yes
[6 empty] | 19INR0145 | Aquilla Lake Wind | Hill | 2022-11-18 | 2020-06-30 | 2021-09-09 | Wind | WT | 202 | 2022 | Yes
[6 empty] | 20INR0256 | Aquilla Lake 2 Wind | Hill | 2022-11-18 | 2020-06-30 | 2021-09-24 | Wind | WT | 100 | 2022 | Yes
[6 empty] | 16INR0081 | Mesteno Wind | Starr | 2022-12-01 | 2018-04-25 | 2019-12-12 | Wind | WT | 201.6 | 2022 | Yes
[6 empty] | 20INR0083 | Baird North Wind | Callahan | 2022-12-01 | 2019-05-31 | 2021-08-20 | Wind | WT | 350 | 2022 | Yes
[6 empty] | 19INR0052 | TG East Wind | Knox | 2022-12-09 | 2018-10-22 | 2021-09-27 | Wind | WT | 336 | 2022 | Yes
[6 empty] | 20INR0129 | Foxtrot Wind | Bee | 2022-12-27 | 2020-05-05 | 2022-03-09 | Wind | WT | 268.2 | 2022 | Yes
[6 empty] | 16INR0085 | Priddy Wind | Mills | 2022-12-30 | 2020-08-13 | 2021-11-19 | Wind | WT | 302.4 | 2022 | Yes
[6 empty] | 19INR0100 | Prairie Hill Wind | McLennan | 2022-12-30 | 2018-09-17 | 2020-11-12 | Wind | WT | 300 | 2022 | Yes
[6 empty] | 21INR0324 | Board Creek Wind | Navarro | 2022-12-30 | 2021-08-19 | 2022-10-06 | Wind | WT | 299.2 | 2022 | Yes
[6 empty] | 17INR0068 | Sweetwater 2 repower | Nolan | 2022-12-31 | 2003-06-27 | 2017-12-20 | Wind | WT | 7.3 | 2022 | No
[6 empty] | 17INR0069 | Trent repower | Nolan | 2022-12-31 | 2018-10-19 | 2019-05-09 | Wind | WT | 6.4 | 2022 | No
[6 empty] | 18INR0073 | Sweetwater 1 repower | Nolan | 2022-12-31 | 2002-10-23 |  | Wind | WT | 3 | 2022 | No
[6 empty] | 20INR0097 | El Sauz Ranch | Willacy | 2022-12-31 | 2021-01-27 |  | Wind | WT | 301.5 | 2022 | Yes
[6 empty] | 22INR0517 | Ray Gulf Wind | Wharton | 2022-12-31 | 2022-05-13 |  | Wind | WT | 207 | 2022 | No
[6 empty] | 19INR0174 | Elbow Creek repower | Howard | 2023-01-01 | 2007-11-30 | 2019-06-27 | Wind | WT | 0 | 2023 | No
[6 empty] | 15INR0064b | Harald (BearKat Wind B) | Glasscock | 2023-01-31 | 2018-05-30 | 2020-05-12 | Wind | WT | 162.1 | 2023 | Yes
[6 empty] | 20INR0120 | Vortex Wind | Throckmorton | 2023-02-06 | 2020-12-01 | 2022-02-23 | Wind | WT | 350 | 2023 | Yes
[6 empty] | 22INR0550 | BLUE SUMMIT I REPOWER | Wilbarger | 2023-02-11 | 2012-02-22 | 2022-11-04 | Wind | WT | 4.4 | 2023 | No
[6 empty] | 20INR0296 | Sand Bluff Wind Repower | Glasscock | 2023-02-22 | 2006-11-11 | 2022-11-01 | Wind | WT | 89.5 | 2023 | No
[6 empty] | 18INR0043 | Lacy Creek wind | Glasscock | 2023-03-09 | 2017-09-28 |  | Wind | WT | 301.3 | 2023 | Yes
[6 empty] | 20INR0250 | Aguayo Wind | Mills | 2023-03-09 | 2022-04-29 |  | Wind | WT | 196 | 2023 | Yes
[6 empty] | 21INR0387 | Anchor Wind | Eastland | 2023-03-10 | 2020-11-30 | 2022-02-11 | Wind | WT | 98.9 | 2023 | Yes
[6 empty] | 21INR0546 | Anchor Wind III | Eastland | 2023-03-10 | 2020-11-30 |  | Wind | WT | 16 | 2023 | Yes
[6 empty] | 21INR0401 | Young Wind | Young | 2023-03-15 | 2022-02-18 |  | Wind | WT | 499.14 | 2023 | Yes
[6 empty] | 20INR0249 | Appaloosa Run Wind | Upton | 2023-03-30 | 2021-04-12 |  | Wind | WT | 175 | 2023 | Yes
[6 empty] | 20INR0033 | WILDWIND | Cooke | 2023-03-31 | 2020-02-21 | 2021-02-10 | Wind | WT | 180.08 | 2023 | Yes
[6 empty] | 19INR0080 | Whitehorse Wind | Fisher | 2023-04-01 | 2018-12-05 | 2019-12-27 | Wind | WT | 418.9 | 2023 | Yes
[6 empty] | 22INR0326 | Inertia Wind | Haskell | 2023-04-11 | 2021-05-04 |  | Wind | WT | 301.3 | 2023 | Yes
[6 empty] | 19INR0177 | Crawfish | Wharton | 2023-07-31 | 2021-07-06 |  | Wind | WT | 163.2 | 2023 | Yes
[6 empty] | 21INR0325 | Sheep Creek Wind | Callahan | 2023-09-01 | 2021-10-01 |  | Wind | WT | 153 | 2023 | No
[6 empty] | 20INR0040 | Montgomery Ranch Wind | Foard | 2023-12-15 | 2022-03-22 |  | Wind | WT | 200.2 | 2023 | Yes
[6 empty] | 14INR0033 | Goodnight Wind | Armstrong | 2023-12-30 | 2018-03-07 |  | Wind | WT | 531 | 2023 | No
[6 empty] | 17INR0052 | Horse13 CallD repower | Taylor | 2023-12-31 | 2019-05-22 | 2021-03-16 | Wind | WT | 44 | 2023 | Yes
[6 empty] | 17INR0053 | HHGT repower Horse13+CallD | Taylor | 2023-12-31 | 2009-06-26 | 2021-09-10 | Wind | WT | 44 | 2023 | No
[6 empty] | 18INR0069 | Indian Mesa repower | Pecos | 2023-12-31 | 2018-12-04 | 2018-11-02 | Wind | WT | 82.5 | 2023 | No
[6 empty] | 18INR0079 | Woodward I repower | Pecos | 2023-12-31 | 2018-12-12 | 2019-11-13 | Wind | WT | 0 | 2023 | Yes
[6 empty] | 18INR0080 | Woodward 2 repower | Pecos | 2023-12-31 | 2018-12-18 | 2018-12-19 | Wind | WT | 0 | 2023 | Yes
[6 empty] | 19INR0022 | Monte Alto I | Willacy | 2023-12-31 | 2020-02-13 |  | Wind | WT | 189 | 2023 | Yes
[6 empty] | 19INR0023 | Monte Alto 2 Wind | Willacy | 2023-12-31 | 2022-03-22 |  | Wind | WT | 272.26 | 2023 | Yes
[6 empty] | 20INR0217 | CAROL wind | Potter | 2023-12-31 | 2020-09-11 |  | Wind | WT | 165.7 | 2023 | No
[6 empty] | 16INR0112 | Loma Pinta Wind | La Salle | 2024-01-31 | 2017-12-13 |  | Wind | WT | 197.01 | 2024 | No
[6 empty] | 19INR0117 | Roadrunner Crossing Wind | Eastland | 2024-01-31 | 2021-04-17 |  | Wind | WT | 128 | 2024 | Yes
[6 empty] | 18INR0068 | Loraine Windpark Phase III | Mitchell | 2024-05-10 | 2018-04-10 |  | Wind | WT | 100 | 2024 | Yes
[6 empty] | 22INR0502 | Shamrock | Crockett | 2024-07-01 | 2022-05-13 |  | Wind | WT | 223.92 | 2024 | Yes
[6 empty] | 16INR0104 | Big Sampson Wind | Crockett | 2024-10-01 | 2019-11-08 |  | Wind | WT | 400 | 2024 | No
[6 empty] | 20INR0047 | Siete | Webb | 2024-10-31 | 2022-06-30 |  | Wind | WT | 375.06 | 2024 | Yes
[6 empty] | 18INR0030 | Canyon Wind | Scurry | 2024-12-02 | 2018-09-20 |  | Wind | WT | 309.12 | 2024 | Yes
Month/Year | Cumulative operational, No FS, and FS Posted | Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Small Generator
2022-11-20 | 35917.81 | 35917.81 | 0 | 0 | 0
2022-12-20 | 36429.31 | 35917.81 | 301.5 | 210 | 0
2023-01-20 | 36429.31 | 35917.81 | 301.5 | 210 | 0
2023-02-20 | 36429.31 | 35917.81 | 301.5 | 210 | 0
2023-03-20 | 37616.75 | 35917.81 | 1488.94 | 210 | 0
2023-04-20 | 37918.05 | 35917.81 | 1790.24 | 210 | 0
2023-05-20 | 37918.05 | 35917.81 | 1790.24 | 210 | 0
2023-06-20 | 37918.05 | 35917.81 | 1790.24 | 210 | 0
2023-07-20 | 38081.25 | 35917.81 | 1953.44 | 210 | 0
2023-08-20 | 38081.25 | 35917.81 | 1953.44 | 210 | 0
2023-09-20 | 38234.25 | 35917.81 | 1953.44 | 363 | 0
2023-10-20 | 38234.25 | 35917.81 | 1953.44 | 363 | 0
2023-11-20 | 38234.25 | 35917.81 | 1953.44 | 363 | 0
2023-12-20 | 39592.41 | 35917.81 | 2614.9 | 1059.7 | 0
2024-01-20 | 39917.42 | 35917.81 | 2742.9 | 1256.71 | 0
2024-02-20 | 39917.42 | 35917.81 | 2742.9 | 1256.71 | 0
2024-03-20 | 39917.42 | 35917.81 | 2742.9 | 1256.71 | 0
2024-04-20 | 39917.42 | 35917.81 | 2742.9 | 1256.71 | 0

## Solar Chart
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Approved for Synchronization | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 20INR0026 | Longbow Solar | Brazoria | 2022-11-30 | 2021-01-06 | 2022-07-27 | Solar | PV | 78.15 | 2022 | Yes
[6 empty] | 21INR0384 | Ratliff (Concho Valley) Solar | Tom Green | 2022-12-02 | 2020-09-28 | 2022-07-25 | Solar | PV | 159.8 | 2022 | Yes
[6 empty] | 19INR0131 | Rowland Solar I | Fort Bend | 2022-12-09 | 2020-09-23 | 2022-06-13 | Solar | PV | 101.75 | 2022 | Yes
[6 empty] | 20INR0081 | Strategic Solar 1 | Ellis | 2022-12-13 | 2020-01-13 | 2021-10-06 | Solar | PV | 136.85 | 2022 | Yes
[6 empty] | 20INR0082 | Vision Solar 1 | Navarro | 2022-12-13 | 2020-01-13 | 2021-10-08 | Solar | PV | 129.24 | 2022 | Yes
[6 empty] | 21INR0493 | Ellis Solar | Ellis | 2022-12-15 | 2021-04-15 |  | Solar | PV | 81 | 2022 | Yes
[6 empty] | 15INR0059 | Emerald Grove Solar | Pecos | 2022-12-30 | 2017-12-04 | 2022-01-04 | Solar | PV | 108 | 2022 | Yes
[6 empty] | 19INR0169 | Sun Valley Solar | Hill | 2022-12-30 | 2020-03-15 | 2022-11-01 | Solar | PV | 252 | 2022 | Yes
[6 empty] | 22INR0254 | Pisgah Ridge Solar | Navarro | 2022-12-30 | 2021-01-27 | 2022-10-07 | Solar | PV | 253.85 | 2022 | Yes
[6 empty] | 19INR0073 | McLean (Shakes) Solar | Zavala | 2022-12-31 | 2018-10-26 | 2022-07-20 | Solar | PV | 206 | 2022 | Yes
[6 empty] | 22INR0527 | Lily Solar (Close Boze - I20 - Rosehill) | Kaufman | 2022-12-31 | 2019-03-29 |  | Solar | PV | 0 | 2022 | Yes
[6 empty] | 21INR0221 | Samson Solar 1 | Lamar | 2023-01-15 | 2020-08-26 | 2021-08-31 | Solar | PV | 250 | 2023 | Yes
[6 empty] | 21INR0491 | Samson Solar 3 | Lamar | 2023-01-15 | 2020-08-27 | 2021-10-26 | Solar | PV | 250 | 2023 | Yes
[6 empty] | 21INR0375 | Grizzly Ridge Solar | Hamilton | 2023-01-18 | 2021-06-09 |  | Solar | PV | 101.68 | 2023 | Yes
[6 empty] | 20INR0098 | Danciger Solar | Brazoria | 2023-01-20 | 2020-03-20 | 2022-07-13 | Solar | PV | 203.2 | 2023 | Yes
[6 empty] | 21INR0323 | Spanish Crown | Falls | 2023-02-10 | 2021-01-13 |  | Solar | PV | 103.1 | 2023 | Yes
[6 empty] | 21INR0434 | Golinda Solar | Falls | 2023-02-10 | 2021-03-21 |  | Solar | PV | 103.1 | 2023 | Yes
[6 empty] | 22INR0404 | Fence Post Solar | Navarro | 2023-02-14 | 2021-08-12 |  | Solar | PV | 240.92 | 2023 | Yes
[6 empty] | 18INR0050 | Mustang Creek Solar | Jackson | 2023-02-16 | 2019-01-04 |  | Solar | PV | 150.5 | 2023 | Yes
[6 empty] | 21INR0233 | Taygete II Solar | Pecos | 2023-02-17 | 2019-03-27 | 2022-11-14 | Solar | PV | 203.8 | 2023 | Yes
[6 empty] | 19INR0041 | Myrtle Solar | Brazoria | 2023-02-24 | 2019-11-13 |  | Solar | PV | 321.2 | 2023 | Yes
[6 empty] | 20INR0205 | Roseland Solar | Falls | 2023-03-01 | 2020-12-10 | 2022-09-26 | Solar | PV | 254 | 2023 | Yes
[6 empty] | 22INR0359 | Dileo Solar | Bosque | 2023-03-01 | 2021-09-17 |  | Solar | PV | 72 | 2023 | Yes
[6 empty] | 22INR0506 | Roseland Solar II | Falls | 2023-03-01 | 2020-12-10 | 2022-09-26 | Solar | PV | 254 | 2023 | Yes
[6 empty] | 22INR0205 | Sbranch Solar | Wharton | 2023-03-03 | 2020-07-26 |  | Solar | PV | 233.52 | 2023 | Yes
[6 empty] | 19INR0001 | Texas Solar Nova | Kent | 2023-03-15 | 2019-07-01 |  | Solar | PV | 253.51 | 2023 | Yes
[6 empty] | 21INR0205 | Radian Solar | Brown | 2023-03-23 | 2021-01-08 | 2022-08-17 | Solar | PV | 327.42 | 2023 | Yes
[6 empty] | 21INR0213 | Vancourt Solar | Cameron | 2023-03-23 | 2020-06-11 | 2022-08-29 | Solar | PV | 45.73 | 2023 | Yes
[6 empty] | 19INR0085 | Blue Jay Solar | Grimes | 2023-03-27 | 2020-10-26 | 2022-06-28 | Solar | PV | 141.05 | 2023 | Yes
[6 empty] | 21INR0538 | Blue Jay Solar II | Grimes | 2023-03-27 | 2020-10-26 | 2021-11-19 | Solar | PV | 68.95 | 2023 | Yes
[6 empty] | 21INR0406 | Buffalo Creek | Fort Bend | 2023-03-31 | 2020-04-16 | 2022-01-06 | Solar | PV | 438.75 | 2023 | Yes
[6 empty] | 20INR0164 | BPL Files Solar | Hill | 2023-04-21 | 2021-03-10 |  | Solar | PV | 148.7 | 2023 | Yes
[6 empty] | 20INR0074 | Pitts Dudik Solar | Hill | 2023-05-20 | 2021-05-10 |  | Solar | PV | 50 | 2023 | Yes
[6 empty] | 22INR0335 | Estonian Solar | Delta | 2023-06-01 | 2021-08-12 |  | Solar | PV | 202.5 | 2023 | Yes
[6 empty] | 23INR0045 | GP Solar | Van Zandt | 2023-06-01 | 2021-12-29 |  | Solar | PV | 121.97 | 2023 | Yes
[6 empty] | 22INR0360 | Jade Solar | Scurry | 2023-06-30 | 2021-01-22 |  | Solar | PV | 326.6 | 2023 | Yes
[6 empty] | 22INR0412 | Andromeda Solar | Scurry | 2023-06-30 | 2021-04-01 |  | Solar | PV | 326.6 | 2023 | Yes
[6 empty] | 22INR0242 | Bright Arrow Solar | Hopkins | 2023-07-07 | 2021-02-18 |  | Solar | PV | 305.07 | 2023 | Yes
[6 empty] | 22INR0202 | Delilah Solar 1 | Lamar | 2023-07-29 | 2020-12-22 |  | Solar | PV | 300 | 2023 | Yes
[6 empty] | 18INR0053 | Tavener Solar | Fort Bend | 2023-07-30 | 2019-06-30 |  | Solar | PV | 143.61 | 2023 | Yes
[6 empty] | 20INR0130 | Plainview Solar | Wharton | 2023-07-31 | 2020-05-29 | 2021-07-26 | Solar | PV | 514 | 2023 | Yes
[6 empty] | 22INR0363 | Hayhurst Texas Solar | Culberson | 2023-08-01 | 2021-09-09 |  | Solar | PV | 25.68 | 2023 | Yes
[6 empty] | 22INR0352 | Sparta Solar | Bee | 2023-08-15 | 2020-08-14 |  | Solar | PV | 252.35 | 2023 | Yes
[6 empty] | 23INR0084 | Lavaca Bay Solar | Matagorda | 2023-08-15 | 2022-06-15 |  | Solar | PV | 243.46 | 2023 | No
[6 empty] | 20INR0255 | Dawn Solar | Deaf Smith | 2023-08-25 | 2021-01-04 |  | Solar | PV | 515.66 | 2023 | No
[6 empty] | 21INR0490 | Samson Solar 2 | Lamar | 2023-09-01 | 2020-08-27 |  | Solar | PV | 203 | 2023 | Yes
[6 empty] | 22INR0203 | Delilah Solar 2 | Lamar | 2023-09-01 | 2020-12-22 |  | Solar | PV | 317.58 | 2023 | Yes
[6 empty] | 22INR0356 | Jungmann Solar | Milam | 2023-09-01 | 2022-02-15 |  | Solar | PV | 40 | 2023 | No
[6 empty] | 23INR0070 | Chillingham Solar | Bell | 2023-09-19 | 2022-02-04 |  | Solar | PV | 359.37 | 2023 | No
[6 empty] | 21INR0413 | Big Star Solar | Bastrop | 2023-09-29 | 2020-10-02 |  | Solar | PV | 203.1 | 2023 | Yes
[6 empty] | 21INR0351 | 7V Solar | Fayette | 2023-09-30 | 2020-09-01 |  | Solar | PV | 244.6 | 2023 | Yes
[6 empty] | 23INR0042 | Delilah Solar 3 | Lamar | 2023-09-30 | 2020-12-22 |  | Solar | PV | 200 | 2023 | Yes
[6 empty] | 23INR0060 | Delilah Solar 4 | Lamar | 2023-09-30 | 2020-12-22 |  | Solar | PV | 90 | 2023 | Yes
[6 empty] | 21INR0431 | Galloway 2 Solar | Concho | 2023-10-01 | 2019-12-20 |  | Solar | PV | 113.88 | 2023 | Yes
[6 empty] | 21INR0031 | Indigo Solar | Fisher | 2023-10-26 | 2022-09-15 |  | Solar | PV | 125 | 2023 | No
[6 empty] | 19INR0203 | Angelo Solar | Tom Green | 2023-10-30 | 2021-12-03 |  | Solar | PV | 195 | 2023 | No
[6 empty] | 22INR0223 | Eiffel Solar | Lamar | 2023-10-30 | 2021-03-19 |  | Solar | PV | 240 | 2023 | Yes
Month/Year | Cumulative operational, No FS, and FS Posted | Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Small Generator | 22INR0409 | Stampede Solar | Hopkins | 2023-10-30 | 2021-12-15 |  | Solar | PV | 259.07 | 2023 | Yes
2022-11-20 | 14029.1 | 14029.1 | 0 | 0 | 0 | 23INR0035 | Starling Solar | Gonzales | 2023-10-30 | 2021-12-03 |  | Solar | PV | 123 | 2023 | No
2022-12-20 | 14117.5 | 14029.1 | 81 | 0 | 7.4 | 21INR0203 | Eastbell Milam Solar | Milam | 2023-10-31 | 2022-09-02 |  | Solar | PV | 244.86 | 2023 | Yes
2023-01-20 | 14219.18 | 14029.1 | 182.68 | 0 | 7.4 | 21INR0353 | Big Elm Solar | Bell | 2023-10-31 | 2022-09-01 |  | Solar | PV | 222.32 | 2023 | Yes
2023-02-20 | 15138 | 14029.1 | 1101.5 | 0 | 7.4 | 19INR0155 | Morrow Lake Solar | Frio | 2023-11-08 | 2019-08-29 |  | Solar | PV | 204 | 2023 | Yes
2023-03-20 | 15697.03 | 14029.1 | 1660.53 | 0 | 7.4 | 21INR0304 | Halo Solar | Bell | 2023-11-11 | 2022-08-18 |  | Solar | PV | 254 | 2023 | No
2023-04-20 | 15845.73 | 14029.1 | 1809.23 | 0 | 7.4 | 20INR0069 | Danish Fields Solar | Wharton | 2023-11-13 | 2020-02-24 |  | Solar | PV | 619.1 | 2023 | Yes
2023-05-20 | 15895.73 | 14029.1 | 1859.23 | 0 | 7.4 | 22INR0511 | Gransolar Texas One | Milam | 2023-11-23 | 2022-02-09 |  | Solar | PV | 60.86 | 2023 | No
2023-06-20 | 16873.4 | 14029.1 | 2836.9 | 0 | 7.4 | 22INR0455 | Blue Sky Sol | Crockett | 2023-11-24 | 2022-02-01 |  | Solar | PV | 101.2 | 2023 | Yes
2023-07-20 | 17622.08 | 14029.1 | 3585.58 | 0 | 7.4 | 20INR0266 | Tres Bahias Solar | Calhoun | 2023-11-30 | 2020-08-07 |  | Solar | PV | 195 | 2023 | Yes
2023-08-20 | 18659.23 | 14029.1 | 3863.61 | 759.12 | 7.4 | 23INR0044 | Parliament Solar | Waller | 2023-12-04 | 2022-05-26 |  | Solar | PV | 482.69 | 2023 | No
2023-09-20 | 20316.88 | 14029.1 | 5121.89 | 1158.49 | 7.4 | 23INR0223 | Garcitas Creek Solar | Jackson | 2023-12-08 | 2022-06-30 |  | Solar | PV | 201.94 | 2023 | Yes
2023-10-20 | 21840.01 | 14029.1 | 6202.02 | 1601.49 | 7.4 | 23INR0080 | Soda Lake Solar 1 SLF | Crane | 2023-12-12 | 2022-03-23 |  | Solar | PV | 202.59 | 2023 | No
2023-11-20 | 23274.17 | 14029.1 | 7321.32 | 1916.35 | 7.4 | 21INR0261 | Horizon Solar | Frio | 2023-12-15 | 2019-07-12 |  | Solar | PV | 203.5 | 2023 | Yes
2023-12-20 | 27120.83 | 14029.1 | 9792.9 | 3291.43 | 7.4 | 22INR0295 | Coral Solar | Falls | 2023-12-15 | 2021-12-29 |  | Solar | PV | 154.8 | 2023 | Yes
2024-01-20 | 27858.38 | 14029.1 | 10429.86 | 3392.02 | 7.4 | 22INR0281 | Pink Solar | Hunt | 2023-12-16 | 2022-08-30 |  | Solar | PV | 151 | 2023 | No
2024-02-20 | 28680.54 | 14029.1 | 10590.86 | 4053.18 | 7.4 | 21INR0499 | Neptune Solar | Jackson | 2023-12-22 | 2000-05-30 |  | Solar | PV | 204.65 | 2023 | Yes
2024-03-20 | 31437.18 | 14029.1 | 12586.73 | 4813.95 | 7.4 | 21INR0278 | Fighting Jays Solar | Fort Bend | 2023-12-23 | 2020-06-22 | 2022-03-31 | Solar | PV | 351.29 | 2023 | Yes
2024-04-20 | 31950.88 | 14029.1 | 13100.43 | 4813.95 | 7.4 | 22INR0342 | Matagorda Solar | Matagorda | 2023-12-28 | 2022-06-08 |  | Solar | PV | 101 | 2023 | No
[6 empty] | 20INR0210 | Hopkins Solar | Hopkins | 2023-12-29 | 2020-09-25 |  | Solar | PV | 252.8 | 2023 | No
[6 empty] | 20INR0269 | Texas Solar Nova 2 | Kent | 2023-12-29 | 2021-07-21 |  | Solar | PV | 201.14 | 2023 | Yes
[6 empty] | 24INR0015 | Five Wells Solar | Bell | 2023-12-29 | 2022-09-01 |  | Solar | PV | 355.4 | 2023 | Yes
[6 empty] | 20INR0091 | Fagus Solar Park | Childress | 2023-12-31 | 2019-02-21 |  | Solar | PV | 517.35 | 2023 | Yes
[6 empty] | 20INR0222 | Tyson Nick Solar | Lamar | 2023-12-31 | 2020-08-28 |  | Solar | PV | 90 | 2023 | No
[6 empty] | 21INR0019 | Zier Solar | Kinney | 2023-12-31 | 2020-10-22 |  | Solar | PV | 162.99 | 2023 | Yes
[6 empty] | 21INR0257 | Mercury Solar | Hill | 2023-12-31 | 2021-10-18 |  | Solar | PV | 206.11 | 2023 | Yes
[6 empty] | 22INR0397 | Buckeye Corpus Fuels Solar | Nueces | 2023-12-31 | 2022-09-19 |  | Solar | PV | 57.59 | 2023 | Yes
[6 empty] | 23INR0153 | Mercury II Solar | Hill | 2023-12-31 | 2021-10-18 |  | Solar | PV | 206.11 | 2023 | Yes
[6 empty] | 23INR0231 | Rocinante Solar | Gonzales | 2023-12-31 | 2022-04-25 |  | Solar | PV | 95 | 2023 | No
[6 empty] | 22INR0354 | XE MURAT Solar | Harris | 2024-01-04 | 2022-03-04 |  | Solar | PV | 60.36 | 2024 | Yes
[6 empty] | 23INR0111 | GULF STAR SOLAR SLF | Wharton | 2024-01-10 | 2021-10-01 |  | Solar | PV | 451.6 | 2024 | Yes
[6 empty] | 20INR0248 | Second Division Solar | Brazoria | 2024-01-15 | 2020-10-14 |  | Solar | PV | 100.59 | 2024 | No
[6 empty] | 19INR0035 | Norton Solar | Runnels | 2024-01-31 | 2019-06-20 |  | Solar | PV | 125 | 2024 | Yes
[6 empty] | 21INR0256 | Amsterdam Solar | Brazoria | 2024-02-01 | 2022-02-17 |  | Solar | PV | 509.88 | 2024 | No
[6 empty] | 20INR0230 | Markum Solar | McLennan | 2024-02-05 | 2021-06-28 |  | Solar | PV | 161 | 2024 | Yes
[6 empty] | 21INR0368 | Eliza Solar | Kaufman | 2024-02-15 | 2022-08-04 |  | Solar | PV | 151.28 | 2024 | No
[6 empty] | 22INR0283 | Peregrine Solar | Goliad | 2024-03-01 | 2021-06-19 |  | Solar | PV | 303.36 | 2024 | Yes
[6 empty] | 23INR0144 | Galactic Solar | Grayson | 2024-03-01 | 2022-08-12 |  | Solar | PV | 205.2 | 2024 | No
[6 empty] | 20INR0080 | Frye Solar | Swisher | 2024-03-15 | 2021-02-06 |  | Solar | PV | 514.1 | 2024 | Yes
[6 empty] | 20INR0086 | Arroyo Solar | Cameron | 2024-03-15 | 2021-09-28 |  | Solar | PV | 180 | 2024 | Yes
[6 empty] | 23INR0026 | Baker Branch Solar | Lamar | 2024-03-15 | 2022-02-14 |  | Solar | PV | 400 | 2024 | Yes
[6 empty] | 22INR0279 | Clutch City Solar | Brazoria | 2024-03-21 | 2022-09-30 |  | Solar | PV | 204.17 | 2024 | No
[6 empty] | 19INR0134 | Cottonwood Bayou Solar | Brazoria | 2024-03-31 | 2019-11-13 |  | Solar | PV | 351.4 | 2024 | No
[6 empty] | 21INR0389 | Red Tailed Hawk Solar | Wharton | 2024-03-31 | 2020-08-28 |  | Solar | PV | 353.41 | 2024 | Yes
[6 empty] | 21INR0458 | Porter Solar | Denton | 2024-03-31 | 2022-02-03 |  | Solar | PV | 245 | 2024 | Yes
[6 empty] | 23INR0007 | Outpost Solar | Webb | 2024-04-01 | 2022-01-11 |  | Solar | PV | 513.7 | 2024 | Yes
[6 empty] | 19INR0103 | Rodeo Solar | Andrews | 2024-05-01 | 2019-08-20 |  | Solar | PV | 200 | 2024 | Yes
[6 empty] | 20INR0050 | Castro Solar | Castro | 2024-05-15 | 2020-11-30 |  | Solar | PV | 222.95 | 2024 | No
[6 empty] | 21INR0341 | Space City Solar | Wharton | 2024-05-30 | 2021-01-06 |  | Solar | PV | 609.74 | 2024 | Yes
[6 empty] | 21INR0022 | Red Holly Solar | Dawson | 2024-05-31 | 2020-10-19 |  | Solar | PV | 260 | 2024 | No
[6 empty] | 22INR0482 | Rowland Solar II | Fort Bend | 2024-05-31 | 2020-09-23 |  | Solar | PV | 202.81 | 2024 | Yes
[6 empty] | 23INR0047 | Charger Solar | Refugio | 2024-05-31 | 2021-06-05 |  | Solar | PV | 406.77 | 2024 | Yes
[6 empty] | 20INR0035 | Angus Solar | Bosque | 2024-06-01 | 2021-12-06 |  | Solar | PV | 112 | 2024 | Yes
[6 empty] | 20INR0143 | Soda Lake Solar 2 SLF | Crane | 2024-06-01 | 2022-02-28 |  | Solar | PV | 202.99 | 2024 | No
[6 empty] | 20INR0216 | Starr Solar Ranch | Starr | 2024-06-01 | 2020-10-01 |  | Solar | PV | 136.66 | 2024 | Yes
[6 empty] | 21INR0220 | Maleza Solar | Wharton | 2024-06-01 | 2021-01-27 |  | Solar | PV | 254.94 | 2024 | No
[6 empty] | 22INR0270 | Brass Fork Solar 1 | Haskell | 2024-06-01 | 2021-06-14 |  | Solar | PV | 304.78 | 2024 | Yes
[6 empty] | 22INR0454 | DR Solar | Culberson | 2024-06-01 | 2022-02-07 |  | Solar | PV | 46.02 | 2024 | Yes
[6 empty] | 23INR0235 | Hoyte Solar | Milam | 2024-06-01 | 2022-10-14 |  | Solar | PV | 203.97 | 2024 | No
[6 empty] | 23INR0300 | Greater Bryant G Solar | Midland | 2024-06-01 | 2022-07-18 |  | Solar | PV | 41.6 | 2024 | No
[6 empty] | 21INR0395 | SunRay | Uvalde | 2024-06-12 | 2021-07-07 |  | Solar | PV | 204.09 | 2024 | Yes
[6 empty] | 20INR0208 | Signal Solar | Hunt | 2024-06-14 | 2020-10-23 |  | Solar | PV | 51.84 | 2024 | No
[6 empty] | 22INR0251 | Shaula I Solar | DeWitt | 2024-06-28 | 2022-02-16 |  | Solar | PV | 205.2 | 2024 | Yes
[6 empty] | 21INR0391 | Grandslam Solar | Atascosa | 2024-06-30 | 2021-01-29 |  | Solar | PV | 121.89 | 2024 | No
[6 empty] | 21INR0393 | Talitha Solar | Jim Wells | 2024-06-30 | 2022-06-08 |  | Solar | PV | 131.03 | 2024 | Yes
[6 empty] | 21INR0424 | Tierra Bonita Solar | Pecos | 2024-07-12 | 2022-09-08 |  | Solar | PV | 309.68 | 2024 | No
[6 empty] | 20INR0203 | Pine Forest Solar | Hopkins | 2024-07-15 | 2020-07-29 |  | Solar | PV | 305 | 2024 | No
[6 empty] | 23INR0180 | Jackalope Solar | San Patricio | 2024-07-31 | 2021-09-30 |  | Solar | PV | 156.4 | 2024 | Yes
[6 empty] | 21INR0362 | Oystercatcher Solar | Ellis | 2024-08-20 | 2021-08-20 |  | Solar | PV | 220.33 | 2024 | No
[6 empty] | 23INR0021 | Hornet Solar | Swisher | 2024-08-30 | 2021-12-06 |  | Solar | PV | 611 | 2024 | Yes
[6 empty] | 23INR0296 | Trojan Solar | Cooke | 2024-08-31 | 2022-10-10 |  | Solar | PV | 206.11 | 2024 | No
[6 empty] | 23INR0061 | Noria Solar DCC | Nueces | 2024-09-01 | 2022-10-12 |  | Solar | PV | 145 | 2024 | Yes
[6 empty] | 22INR0267 | Shaula II Solar | DeWitt | 2024-09-18 | 2022-04-27 |  | Solar | PV | 205.2 | 2024 | Yes
[6 empty] | 20INR0236 | Old Hickory Solar | Jackson | 2024-09-24 | 2020-06-30 |  | Solar | PV | 206 | 2024 | Yes
[6 empty] | 18INR0058 | Texana Solar | Wharton | 2024-09-27 | 2021-06-30 |  | Solar | PV | 152.34 | 2024 | Yes
[6 empty] | 23INR0160 | Grimes County Solar | Grimes | 2024-09-30 | 2022-06-23 |  | Solar | PV | 210 | 2024 | Yes
[6 empty] | 24INR0023 | Compadre Solar | Hill | 2024-10-01 | 2022-11-12 |  | Solar | PV | 405.31 | 2024 | No
[6 empty] | 20INR0241 | Crowded Star Solar | Jones | 2024-10-03 | 2019-12-17 |  | Solar | PV | 217.6 | 2024 | Yes
[6 empty] | 21INR0421 | Armadillo Solar | Navarro | 2024-10-15 | 2021-02-02 |  | Solar | PV | 204 | 2024 | Yes
[6 empty] | 21INR0253 | Ulysses Solar | Coke | 2024-11-01 | 2022-10-03 |  | Solar | PV | 150 | 2024 | Yes
[6 empty] | 23INR0089 | Donegal Solar | Dickens | 2024-11-30 | 2022-07-25 |  | Solar | PV | 204.2 | 2024 | No
[6 empty] | 19INR0042 | Long Point Solar | Brazoria | 2024-12-01 | 2019-10-24 |  | Solar | PV | 101.25 | 2024 | No
[6 empty] | 23INR0162 | Redonda Solar | Zapata | 2024-12-01 | 2021-12-28 |  | Solar | PV | 253.21 | 2024 | Yes
[6 empty] | 21INR0021 | Green Holly Solar | Dawson | 2024-12-31 | 2020-05-19 |  | Solar | PV | 413.6 | 2024 | No
[6 empty] | 21INR0223 | Tulsita Solar | Goliad | 2024-12-31 | 2022-09-19 |  | Solar | PV | 260.99 | 2024 | Yes
[6 empty] | 21INR0268 | Greyhound Solar | Ector | 2024-12-31 | 2022-01-15 |  | Solar | PV | 608.7 | 2024 | No
[6 empty] | 21INR0344 | Lunis Creek Solar SLF | Jackson | 2024-12-31 | 2021-10-29 |  | Solar | PV | 617.12 | 2024 | Yes
[6 empty] | 22INR0374 | Inertia Solar | Haskell | 2024-12-31 | 2021-05-04 |  | Solar | PV | 258.35 | 2024 | Yes
[6 empty] | 23INR0027 | Cachena Solar SLF | Wilson | 2024-12-31 | 2021-11-23 |  | Solar | PV | 600 | 2024 | Yes
[6 empty] | 23INR0155 | Umbra (Stockyard) Solar | Franklin | 2024-12-31 | 2022-10-11 |  | Solar | PV | 210 | 2024 | No
[6 empty] | 22INR0257 | Corazon Solar Phase II | Webb | 2025-01-12 | 2020-08-04 |  | Solar | PV | 203.9 | 2025 | No
[6 empty] | 23INR0054 | Tanglewood Solar | Brazoria | 2025-01-16 | 2022-11-01 |  | Solar | PV | 257 | 2025 | No
[6 empty] | 21INR0428 | Nabatoto Solar North | Leon | 2025-02-01 | 2021-02-26 |  | Solar | PV | 365.7 | 2025 | No
[6 empty] | 22INR0274 | Crowded Star Solar II | Jones | 2025-02-03 | 2019-12-17 |  | Solar | PV | 188.8 | 2025 | No
[6 empty] | 16INR0049 | Nazareth Solar | Castro | 2025-03-24 | 2018-05-10 |  | Solar | PV | 204 | 2025 | No
Small Generator
[6 empty] | 12INR0059b | HOVEY (Barilla Solar 1B) | Pecos | 2022-12-12 | 2013-12-26 |  | Solar | PV | 7.4 | 2022 | Yes

## Battery Chart
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Approved for Synchronization | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 21INR0479 | Endurance Park Storage | Scurry | 2022-12-13 | 2021-02-13 | 2022-10-04 | Battery | BA | 51.5 | 2022 | Yes
[6 empty] | 21INR0474 | Anchor BESS | Eastland | 2022-12-15 | 2021-03-15 | 2022-08-17 | Battery | BA | 71.45 | 2022 | Yes
[6 empty] | 20INR0290 | River Valley Storage 1 | Williamson | 2022-12-16 | 2021-08-25 |  | Battery | BA | 51.5 | 2022 | Yes
[6 empty] | 20INR0293 | River Valley Storage 2 | Williamson | 2022-12-16 | 2021-08-25 |  | Battery | BA | 51.5 | 2022 | Yes
[6 empty] | 21INR0357 | SP TX-12B BESS | Upton | 2022-12-29 | 2020-05-01 | 2022-11-29 | Battery | BA | 25.12 | 2022 | Yes
[6 empty] | 20INR0280 | High Lonesome BESS | Crockett | 2022-12-30 | 2020-08-26 | 2022-06-01 | Battery | BA | 51.06 | 2022 | Yes
[6 empty] | 20INR0281 | Queen BESS | Upton | 2022-12-30 | 2020-08-06 | 2022-04-12 | Battery | BA | 51.06 | 2022 | Yes
[6 empty] | 22INR0528 | Lily Storage (Close Boze - I20 - Rosehill) | Kaufman | 2022-12-31 | 2019-03-29 |  | Battery | BA | 0 | 2022 | Yes
[6 empty] | 20INR0291 | Silicon Hill Storage | Travis | 2023-01-09 | 2020-03-27 | 2022-06-02 | Battery | BA | 104.62 | 2023 | Yes
[6 empty] | 21INR0244 | Madero Grid | Hidalgo | 2023-01-27 | 2019-12-06 | 2022-05-26 | Battery | BA | 101.52 | 2023 | Yes
[6 empty] | 21INR0522 | Madero Unit2 | Hidalgo | 2023-01-27 | 2020-10-27 | 2022-05-26 | Battery | BA | 101.52 | 2023 | Yes
[6 empty] | 22INR0302 | Bright Arrow Storage | Hopkins | 2023-02-28 | 2022-03-17 |  | Battery | BA | 103.56 | 2023 | Yes
[6 empty] | 22INR0405 | Fence Post BESS | Navarro | 2023-03-03 | 2021-08-12 |  | Battery | BA | 73.11 | 2023 | Yes
[6 empty] | 22INR0509 | Turquoise Storage | Hunt | 2023-03-07 | 2021-10-22 |  | Battery | BA | 196.21 | 2023 | Yes
[6 empty] | 22INR0280 | Roseland Storage | Falls | 2023-03-10 | 2022-01-26 | 2022-11-10 | Battery | BA | 51.63 | 2023 | Yes
[6 empty] | 21INR0473 | Vortex BESS | Throckmorton | 2023-03-14 | 2021-04-23 | 2022-05-23 | Battery | BA | 121.83 | 2023 | Yes
[6 empty] | 20INR0268 | Pyron BESS II | Nolan | 2023-03-15 | 2007-10-15 |  | Battery | BA | 30.2 | 2023 | Yes
[6 empty] | 22INR0551 | Wolf Tank Storage | Webb | 2023-03-15 | 2021-11-04 |  | Battery | BA | 155.48 | 2023 | Yes
[6 empty] | 23INR0019 | Blue Jay BESS | Grimes | 2023-03-17 | 2022-01-24 | 2022-10-25 | Battery | BA | 51.63 | 2023 | Yes
[6 empty] | 21INR0484 | Mustang Creek Storage | Jackson | 2023-03-29 | 2019-01-04 |  | Battery | BA | 70.5 | 2023 | Yes
[6 empty] | 22INR0398 | Sabal Storage | Cameron | 2023-05-15 | 2022-05-02 |  | Battery | BA | 18 | 2023 | Yes
[6 empty] | 22INR0485 | House Mountain | Brewster | 2023-05-31 | 2021-07-07 |  | Battery | BA | 63 | 2023 | Yes
[6 empty] | 23INR0072 | BRP Tortolas BESS | Brazoria | 2023-05-31 | 2021-07-15 |  | Battery | BA | 50.67 | 2023 | Yes
[6 empty] | 21INR0469 | Big Star Storage | Bastrop | 2023-06-01 | 2020-10-02 |  | Battery | BA | 80 | 2023 | Yes
[6 empty] | 22INR0336 | Estonian Storage | Delta | 2023-06-01 | 2021-08-12 |  | Battery | BA | 101.6 | 2023 | Yes
[6 empty] | 23INR0354 | Bordertown BESS | Starr | 2023-06-01 | 2022-10-12 |  | Battery | BA | 106.15 | 2023 | Yes
[6 empty] | 21INR0492 | Stockyard Grid Batt | Tarrant | 2023-07-01 | 2022-10-26 |  | Battery | BA | 150.6 | 2023 | Yes
[6 empty] | 22INR0338 | Limousin Oak Storage | Grimes | 2023-07-01 | 2022-04-01 |  | Battery | BA | 104.62 | 2023 | Yes
[6 empty] | 23INR0239 | Giga Texas Energy Storage | Travis | 2023-07-10 | 2021-12-03 |  | Battery | BA | 131.05 | 2023 | Yes
[6 empty] | 23INR0371 | Rodeo Ranch Energy Storage | Reeves | 2023-07-17 | 2022-02-01 |  | Battery | BA | 307.46 | 2023 | Yes
[6 empty] | 22INR0366 | BRP Libra BESS | Guadalupe | 2023-07-28 | 2022-02-16 |  | Battery | BA | 202.38 | 2023 | Yes
[6 empty] | 22INR0372 | BRP Hydra BESS | Pecos | 2023-08-01 | 2021-05-08 |  | Battery | BA | 202.31 | 2023 | Yes
[6 empty] | 22INR0384 | BRP Pavo BESS | Pecos | 2023-08-01 | 2021-07-15 |  | Battery | BA | 176.85 | 2023 | Yes
[6 empty] | 22INR0322 | BRP Paleo BESS | Hale | 2023-08-11 | 2021-02-05 |  | Battery | BA | 202.36 | 2023 | Yes
[6 empty] | 22INR0325 | BRP Dickens BESS | Dickens | 2023-08-11 | 2020-11-03 |  | Battery | BA | 202.33 | 2023 | Yes
[6 empty] | 22INR0490 | Callisto I Energy Center | Harris | 2023-09-01 | 2022-05-17 |  | Battery | BA | 203.04 | 2023 | Yes
[6 empty] | 22INR0495 | TIMBERWOLF BESS 2 | Upton | 2023-09-01 | 2021-10-08 |  | Battery | BA | 150 | 2023 | No
[6 empty] | 23INR0079 | Chillingham Storage | Bell | 2023-09-19 | 2022-02-04 |  | Battery | BA | 153.75 | 2023 | No
[6 empty] | 23INR0154 | Ebony Energy Storage | Comal | 2023-10-17 | 2022-05-31 |  | Battery | BA | 204.97 | 2023 | Yes
[6 empty] | 22INR0410 | Stampede BESS | Hopkins | 2023-10-30 | 2021-12-15 |  | Battery | BA | 73.11 | 2023 | Yes
[6 empty] | 22INR0328 | Inertia BESS | Haskell | 2023-10-31 | 2021-05-04 |  | Battery | BA | 13 | 2023 | Yes
[6 empty] | 22INR0552 | Sowers Storage | Kaufman | 2023-10-31 | 2022-04-22 |  | Battery | BA | 203 | 2023 | Yes
[6 empty] | 21INR0450 | Danish Fields Storage | Wharton | 2023-11-15 | 2022-06-27 |  | Battery | BA | 150.83 | 2023 | No
[6 empty] | 22INR0327 | Hummingbird Storage | Denton | 2023-11-29 | 2022-02-23 |  | Battery | BA | 103.8 | 2023 | Yes
[6 empty] | 22INR0349 | BRP Antlia BESS | Val Verde | 2023-12-01 | 2021-06-05 |  | Battery | BA | 70.95 | 2023 | Yes
[6 empty] | 22INR0353 | BRP Carina BESS | Nueces | 2023-12-01 | 2021-08-03 |  | Battery | BA | 151.85 | 2023 | Yes
[6 empty] | 22INR0388 | BRP Cachi BESS | Guadalupe | 2023-12-01 | 2021-06-11 |  | Battery | BA | 202.46 | 2023 | No
[6 empty] | 23INR0124 | Coral Storage | Falls | 2023-12-15 | 2022-10-28 |  | Battery | BA | 101 | 2023 | Yes
[6 empty] | 23INR0369 | Anemoi Energy Storage | Hidalgo | 2023-12-20 | 2022-01-05 |  | Battery | BA | 205 | 2023 | Yes
[6 empty] | 21INR0027 | Zier Storage | Kinney | 2023-12-31 | 2020-10-22 |  | Battery | BA | 40.41 | 2023 | Yes
[6 empty] | 23INR0232 | Rocinante BESS | Gonzales | 2023-12-31 | 2022-04-25 |  | Battery | BA | 33 | 2023 | No
[6 empty] | 22INR0417 | Amsterdam Storage | Brazoria | 2024-02-01 | 2022-04-14 |  | Battery | BA | 201.13 | 2024 | No
[6 empty] | 22INR0260 | Eliza Storage | Kaufman | 2024-02-15 | 2022-08-04 |  | Battery | BA | 100.62 | 2024 | No
[6 empty] | 24INR0306 | Arroyo Storage SLF | Cameron | 2024-03-15 | 2022-08-10 |  | Battery | BA | 0 | 2024 | No
[6 empty] | 23INR0363 | Brazos Bend BESS | Fort Bend | 2024-03-29 | 2022-10-18 |  | Battery | BA | 101.21 | 2024 | Yes
[6 empty] | 21INR0443 | Cottonwood Bayou Storage | Brazoria | 2024-03-31 | 2022-03-18 |  | Battery | BA | 150.83 | 2024 | No
[6 empty] | 22INR0368 | Padua Grid BESS | Bexar | 2024-03-31 | 2021-11-16 |  | Battery | BA | 202.6 | 2024 | Yes
[6 empty] | 22INR0401 | Eval Storage | Cameron | 2024-04-01 | 2022-02-03 |  | Battery | BA | 255 | 2024 | Yes
Month/Year | Cumulative operational, No FS, and FS Posted | Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Small Generator | 24INR0147 | Citadel BESS | Harris | 2024-05-07 | 2022-07-29 |  | Battery | BA | 206.32 | 2024 | No
2022-11-20 | 2787.86 | 2787.86 | 0 | 0 | 0 | 21INR0505 | Ramsey Storage | Wharton | 2024-05-11 | 2022-08-11 |  | Battery | BA | 510.4 | 2024 | No
2022-12-20 | 2900.81 | 2787.86 | 103 | 0 | 9.95 | 21INR0029 | Green Holly Storage | Dawson | 2024-05-31 | 2020-10-19 |  | Battery | BA | 50 | 2024 | No
2023-01-20 | 2910.76 | 2787.86 | 103 | 0 | 19.9 | 21INR0033 | Red Holly Storage | Dawson | 2024-05-31 | 2020-10-19 |  | Battery | BA | 50 | 2024 | No
2023-02-20 | 3014.32 | 2787.86 | 206.56 | 0 | 19.9 | 23INR0166 | Great Kiskadee Storage | Hidalgo | 2024-08-01 | 2022-06-30 |  | Battery | BA | 103.05 | 2024 | Yes
2023-03-20 | 3539.82 | 2787.86 | 732.06 | 0 | 19.9 | 23INR0062 | Noria Storage | Nueces | 2024-09-01 | 2022-10-12 |  | Battery | BA | 75 | 2024 | No
2023-04-20 | 3539.82 | 2787.86 | 732.06 | 0 | 19.9 | 23INR0343 | Guajillo Energy Storage | Webb | 2024-09-30 | 2021-12-21 |  | Battery | BA | 201.09 | 2024 | Yes
2023-05-20 | 3671.49 | 2787.86 | 863.73 | 0 | 19.9 | 20INR0246 | Ryan Energy Storage | Coryell | 2024-10-21 | 2021-02-18 |  | Battery | BA | 50 | 2024 | Yes
2023-06-20 | 3989.09 | 2787.86 | 1151.48 | 0 | 49.75 | 23INR0103 | Donegal BESS | Dickens | 2024-11-30 | 2022-07-25 |  | Battery | BA | 101.3 | 2024 | No
2023-07-20 | 4885.2 | 2787.86 | 2047.59 | 0 | 49.75 | 21INR0517 | Tidwell Prairie Storage 1 | Robertson | 2024-12-01 | 2022-11-03 |  | Battery | BA | 304.78 | 2024 | No
2023-08-20 | 5669.05 | 2787.86 | 2831.44 | 0 | 49.75 | 23INR0156 | Umbra (Stockyard) BESS | Franklin | 2024-12-31 | 2022-10-11 |  | Battery | BA | 73 | 2024 | No
2023-09-20 | 6175.84 | 2787.86 | 3034.48 | 303.75 | 49.75 | 23INR0340 | Larkspur Energy Storage | Upton | 2025-01-31 | 2022-02-28 |  | Battery | BA | 307.46 | 2025 | No
2023-10-20 | 6669.92 | 2787.86 | 3528.56 | 303.75 | 49.75 | 22INR0375 | Inertia BESS 2 | Haskell | 2025-03-31 | 2021-05-04 |  | Battery | BA | 100.77 | 2025 | Yes
2023-11-20 | 6924.55 | 2787.86 | 3632.36 | 454.58 | 49.75
2023-12-20 | 7729.22 | 2787.86 | 4201.57 | 690.04 | 49.75 | Small Generator
2024-01-20 | 7729.22 | 2787.86 | 4201.57 | 690.04 | 49.75 | 22INR0596 | Grizzly Ridge BESS | Hamilton | 2022-12-28 | 2021-10-18 |  | Battery | BA | 9.95 | 2023 | Yes
2024-02-20 | 8030.97 | 2787.86 | 4201.57 | 991.79 | 49.75 | 22INR0603 | Olney BESS | Young | 2023-06-15 |  |  | Battery | BA | 9.95 | 2023 | No
2024-03-20 | 8485.61 | 2787.86 | 4505.38 | 1142.62 | 49.75 | 23INR0520 | Pleasanton BESS | Atascosa | 2023-06-15 | 2022-08-17 |  | Battery | BA | 9.95 | 2023 | Yes
2024-04-20 | 8740.61 | 2787.86 | 4760.38 | 1142.62 | 49.75 | 23INR0521 | Junction BESS | Kimble | 2023-06-15 | 2022-08-17 |  | Battery | BA | 9.95 | 2023 | Yes
[6 empty] | 23INR0522 | Diboll Bess | Angelina | 2023-01-18 | 2022-08-22 |  | Battery | BA | 9.95 | 2023 | Yes

## Gas-Combined Cycle Chart
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Approved for Synchronization | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 21INR0202 | R Massengale | Lubbock | 2021-11-15 | 2020-10-30 | 2021-07-26 | Gas | CC | 58 | 2021 | Yes
[6 empty] | 22INR0533 | Temple Generation I Repower | Bell | 2022-06-09 | 2012-06-21 |  | Gas | CC | 67 | 2022 | Yes
[6 empty] | 19INR0014 | Formosa Increase | Calhoun | 2022-12-31 | 2019-04-30 | 2020-03-04 | Gas | CC | 240 | 2022 | Yes
[6 empty] | 20INR0286 | Wise County Power Repower (CT1, CT2) | Wise | 2023-05-01 | 2001-03-19 |  | Gas | CC | 21 | 2023 | Yes
[6 empty] | 23INR0472 | Frontera Energy Center | Hidalgo | 2023-06-30 | 2022-11-01 |  | Gas | CC | 524 | 2023 | Yes
Month/Year | Cumulative operational, No FS, and FS Posted | Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Small Generator
2022-11-20 | 43370.779 | 43303.779 | 67 | 0 | 0
2022-12-20 | 43370.779 | 43303.779 | 67 | 0 | 0
2023-01-20 | 43370.779 | 43303.779 | 67 | 0 | 0
2023-02-20 | 43370.779 | 43303.779 | 67 | 0 | 0
2023-03-20 | 43370.779 | 43303.779 | 67 | 0 | 0
2023-04-20 | 43370.779 | 43303.779 | 67 | 0 | 0
2023-05-20 | 43391.779 | 43303.779 | 88 | 0 | 0
2023-06-20 | 43915.779 | 43303.779 | 612 | 0 | 0
2023-07-20 | 43915.779 | 43303.779 | 612 | 0 | 0
2023-08-20 | 43915.779 | 43303.779 | 612 | 0 | 0
2023-09-20 | 43915.779 | 43303.779 | 612 | 0 | 0
2023-10-20 | 43915.779 | 43303.779 | 612 | 0 | 0
2023-11-20 | 43915.779 | 43303.779 | 612 | 0 | 0
2023-12-20 | 43915.779 | 43303.779 | 612 | 0 | 0
2024-01-20 | 43915.779 | 43303.779 | 612 | 0 | 0
2024-02-20 | 43915.779 | 43303.779 | 612 | 0 | 0
2024-03-20 | 43915.779 | 43303.779 | 612 | 0 | 0
2024-04-20 | 43915.779 | 43303.779 | 612 | 0 | 0

## Gas-Other Chart
[7 empty] | INR | Project Name | County | Projected COD | IA Signed | Approved for Synchronization | Fuel | Technology | Capacity (MW) | Year | Financial Security
[7 empty] | 21INR0201 | Brandon | Lubbock | 2021-11-15 | 2020-10-30 | 2021-07-19 | Gas | GT | 21 | 2021 | Yes
[7 empty] | 21INR0506 | Ty Cooke | Lubbock | 2021-11-15 | 2020-10-30 | 2021-07-14 | Gas | GT | 33 | 2021 | Yes
[7 empty] | 21INR0512 | Colorado Bend I Expansion | Wharton | 2023-01-17 | 2021-12-08 |  | Gas | GT | 78 | 2023 | Yes
[7 empty] | 22INR0607 | Beachwood Power Station Phase 2 (Mark One) | Brazoria | 2023-01-20 | 2021-07-21 |  | Gas | GT | 153 | 2023 | Yes
[7 empty] | 23INR0095 | Brotman Power Station | Brazoria | 2023-06-01 | 2021-10-01 |  | Gas | GT | 299 | 2023 | Yes
[7 empty] | 17INR0022 | MIRAGE | Harris | 2023-12-01 | 2016-08-31 |  | Gas | GT | 11 | 2023 | Yes
[7 empty] | 23INR0506 | Beachwood II Power Station | Brazoria | 2024-03-01 | 2022-08-01 |  | Gas | GT | 102 | 2024 | Yes
[7 empty] | 23INR0339 | Remy Jade Power Station | Harris | 2024-04-01 | 2022-08-01 |  | Gas | GT | 408 | 2024 | Yes
Month/Year | Cumulative operational, No FS, and FS Posted | Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned | Small Generator
2022-11-20 | 23654.99 | 23654.99 | 0 | 0 | 0 | 0
2022-12-20 | 23663.39 | 23654.99 | 0 | 0 | 8.4 | 0
2023-01-20 | 23895.59 | 23654.99 | 231 | 0 | 9.6 | 0
2023-02-20 | 23900.39 | 23654.99 | 231 | 0 | 14.4 | 0
2023-03-20 | 23901.99 | 23654.99 | 231 | 0 | 16 | 0
2023-04-20 | 23901.99 | 23654.99 | 231 | 0 | 16 | 0
2023-05-20 | 23901.99 | 23654.99 | 231 | 0 | 16 | 0
2023-06-20 | 24200.99 | 23654.99 | 530 | 0 | 16 | 0
2023-07-20 | 24200.99 | 23654.99 | 530 | 0 | 16 | 0
2023-08-20 | 24200.99 | 23654.99 | 530 | 0 | 16 | 0
2023-09-20 | 24200.99 | 23654.99 | 530 | 0 | 16 | 0
2023-10-20 | 24200.99 | 23654.99 | 530 | 0 | 16 | 0
2023-11-20 | 24200.99 | 23654.99 | 530 | 0 | 16 | 0
2023-12-20 | 24211.99 | 23654.99 | 541 | 0 | 16 | 0
2024-01-20 | 24211.99 | 23654.99 | 541 | 0 | 16 | 0
2024-02-20 | 24211.99 | 23654.99 | 541 | 0 | 16 | 0
2024-03-20 | 24313.99 | 23654.99 | 643 | 0 | 16 | 0
2024-04-20 | 24721.99 | 23654.99 | 1051 | 0 | 16 | 0