## Slide 1: Lubbock Retail Integration Task Force – LRITF December 6th, 2022
Chris Rowley Michael Winegeart Sheri Wiegand

## Slide 2: LRITF Meeting 11/1/22
TXSET Flight Testing Update – LPL0423
  Flight Test LPL0423 approved by RMS for existing REPs to test with LP&L.
  Full end to end testing will be conducted by LP&L with seven market participants with the understanding the results will be accepted to apply to other REPs
  All existing REPs intending to enter the LP&L market will be required to conduct penny and connectivity via FlighTrak
  Ensure uniqueness of flight testing is clearly communicated to the market – 1st market notice distributed 11/3/22; additional notices forthcoming
  If new REPs intend to enter the LP&L market at the time LP&L enters into customer choice (projected for October 2023), they must participate in the first flight 0223 with an application deadline of 1/18/23 including all registration support (PUCT, etc)
The Task Force will continue to be the forum for vetting, reporting, and posting all ACTION items identified for LP&L’s transition to competition.

## Slide 3: LRITF Meeting 11/1/22 continued
The Task Force will continue to discuss four major implementation items that must be resolved prior to LP&L entering competition:
Pro-Forma Retail Access Tariff
CSA & Mass Transition Transaction Workflows
Customer Data Issue
Customer Choice Billing
Major Implementation Issues

## Slide 4: LRITF Meeting 11/1/22 continued
ISSUE: The Pro-Forma Retail Access Tariff (PUCT Subst. Rule 25.215) for MOUs has not been reviewed since market open. Existing tariff restricts an MOU from entering retail competition if intending to operate similar to an IOU.
RESOLUTION: LP&L has worked with market participants and PUCT Staff to draft redlines to the existing pro forma tariff to allow flexibility in operations.
UPDATE: PUCT approved the Proposal for Publication at the November 30th Open Meeting in PUCT Project# 54212
January 9, 2023 – Comments due
January 23, 2023 – Reply comments due
January 23, 2023 – Deadline to request a public hearing
Pro-Forma Retail Access Tariff

## Slide 5: LRITF Meeting 11/1/22 continued
ISSUE: ERCOT’s functionality for CSA and Mass Transition workflows for MOUs allows for CSAs (814_22s) and Drops (814_14s) to flow back to the MOU. LP&L prefers to operate as an IOU whereby the customer would transition to a designated REP.
RESOLUTION: ERCOT Staff is proposing to update applicable protocols and guides allowing for flexibility of an MOU entering competition to select a preferred operation – MOU path or an IOU path.
UPDATE: ERCOT is reviewing Nodal Protocols 15.1.9 – IOU and 15.1.10 – MOU and preparing a necessary NPRR and RGRR for stakeholder review.
CSA & Mass Transition Transaction Workflows

## Slide 6: LRITF Meeting 11/1/22 continued
ISSUE: Per TX Utility Code 182, LP&L is unable to share any customer data with an entity such as ERCOT. REPs are not included in the restriction. Impacts include 867s (consumption data), Mass Customer Lists, Customer Billing & Contact Information, and daily LSE files.
RESOLUTION: ERCOT & LP&L are seeking a possible legislative solution.
UPDATE: ERCOT & LP&L were planning to present solution at December’s LRITF meeting.
Customer Data Issue

## Slide 7: LRITF Meeting 11/1/22 continued
ISSUE: Per PURA Section 40.057, an end use customer in an opt-in MOU service area has the option of receiving a single bill (energy+delivery) or separate bills for each. LP&L intends and is prepared to adopt the single bill scenario through REPs, however, a plan will need to be drafted for the instances in which a customer chooses for separate bills
RESOLUTION: REPs and TDSPs are determining the impacts and timeline of any protocol/guide/system changes needed to support customer choice billing.
UPDATE: Market participants (LP&L, REPs, ERCOT, EDI Service Providers, TDSPs) have met to frame issue, identify operational impacts, and seek regulatory/legislative guidance on potential solutions. Details will be discussed at next LRITF meeting.
Customer Choice Billing

## Slide 8: Completed Action Items Q&A
Customer Education
Q: Will LP&L’s customer sales tax exemption certificates transfer to a customer’s REP of choice/DREP? A: NO, customers will be responsible for providing their tax certificate to their new REP of choice/DREP upon transition to ensure sales taxes are not assessed.

## Slide 9: TIMELINE of Actions
Q1 2023
Q2 2023
Q3 2023
Q4 2023
LP&L Rates
Customer Enrollment Process – Detailed Timeline
PUCT Complaint Process / Application of PUCT Rules
Transaction Timelines / TXSET Timelines
CSA Process
Mass Customer Lists
Power to Choose website
Customer Forums/Town Halls
Flight Testing / Bank Testing
CBCI files
Default REP Selection Process
DNP Blackout Period
Market Operations Group Established
GO LIVE – Transition to Competition
Q4 2022
Pro Forma Tariff
Access Agreement
POLR Process
Safety Net Process
Tampering Information Process
Smart Meter Texas
ESI IDs in TDSP Extract
RMG Chapter 8 Revisions
Historical Usage Requests
TDSP AMS Data Practices
ERCOT Activities: SAC04s, Load Profiles
TSDP Activities: Critical Care, DLFs, Solar/DG, Switch Hold Files, BUSIDDRQ, Call Center, OGFLT, Weather Moratoriums, Proration

## Slide 10: Lritf meeting Held after RMS @ 1:30 PM December 6th, 2022
AGENDA:
Pro Forma Tariff PFP – PUCT Project 54212
LP&L Proposed Legislation –
Customer Data
Dual Billing & POLR
CSA & Mass Transition Transaction Flows
Customer Choice Billing Operations
Review List of Integration Activities
Open Discussion