## Slide 1
Resource Integration Topics
Jay Teixeira
ERCOT
Resource Integration Working Group
December 15, 2022

## Slide 2: Quarterly Stability Assessment (QSA)
Planning Guide 5.9
Next Deadline for QSA
If a GINR is not included in QSA, its Initial Synchronization date will be automatically delayed to the next quarter
All-Inclusive Generation Resource Initial Synchronization Date | Last Day for an IE to meet prerequisites as listed in paragraph (4) below | Completion of Quarterly Stability Assessment
Upcoming January, February, March | Prior August 1 | End of October
Upcoming April, May, June | Prior November 1 | End of January
Upcoming July, August, September | Prior February 1 | End of April
Upcoming October, November, December | Prior May 1 | End of July

## Slide 3: Quarterly Stability Assessment (QSA)
Planning Guide 5.9, Quarterly Stability Assessment
Issue’s seen in previous QSA’s
  10 day comment period for FIS
    Needs to be complete before QSA deadline
    TSPs need to plan for it
  Dynamic/PSCAD Model Review
    Dependent on FIS Stability study
    Need to meet PG 6.9 15 to 30 days prior to QSA deadline
PSSE Model Quality Test Required
PSCAD Model Quality Test and Unit Model Validation required
TSAT Model Required – If PSSE model is UDM, then TSAT model should be UDM

## Slide 7: Discussion Items (From April 2022 meeting)
What are Generator Terminals
  As modeled in ERCOT Operations Model
  For non-conventional, usually 34.5 kV
Dissimilar Real Power/Turbine Rating
  Need to study summer and winter with higher turbine ratings in winter
  Use highest sustainable rating regardless of temperature

## Slide 8: Weather Preparedness
The Protocol 22 Attachment K has been replaced by new language in the PUC section 25 rules:

## Slide 9: RIOO-IS Updated 12/9/2022
The new release allows entry of resource data into RIOO database rather than use of RARF
The existing RARF forms that were in RIOO-IS were supposed to be migrated to the new database
Migration effort is delayed
IE/RE may re-enter data into RIOO-IS or wait for Migration effort
Screenshot document created to help with RIOO-IS

## Slide 10: Active RR’s
None

## Slide 11: Other contact information
ResourceIntegrationDepartment@ercot.com is distribution list for Resource Integration department
Mailing List
  RESOURCE_INTEGRATION@LISTS.ERCOT.COM

## Slide 12: Questions?
Thank you!