## Sheet1
Joint TX SET / MCT Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 2022-11-16
Agenda Item: | Decision / Resolution | Action Items :
Meeting Notes October 20 and 27, 2022
| Both Sets of notes were approved. | The Texas SET Vice Chair will have these posted to the meeting page key documents.
ERCOT Update
Market Test Flight 1022 and 0223 Preview | It was noted that new entrants in the 0223 test flight will be eligible to test in the Lubbock Test flight, plus they will be encouraged to sign up early. The ERCOT Flight Administrator stated that Market Participants have the ability to sign up now for any of the flights in 2023. | The Texas SET Chair stated that verbal encouragement will be mentioned in other meetings to help get the word out.
Lubbock Power & Light (LPL) 0423 | ERCOT agreed to send additional notices for the test flights encouraging early signup for this flight due to the number possible testing entities. One meeting attendee asked how the entities would be chosen to test the full flight. It was stated that the decision had not been determined on which Competitive Retailers (CRs) would complete the end-to-end flight. LP&L provided the following contact information Marketops@lpandl.com to let Lubbock know they are interested in testing. ERCOT reviewed proposed changes to the Nodal Protocols to note how the MOU/ECs will implement Continuous Service Agreements. | The Texas SET Chair stated that verbal encouragement will be mentioned in other meetings to help get the word out. Texas SET will revisit the question of how the participants are chosen at the next meeting. The Texas SET Chair encouraged potential testing participants attend the next Task Force meeting in December.
Texas SET Version 5.0 Flight 0224 | The Texas SET Chair requested an update on the subject of new entrants being allowed to test during the first flight. Two TDSPs stated the Flight should include new entrants, but eliminate the 2nd flight in June to allow for stabilization; then have the October test flight. ERCOT requested emails from the TDSPs to support this path. | Texas SET will revisit the questions at the next meeting.
Market Coordination Team (MCT)
Issues Log Review | The ERCOT MCT reviewed some recommended changes to the guides. 814_19 will keep the NCC reject code and omit the duplicate code. Retail Market Guide Revision Request (RMGRR) to add section 7.19 Business Processes related to Continuous Service Agreements. Texas SET agreed to the changes. The ERCOT Market Rules attendee reviewed the path for approval of these changes. It was noted that these changes will have to be submitted by Monday November 21 to get it added to the December RMS meeting. Otherwise the changes will be reviewed by RMS in January. | The Texas SET Chair, Vice Chair and ERCOT will take the assignment to get the changes submitted to Market Rules. These will include the Business Case and any changes to both the RMGRR and the Nodal Protocol Change Request (NPRR). The ERCOT changes will be reviewed again at the next meeting.
Testing Questions
During this last flight BDE kept a log of items that we would like discussed at TX set for potential updates
BIG08 = “05” should say BIG08 = “00” for Mbank 810_03 | An update will be made to the script to correct this.
Email push notifications when a TDSP sends a task back to the CR – BDE does not get notified until ERCOT sends us an email. We would like to pbe more proactive when the CR sends back a transaction | It was noted that there was an issue with emails that is in the process of being corrected.
TDSP’s to have the ability to update Zip codes when they enter them incorrectly so the CR’s don’t have to try and remember the updated zip code throughout the two weeks | ERCOT noted that once the TDSP test beds are loaded there can be no changes.
CBCI Script could be updated to say “Simulated Customer Billing Contact Information file is sent via NAESB - five (5) contacts to be input in one file. One row should not contain CR DUNS number. This field needs to be empty. Note: File layout found in appendix F6 of Retail Market Guide.” | ERCOT noted the changes can be made fairly easy.
MBANK Script could be updated to not include the transactions that Nueces does not test. – this may just be a Nueces specific ask and with LPL coming on board they may complete the full flight of tests | This will be treated as a case by case basis
A new task for the TDSP’s to notify the CR and Service provider that the ACH and the 820 was received and successful. The task is closed but there is not a formal communication to the stakeholders involved | This will have to be implemented during an upgrade in the future. | ERCOT will bring changes back to the next meeting for review..
LPL (Open Discussion
See the MCT discussion
Other Business
The Texas SET Chair noted that Goals and Accomplishments may be reviewed next month.
Next Meeting-- WebEx Only | 2022-12-07
In the afternoon.
Attendees F-T-F
Attendees Webex
Aly B ? | Kathryn Thurman ERCOT
Bill Snyder AEP | Kathy Scott Centerpoint Energy
Carole Root AEP | Kim Se TNMP
Catherine Meiners ERCOT | Kim Wall Hansen Technologies
Matthew Abbene ONCOR | Kyle Patrick NRG
Melissa Maldonado LP&L | Laura G LPL
Monica Jones Centerpoint Energy | Mark Pepdjonovic ESG
Dave Michaelson ERCOT | Pam Shaw LPL
Deb Belin Earth Etch | Paul Yockey ERCOT
Debra Foster AEP | Paula Shadle NEC
Diana Rehfeldt TNMP | Ruben Gonzales
Eric Lotter GridMonitor | Sam Pak ONCOR
Frank Nunes VertexOne | Sheri Wiegand Vistra
James McElroy ONCOR | Stephen Wilson TXU Energy
Jamie Wood LPL | Steve Pliler Vistra
Jeff Chen Centerpoint Energy | Suzy Clifton ERCOT
John Schatz Vistra | Tyler Krueger BDE
Jordon Troublefield ERCOT | William Butler LPL