## Slide 1
Project Update
January 17, 2023
Troy Anderson
ERCOT Portfolio Management

## Slide 2
  Recent / Upcoming Project Highlights
  2022 Release Targets
  2023 Release Targets
  Additional Project Status Information
  Priority/Rank Options for Revision Requests with Impacts
    NPRR1149 – Implementation of Systematic AS Failed Quantity Charges
    NPRR1153 – ERCOT Fee Schedule Changes
  Technology Working Group (TWG)
    Next meeting TBD
Location of Revision Request Project Information: http://www.ercot.com/services/projects
Project Update Agenda

## Slide 3: Recent / Upcoming Project Highlights
2022 December Release – R6 – 12/6/2022-12/8/2022 Complete
  NPRR1084 – Improvements to Reporting of Resource Outages, Derates, & Startup Loading Failures
  NPRR1096(a) – Require Sustained Four-Hour Capability for Non-Spin portion
  NPRR1097 – Create Resource Forced Outage Report
  SCR812 – Create Intermittent Renewable Generation Integration Report
2022 December Release – Off-Cycle – 12/9/2022 Complete
  RIOO (“Create”, SODG, Load Resources functionality)
2023 February Release – R1 – 1/31/2023-2/2/2023 In Flight
  NPRR1020(a) – Allow Some Integrated Energy Storage Designs to Calculate Internal Loads
    EPS Metering portion
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2022 Release Targets – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February Various Dates | April 4/5 – 4/7 | May 5/24 – 5/26 | July 7/26 – 7/28 | October 10/4 – 10/6 | December 12/6 – 12/8
LPGRR068 NPRR1054(a) NPRR1005 NOGRR210 RRGRR025 NPRR917 NPRR1052 NPRR1065 NPRR1073 NPRR1016 PGRR082 NOGRR212 | None NPRR1092(a) | NPRR939 NPRR1093 NPRR1101 NPRR1113 NOGRR191 NOGRR198 NOGRR232 OBDRR032 OBDRR033 OBDRR035 SCR800 SCR809 SCR814 MarkeTrak User Interface Refresh | NPRR1108(a) NPRR935(b) NOGRR239 NPRR1129 NPRR1108(b) | None FFR Advancement (NPRR863 FFR) NPRR1120 OBDRR039 NPRR987(a) NPRR1002(a) NPRR1063 NPRR1142 | NPRR1084 NPRR1096(a) NPRR1097 SCR812 RIOO (“Create”, SODG, Load Resources)
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
ü
ü
ü
ü
Securitization Subchapter N March Go-Live
1/1
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
DGR/DESR
NPRR935(b) – New solar forecasts and reports
NPRR987(a) – ESR Contribution to PRC
NPRR1002(a) – Charging Restrictions in Emergency Conditions
NPRR1054(a) – Portion of gray box
NPRR1092(a) – RUC offer floor change
NPRR1096(a) – Non-Spin portion
TBD | NPRRs: 484,825(b),826,829,841,857,879,885,904,918,930,936,941,945,962,963,965,975,987,995,1004,1006,1007,1019,1023,1026,1030,1032,1034,1057, 1077,1090,1092(b),1105 SCRs: 799,805,807,810,813,816,818,819 PGRRs: 066,076,088,091,094,099 Other: OBDRR009,OBDRR017,RRGRR028
ü
ü
ü
ü
6/4 – 6/6
7/1
5/13
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
10/13
ü
ü
ü
7/15
ü
8/16
ü
12/1
ü
12/9
ü
ü
ü
ü
ü

## Slide 5: 2023 Release Targets – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 1/31 – 2/2 | March 3/28 – 3/30 | June 6/6 – 6/8 | July 7/25 – 7/27 | October 10/3 – 10/5 | December 12/5 – 12/7
NPRR1020(a) NPRR1040 SCR789 Ph2 | NPRR1040 | ECRS (NPRR863) NPRR1085 NPRR1096 | SCR807 SCR816 | SCR807 SCR816 EMS Upgrade | Securitization Phase 2A – Maine Invoice and Credit Exposure
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
EMS Upgrade Freeze
May 2023 – Jan. 2024
Closed Loop Testing – 9/18/2023-11/15/2023
NPRR1020(a) – EPS Metering portion
TBD | NPRRs: 484,825(b),826,829,841,857,879,885,904,918,930,936,941,945,962,963,965,975,987,995,1004,1006,1007,1019,1023,1026,1030,1032,1034,1057, 1077,1090,1092(b),1105 SCRs: 799,805,807,810,813,816,818,819 PGRRs: 066,076,088,091,094,099 Other: OBDRR009,OBDRR017,RRGRR028
E
E
E
NS
E
P
P
3/10
P
11/15
E
E
Coming in February | Additional context showing major ERCOT projects in-flight that are consuming critical resources

## Slide 6: Additional Project Status Information
Revision Request | Description | Project Phase | Additional Detail
NPRR1095 SCR817 SCR823 | Texas SET V5.0 Changes MarkeTrak Validation Revisions Aligning w/TX SET 5.0 ERCOT Mass System “County Name” File Updates | Planning | Expected completion in 2024
NPRR945 | Net Metering Requirements | Not Started | Reporting portion 2023 Q2 start candidate
NPRR962 | Publish Approved DC Tie Schedules | Not Started | Evaluating for a Q1 Q2 2023 start
NPRR1004 | Load Distribution Factor Process Update | Not Started | Mid-2023 start candidate
NPRR1006 | Update RT On-Line Reliability Deployment Price Adder Inputs to Match Actual Data | On Hold | Assessing restart date options
NPRR1090 | ERS Winter Storm Uri Lessons Learned Changes and Other ERS Items | Not Started | Evaluating for a 2023 start after ECRS
NPRR1092 | Limit RUC Opt-Out Provision | Not Started | Mid-2023 start candidate
NPRR1112 | Elimination of Unsecured Credit Limits | Not Started | Mid-2023 start candidate
NPRR1121 | Add a Posting Requirement to the Exceptional Fuel Cost Submission Process | Not Started | Early 2023 start candidate
NPRR1131 | Controllable Load Resource Participation in Non-Spin | Not Started | Assessing start date options 2023 candidate
NPRR1136 | Updates to Language Regarding a QSE Moving Ancillary Service Responsibility Between Resources | Not Started | Mid-2023 start candidate
Red Text: New additions and updates
Page 1 of 2

## Slide 7: Additional Project Status Information
Revision Request | Description | Project Phase | Additional Detail
NPRR1007 NPRR1014 | SCED Postings Gray-boxed in Section 3.2.5(4) Publication of Resource and Load Information | Not Started | Potential implementation of the gray box in this section, specifically the increasing of granularity for SCED disclosure reporting Evaluating for a Q2 2023 start
SCR819 NPRR1111 | Improving IRR Control to Manage GTC Stability Limits | Not Started | 2023 candidate
SCR820 | Operator Real-Time Messaging During Emergency | Not Started | Evaluating for a Q1 2023 start
PGRR066 | Interconnection Request Cancellation and Creation of Inactive Status | Not Started | 2023 start candidate for next bundle of RIOO enhancements
PGRR076 | Improvements to Generation Resource Interconnection or Change Request (GINR) Process | Not Started | 2023 start candidate for next bundle of RIOO enhancements
Red Text: New additions and updates
Page 2 of 2

## Slide 8: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR1149 | Implementation of Systematic Ancillary Service Failed Quantity Charges | 2023 | 3780 | $120k-$160k, 6-8 months Impacted Systems: S&B, MMS, Data Analytics
NPRR1153 | ERCOT Fee Schedule Changes | 2023 | 3790 | $20k-$30k, 3-5 months (Phase 2) Impacted Systems: RIOO, ERCOT.com See Comments in the IA for the breakdown of Phase 1 and Phase 2 of this NPRR
Options for…
PPL Rank Information
Next available 2023 Rank in Business Strategy = 3780
Next available Rank in Regulatory = 360

## Slide 9: ERCOT Technology Working Group (TWG)
Next TWG meeting will be in January or February 2023