## Sheet1
Joint TX SET / MCT Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 2022-12-07
Agenda Item: | Decision / Resolution | Action Items :
Meeting Notes November 16, 2022
| No changes were made to the notes. | The Texas SET Vice Chair will have the final version of the notes posted to the meeting date key documents page.
ERCOT Update
Flight Update | The ERCOT Flight Administrator clarified some language in the CBCI amd MBANK01 test scripts. | The ERCOT Flight Adminstrator will update the scripts in FlighTrak
Market Coordination Team (MCT)
Issues Log | No discussion was held on this topic.
Retail Market Guide Revision Request (RMGRR) | ERCOT reviewed updates that were needed to the transaction timing matrix in the Retail Market Guide (RMG) and in the 814_18 and 814_19 Implementation Guides. | A smaller group will colaborate to make other changes needed in the RMGRR such as the business case and description.
Nodal Protocol Revision Request (NPRR) | No additional changes were made to the NPRR at the meeting. ERCOT noted that the RMGRR and the NPRR need to be submitted by December 26 to be reviewed, approved and endorsed respectively at the Janaury 10 Retail Market Subcommittee (RMS) meeting; then if endorsed the NPRR needs to be submitted to the Market by Janaury 25 to have the language reviewed and possibly approved at the February Protocol Revision Subcommittee (PRS) meeting. | A smaller group colaborate to make other changes needed in the NPRR such as the business case and description.
Open Discussion | No other topics were discussed
Lubbock Power & Light (LP&L)
Open Discussion | Texas SET Leadership conducted a discussion regarding the number of Competitive Retailers(CRs) that have signed up to test in the Lubbock Flight. ERCOT stated that 13 CRs have signed up so far.
Texas SET Leadership conducted a discussion on the scripts and how they need to be modified to accommodate specific LP&L needs (e. g. 650_04 Disconnects for Non Pay, 814_PC/PD changes to billing methods, etc.).
Wrap Up Topics
Additional Items
Goals and Accomplishments | The Goals and Accomplishements will be discussed and developed at the Janaury meeting.
2023
Meeting Schedule | The TX SET Chair reviewed the meeting schedule to include TX SET, MCT, TDTMS, PWG and RMTTF in the decision for TX SET and MCT meetings. It was noted that MCT needs to be time specific so the appropriate Market Participants' personnel can be in attendance without having to attend the rest of the Texas SET meeting. It was also noted that a separate MCT meeting can be called if enough discussion topics warrant it. | The TX SET Chair will provide the schedule for all RMS Working Groups and Task Force at the Janaury meeting.
Leadership | 2023 Leadship will be determined at the January meeting.
Other Business
No "Other Business" topics were discussed.
Next Meeting-- WebEx Only | 2023-01-18
Attendees F-T-F
Attendees Webex
Bill Snyder AEP | Kathy Scott Centerpoint Energy
Catherine Meiners ERCOT | Krista PL&L
Connie Hermes NEC | Kyle Patrick NRG
Connie Laureano | Laura Green LP&L
Corrina G LP&L | Linda ?
Daily Smith LP&L | Mark Pepdjonovic ESG
Dave Michaelson ERCOT | Paul Yockey ERCOT
Deb Belin Earth Etch | Paul Williams ePsolutions
Debbie McKeever ONCOR | Paula Shadle NEC
Diana Rehfeldt TNMP | Sam Pak ONCOR
Jamie Wood LPL | Sheri Wiegand Vistra
Janie Duron Escalante Summer Electric | Stephen Wilson TXU Energy
Jeff Chen Centerpoint Energy | Steve Pliler Vistra
Jordon Troublefield ERCOT | Tyler Krueger BDE
Kathryn Thurman ERCOT | William Butler LPL