## Visual (ERCOT)
| 2022 | [25 empty] | 2023
| 2022-07-04 |  |  |  | 2022-08-01 |  |  |  |  | 2022-09-05 |  |  |  | 2022-10-03 |  |  |  |  | 2022-11-07 |  |  |  | 2022-12-05 |  |  |  | 2023-01-02 |  |  |  |  | 2023-02-06 |  |  |  | 2023-03-06 |  |  |  | 2023-04-03 |  |  |  | 2023-05-01 |  |  |  |  | 2023-06-05 |  |  |  | 2023-07-03 |  |  |  |  | 2023-08-07 |  |  |  | 2023-09-04 |  |  |  | 2023-10-02 |  |  |  |  | 2023-11-06 |  |  |  | 2023-12-04
 | time axis 2022-07-04 to 2023-12-25
PURA Ch. 40 Dual Billing/POLR | 2022-09-05: Rates Study; 2022-12-05: Draft; 2023-01-02: Pass to Delegation COMPLETE; 2023-02-06: Wait for Budget to pass; 2023-02-27: Budget is normally Passed; 2023-03-13: Legislative Process Committee--> House--> Senate -->Governor; 2023-04-03: Best Possible Case for Passing (needs Gov's signature immediately); 2023-04-17: Most bills passed in April; 2023-05-01: GOAL; 2023-05-08: If expected to NOT pass, add language to another bill.; 2023-05-29: END of Session; 2023-06-05: Govenor Normally Signs Bills; 2023-08-28: Bills become law - 9/1 (if not 2/3 approved)
Utilities Code 182 Customer Confidentiality for MOU | 2022-09-26: POLR / Default REP - RFP Receiving Submissions; 2022-12-05: Draft; 2023-01-02: Pass to Delegation COMPLETE
Market Transactions | 2022-07-04: Establish EDI Gateway; 2022-12-05: System Testing; 2023-03-13: Flight Testing; 2023-07-17: Customer Choice - Selection of REPs Start receiving MOVE-IN orders from REPs; 2023-09-11: Blackout Period No new market transactions; 2023-10-02: Transition ESI IDs to REPs on their billing cycle day
| System Configuration and Process Changes | [25 empty] | System Configuration | [11 empty] | Create ESI IDs |  | Send ESI/Load Profile to ERCOT (~90 days prior to Opt-in Date) If 182 bill has not passed, or contract w/ ERCOT, cannot send data to ERCOT |  | Create MCL and send to REPs |  | System Testing Integration Training | [17 empty] | Assign Customers to Default REPs
Market Rules | 2023-01-16: Draft Chapter 5 Customer Protection Rules Discretionary Fees; 2023-02-13: Market Feedback (RMS); 2023-03-06: Approval EUB - 3/21 CC - 3/28
Rates | 2023-01-02: Received Rates Structure; 2023-01-16: LP&L Internal Review (structure only); 2023-02-06: Market Feedback of Structure (RMS); 2023-03-06: Approval EUB - 3/21 CC - 3/28 Structure and Rates
pro forma | 2023-01-02: Comments Due 1/9; 2023-01-23: Response Due 1/23 SUBMITTED; 2023-02-06: PUC Staff Review Process; 2023-03-06: PUC approve; 2023-03-13: Present to EUB / CC
Transfer Remaining 30% of Customer Load Into ERCOT | 2022-07-04: Develop Switching Plan; 2022-09-05: Modelling; 2022-12-05: Contestation (Currently waiting to be put on PUC Open Meeting); 2023-01-02: Contestation; 2023-03-06: PUC Open Meeting Mar. 9th Settlement Approval; 2023-03-13: SPS Files with FERC; 2023-03-20: FERC Approves Load Transfer 60 Day Review Process; 2023-05-15: Texas AG Approval (10 days); 2023-05-29: Bond Process (~30 days); 2023-06-26: Bond Issue; 2023-07-03: Pay SPS; 2023-07-10: Payment Due - 7/15 (If load transfer completes after 6/1)
Motion for Rehearing (25 day process)
[27 empty] | Construction | [19 empty] | Transfer Load to ERCOT Can begin after FERC Approves