## Slide 1
Market Readiness Update for
ERCOT Contingency Reserve Service (ECRS)
Matt Mereness
Sr. Director Market Operations and Implementation
DSWG
February 13, 2023

## Slide 2: Market Readiness Progression for ECRS
  ECRS Interface changes reviewed at Sept 29, 2022 TWG meeting:
    https://www.ercot.com/calendar/09292022-TWG-Meeting-by-Webex
      EIP External Interfaces Specification ECRS.doc ERCOT Common Types ECRS.xsd
      ERCOT Transaction Types ECRS .xsd ECRS ICCP telemetry handbook update.doc (new ICCP points)
  February 2023
    Continue TWG updates (next meeting Feb 16, 2023)
    Begin regular TAC updates
  April 2023
    Project/Business review workshop (April TBD)
    ECRS in MOTE (April 13, 2023)
    Begin Weekly Market Readiness WebEx meetings (April TBD)
    Scorecards for QSE testing progress (late April TBD)
      QSE AS Self-Arrangement, AS Trades, AS Offers, COP
  June 6-8, 2023 Go-Live (first OD with ECRS likely to be June 10, 2023)