## Sheet1
Joint TX SET / MCT Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 2023-01-18
Agenda Item: | Decision / Resolution | Action Items :
Elections
ERCOT conducted the 2023 Leadership Elections for Chair and Vice Chair | Chair--Kyle Patrick NRG Vice Chair-- Diana Rehfeldt TNMP
Meeting Notes December 7, 2022
| No changes were made to the notes. | The Texas SET Vice Chair will have the final version of the notes posted to the meeting date key documents page.
ERCOT Update
Flight Update | ERCOT Staff presented the Flights 0203 and 0423LP&L
ERCOT -- Mass Transition Testing | ERCOT stated that they are working with their Legal Department and the Commission to determine if the Market is comfortable enough to refrain from testing Mass Transition. ERCOT also stated that they should have an official answer by the next Texas SET meeting.
Change Control Call 10 AM | ERCOT conducted the change control Call
TXSETCC840: Update the 814_18 and 814_19 Guides to be in line with Texas SET 5.0 Changes. | Texas SET agreed to make a recommendation to The Retail Market Subcommittee (RMS) to approve this to be included in Texas SET V5.0.
TXSETCC841: Update the Implementation Guides to support options available to MOU/EC for retail transactions. | Texas SET agreed to make a recommendation to RMS to approve as urgent to be included with Texas SET V4.0A
In Review Change Control to be discussed
TXSETCC838: Update the 814_19 to add the ASI02 of (001) Change and additional reject codes | ERCOT reviewed the Change Control and made changes where needed. Texas SET agreed to make a recommendation to The Retail Market Subcommittee (RMS) to approve this to be included in Texas SET V5.0.
Market Coordination Team (MCT)
Flight / Go Live Date Discussion | The group agreed to develop a timeline proposal for Version 5.0 to be tested at the end of 2024; then present this proposal to RMS. The RMS Vice Chair requested that selling points be added to the proposal. | Leadership will work with ERCOT to develop a proposal for the end of 2024.
Review Requirements Document | ERCOT conducted a review of the document and made changes where needed. | ERCOT will post the updated version to the meeting page.
RMGRR | ERCOT conducted a review of the document and made changes where needed. Leadership will update the Business Case to show that the changes are clean up for V5.0. The group suggested to use some of the language from NPRR1095 and RMGRR169 to prevent re-inventing the wheel. | Leadership will complete the upper section of the Revision Request; then submit the RMGRR to the Revision Request listserv for a number and present the document for approval at RMS.
NPRR | ERCOT conducted a review of the document and made changes where needed. Leadership will update the Business Case to show that the changes are clean up for V5.0. The group suggested to use some of the language from NPRR1095 and RMGRR169 to prevent re-inventing the wheel. | Leadership will complete the upper section of the Revision Request; then request a review and possible endorsement at the next RMS meeting; if approved/endorsed; the Revision Request will be submitted to the Revision Request listserv for a number, review and approval at the next Protocol Revision Subcommittee (PRS) meeting.
Open Discussion
Goals and Accomplishments
The review and creation of 2023 Goals and 2022 Accomplishments is delayed until the February meeting.
Wrap Up Topics
Other Business
RMS update | Elections resulted in Debbie Mckeever as Chair and John Schatz as Vice Chair. Update on Retail Market
Next Meeting-- WebEx Only | 2023-02-15
Attendees F-T-F
Attendees Webex
Brittney Albracht ERCOT | Kyle Patrick NRG
Cassandra Jenkins Centerpoint Energy | Laura Green LP&L
Catherine Meiners ERCOT | Leo Castillo ERCOT
Connie Hermes NEC | Linda ?
Daily Smith LP&L | Mark Pepdjonovic ESG
Dave Michaelson ERCOT | Melinda Earnest AEP
Deb Belin Earth Etch | Monica Jones Centerpoint Energy
Diana Rehfeldt TNMP | Olivia Ryan ?
Eric Lotter - GridMonitor | Pam Shaw LP&L
Frank Nunes Vertex One | Paul Yockey ERCOT
Jeff Chen Centerpoint Energy | Paula Shadle NEC
Jesse Macias AEP | Ross Delahoussaye ?
Jim Lee Centerpoint Energy | Sam Pak ONCOR
John Schatz Vistra | Sheri Wiegand Vistra
Kathryn Thurman ERCOT | Stephen Wilson TXU Energy
Kathy Scott Centerpoint Energy | Tracie Gaetano Accent Energy
Katy LP&L | Tyler Krueger BDE
Kim Wall Hansen Technologies