## Slide 1
Market Readiness Update for
ERCOT Contingency Reserve Service (ECRS)
Matt Mereness
Sr. Director Market Operations and Implementation
TWG
February 16, 2023

## Slide 2: Market Readiness Progression for ECRS
  ECRS Interface changes reviewed at Sept 29, 2022 TWG meeting
  February-March 2023
    Regular TAC updates for awareness of implementation
    Continue TWG updates
  April-May 2023
    Project/Business detailed workshop
    ECRS in MOTE 4/20/2023
    Begin Weekly Market Readiness WebEx meetings
    Scorecards for QSE testing and qualification progress
  June 6-8, 2023 Go-Live (first ECRS OD likely to be June 10, 2023)

## Slide 3: Market Readiness Progression for ECRS
  Key References:
    ECRS Interface changes:
      https://www.ercot.com/calendar/09292022-TWG-Meeting-by-Webex
      EIP External Interfaces Specification ECRS.doc ERCOT Common Types ECRS.xsd (UPDATED Feb 2023)
      ERCOT Transaction Types ECRS .xsd ECRS ICCP telemetry handbook update.doc (new ICCP points)
      Update made to ensure backward compatibility:
        added OFFEC to the ASType element and then made OFFNS and OFFEC optional under OfflineNonSpin
    ECRS Operations and Business explanation
      WMWG Meeting July 26, 2022
      https://www.ercot.com/files/docs/2022/07/26/Preliminary_ECRS_Deployment_Procedure_v0_JulyWMWG.pptx
  In development:
    Workshop materials for early April
    Weekly Market Readiness WebEx meetings (late April TBD)
      Qualification process for existing Resources to qualify for ECRS
      Data Cutover plan (not as significant as FFRA)
      Scorecards for QSE testing progress (late April TBD):
      QSE AS Self-Arrangement, AS Trades, AS Offers, COP
  June 6-8, 2023 Go-Live (first OD with ECRS likely to be June 10, 2023)

## Slide 4: Market Readiness Progression for ECRS
  FAQ
    When will MOTE be available (4/20/2023)
    Will MOTE send notifications of receipt (ack/nack)
    Will MOTE publish ECRS awards? (No, but will post sample file in coming weeks)
    Will ERCOT provide Mock settlement statement and extracts (No)
  Qualification principles being internally discussed to enable a robust ECRS fleet “qualified and ready” for ECRS participation on the first Operating Day.
    ERCOT will be requesting from QSEs which Resources plan to qualify for ECRS
    Recognition of constraints to testing all Resources
      Not enough time to schedule tests for every Resource.
      Some types of testing may not be available until after cut-over (eg AS Manager)
    Qualification consideration may include:
      Leveraging existing qualification and consider provisional qualification for transitional purposes.
      Considering open-loop telemetry tests to qualify a Resource.
      Considering if one Resource successfully qualifies, allow provisional qualification for remainder of fleet with similar capabilities or other AS qualification.
    ANY QUESTIONS?