## Sheet1
| 2022 |  |  | 2023 | [11 empty] | 2024
Activities | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
TRANSITION TO COMPETITION
Develop high level customer transition plan | 2022 Dec: Complete
Finalize Access Agreement (Delivery Service Agreement) | bar: 2022 Oct to 2022 Dec
Develop customer enrollment process
Finalize customer billing options
Determine if the City of Lubbock has D2D registration requirements
Create Mass Customer Lists / Resolve customer data Issue | bar: 2023 Apr to 2023 Jun
Create CBCI files for Default REPs | bar: 2023 Jul to 2023 Sep
Finalize Default REP selection process | 2023 Feb: Complete
Define Disconnect for Non-Pay (DNP) Blackout Period | bar: 2023 Jul to 2023 Sep
CUSTOMER EDUCATION
Identify tax exempt customers (REPs to do this once enrolled) | 2022 Dec: Complete
Determine Continuous Service Agreement process
Populate Power to Choose website | bar: 2023 Apr to 2023 Jun
Conduct customer forums/town halls | bar: 2023 Apr to 2023 Sep
PUCT REQUIREMENTS
Determine if Solix Low Income list applies | 2022 Dec: Complete
Finalize Tariff | bar: 2022 Oct to 2022 Dec
Finalize POLR process/POLRs | 2023 Feb: Complete
Define PUCT complaint process
Finalize the application of LP&L Customer Protection Rules
ERCOT MARKET REQUIREMENTS
Identify if MarkeTrak will be used | 2022 Dec: Complete
Identify if LSE files will be used | 2022 Dec: Complete
Determine what Load Zone/Congestion Zone/Weather Zones apply | 2022 Dec: Complete
Idenitfy transactions – Membership ID | 2022 Dec: Complete
Implement substation mapping - station name begins with LP_ | 2022 Dec: Complete
Finalize flight testing plan
Define Safety Net process | bar: 2022 Oct to 2022 Dec
Determine load profiles for ESI IDs
Identify applicable SAC04 Codes
Revise RMG Chapter 8 and Protocols (CSA/Mass Tran) (Sections 7, 19) | bar: 2023 Apr to 2023 Jun
Conduct bank testing | bar: 2023 Apr to 2023 Jun
Input ESI IDs in TDSP Extract | bar: 2023 Apr to 2023 Jun
Conduct flight testing - TEST | bar: 2023 Apr to 2023 Sep
Deploy TXSET v5.0 | bar: 2024 Apr to 2024 Jun
TDSP-SPECIFIC ACTIVITIES
Identify LP&L DUNS | 2022 Dec: Complete
Post zip code list | 2022 Dec: Complete
Post meter read calendar | 2022 Oct: Complete
Post holiday calendar | 2022 Oct: Complete
Determine if AMS Operational Days will apply | 2023 Feb: Complete
Critical Care/Critical Load communications pre&post transition
Define Distribution Loss Factors
Identify Solar/DG customers
Determine where daily Switch Hold files will be housed (SFTP site)
Identify Metering / True IDR (BUSIDDRQ) types | 2023 Feb: Complete
Establish call center support line / phone number | 2023 Feb: Complete
Determine if OGFLT profiles will be available | 2023 Feb: Complete
Define weather moratorium process (Customer Protection)
Define transaction timelines - Ch 5
Define TXSET transaction timing
Develop TDSP Proration Guidelines
Create and share testing contact information and update FlighTrak
Create TDSP AMS Data Practices table | bar: 2023 Apr to 2023 Jun
Determine Historical usage request process & availability | bar: 2023 Apr to 2023 Jun
Determine if LP&L REP Portal will be created | bar: 2023 Jul to 2023 Sep
Determine process for housing tampering Information | bar: 2023 Jul to 2023 Sep
Finalize Smart Meter Texas agreement | bar: 2023 Jul to 2023 Sep
LP&L RATES
Determine if power factor adjustments will apply
Identify street lighting / security lighting practices
Determine if demand ratchet billing will apply
Determine if 4CP assignment will be used
Finalize rate structure
Review Tariff was finalized
Determine if transition charges will apply
Create timeline and complete registration of REPs