## Sheet1
Joint TX SET / MCT Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 2023-02-15
Agenda Item: | Decision / Resolution | Action Items :
Meeting Notes January 18 , 2023
Texas SET attendees approved the January 18 meeting notes. |  | The Texas SET Vice Chair will have the notes posted to the January meeting page key documents.
ERCOT Update
Flight Update 0223 | ERCOT Staff presented the Update
Lubbock Power & Light (LPL) LPL0423 | ERCOT Staff presented the Update. The Texas SET Chair and some of the attendees conducted a discussion on how many CRs will test with Lubbock.
2024 Testing Schedule Review--Includes Texas SET Version 5.0 in last flight | ERCOT reviewed the schedule discussed at the Subteam meeting after the last Texas SET meeting. | The 2024 schedule will be presented at the March RMS meeting for approval.
Change Control Call 10 AM | ERCOT conducted the change control Call
TXSETCC842: Update the gray box for the 814_04 and 814_25 for the I2M - Invalid Second Move Out. | Texas SET agreed to send the change control to RMS for approval for Texas SET Version 5.0 | ERCOT will present the Change Control at the next RMS meeting and request approval.
TXSETCC817: Update the 650_04 Guide as a result of the market recommendations following Hurricane Harvey. | Texas SET agreed to send the change control to RMS for approval for Texas SET Version 5.0 | ERCOT will present the Change Control at the next RMS meeting and request approval.
TXSETCC821: Add necessary data elements to transactions to allow the submission of County to be communicated. | Texas SET agreed to send the change control to RMS for approval for Texas SET Version 5.0 | ERCOT will present the Change Control at the next RMS meeting and request approval.
TXSETCC840: Update the 814_18 and 814_19 Guides to be in line with Texas SET 5.0 Changes. – Requesting to add a gray box to both DTM segments | Texas SET agreed to send the change control to RMS for approval for Texas SET Version 5.0 | ERCOT will present the Change Control at the next RMS meeting and request approval.
Market Coordination Team (MCT) Version 5.0
Flight / Go Live Date Discussion | Since the 3rd flight of 2024 is going to be used for Texas SET 5.0, the GoLive conversion is proposed for the 2nd weekend in November 8th through the 10th. November 15th through 17th will be used as a contingent GoLive time period. | The 2024 schedule will be presented at the March RMS meeting for approval.
Review Requirements Document | ERCOT reviewed the Requirements Document and made changes where needed.
Testing Matrix | ERCOT reviewed the testing matrix and made updates where needed. ERCOT also added Example needed and Swimlane needed columns; then asked that Texas SET devlop the scripts for all the changes from Version 5.0 no later than May 2023. | MCT Meeting attendees will work on the Examples and Swimlanes at the March meeting.
Goals and Accomplishments
2022 Accomplishments | Discussion will be held at the next meeting.
2023 Goals | Discussion will be held at the next meeting.
Lubbock Light & Power (LL&P)
Test Scripts | ERCOT began a review of the test scripts and will continue to review at a subsequent meeting.
Who will test and when? | The Texas SET Chair conducted a discussion on how to determine who will test end-to-end with Lubbock. It was suggested that Lubbock make that determination. All the other CRs will only test scripts for connectivity and the penny test. The GoLive date will have to be determined after all the legislative approvals are made. All the CRs will have to complete the post testing paperwork to be able to send transations in production. The question of which kind of billing will be used (IOU vs Dual) was discussed. It was determined that there are more items being discussed and decided outside of ERCOT Working Groups and Task Forces prior to determining the type of billing that will be used. The group determined that a workshop should be held to discuss requirments coming out of the Legislature and PUCT at a later date.
Transactions Matrix | This will be discussed at a future meeting.
SAC04 Codes | This will be discussed at a future meeting.
Other Business
No "Other Business" topics were discussed.
Next Meeting-- WebEx Only | 2023-03-22
Attendees F-T-F
Attendees Webex
Amy Sue Stirland LP&L | Kathy Scott Centerpoint Energy
Bill Snyder AEP | Kyle Patrick NRG
Carole Root AEP | Laura Green LP&L
Cindy Juarez AEP CRR | Leo Castillo ERCOT
Daily Smith LP&L | Olivia Ryan Kraken Tech
Dave Michaelson ERCOT | Mark Hunt AEP
Deb Belin Earth Etch | Monica Jones Centerpoint Energy
Dee Lowerre NRG | Naomi M Serrata AEP
Diana Rehfeldt TNMP | Olivia Ryan Kraken Tech
Eric Lotter - GridMonitor | Paul Yockey ERCOT
Frank Nunes Vertex One | Sam Pak ONCOR
Jeff Chen Centerpoint Energy | Sheri Wiegand Vistra
Jesse Macias AEP | Stephen Wilson Vistra
John Schatz Vistra | Steve Pliler Vistra
Jordan Troublefield ERCOT | Tiffany Kraken Tech
Kathryn Thurman ERCOT | Tyler Krueger BDE