## Sheet1
Version Date: 3-31-2023
| 2022 |  |  | 2023 | [11 empty] | 2024
Activities | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
TRANSITION TO COMPETITION
Develop high level customer transition plan | 2022 Dec: Complete
Finalize Access Agreement (Delivery Service Agreement) | 2023 Mar: Complete
Develop customer enrollment process | bar: 2023 Jan to 2023 Mar
Finalize customer billing options | bar: 2023 Jan to 2023 Mar
Determine if the City of Lubbock has D2D registration requirements | bar: 2023 Jan to 2023 Mar
Create Mass Customer Lists / Resolve customer data Issue | bar: 2023 Apr to 2023 Jun
Create CBCI files for Default REPs | bar: 2023 Jul to 2023 Sep
Finalize Default REP selection process | 2023 Feb: Complete
Define Disconnect for Non-Pay (DNP) Blackout Period | bar: 2023 Jul to 2023 Sep
CUSTOMER EDUCATION
Identify tax exempt customers (REPs to do this once enrolled) | 2022 Dec: Complete
Determine Continuous Service Agreement process | bar: 2023 Jan to 2023 Mar
Populate Power to Choose website | bar: 2023 Apr to 2023 Jun
Conduct customer forums/town halls | bar: 2023 Apr to 2023 Sep
PUCT REQUIREMENTS
Determine if Solix Low Income list applies | 2022 Dec: Complete
Finalize Tariff | 2023 Mar: Complete
Finalize POLR process/POLRs | 2023 Feb: Complete
Define PUCT complaint process | bar: 2023 Jan to 2023 Mar
Finalize the application of LP&L Customer Protection Rules | bar: 2023 Jan to 2023 Mar
ERCOT MARKET REQUIREMENTS
Identify if MarkeTrak will be used | 2022 Dec: Complete
Identify if LSE files will be used | 2022 Dec: Complete
Determine what Load Zone/Congestion Zone/Weather Zones apply | 2022 Dec: Complete
Idenitfy transactions – Membership ID | 2022 Dec: Complete
Implement substation mapping - station name begins with LP_ | 2022 Dec: Complete
Finalize flight testing plan | 2023 Mar: Complete
Define Safety Net process | bar: 2022 Oct to 2022 Dec
Determine load profiles for ESI IDs | bar: 2023 Jan to 2023 Mar
Identify applicable SAC04 Codes | bar: 2023 Jan to 2023 Mar
Revise RMG Chapter 8 and Protocols (CSA/Mass Tran) (Sections 7, 19) | bar: 2023 Apr to 2023 Jun
Conduct bank testing | bar: 2023 Apr to 2023 Jun
Input ESI IDs in TDSP Extract | bar: 2023 Apr to 2023 Jun
Conduct flight testing - TEST | bar: 2023 Apr to 2023 Sep
Deploy TXSET v5.0 | bar: 2024 Apr to 2024 Jun
TDSP-SPECIFIC ACTIVITIES
Identify LP&L DUNS | 2022 Dec: Complete
Post zip code list | 2022 Dec: Complete
Post meter read calendar | 2022 Oct: Complete
Post holiday calendar | 2022 Oct: Complete
Determine if AMS Operational Days will apply | 2023 Feb: Complete
Critical Care/Critical Load communications pre&post transition | bar: 2023 Jan to 2023 Mar
Define Distribution Loss Factors | bar: 2023 Jan to 2023 Mar
Identify Solar/DG customers | bar: 2023 Jan to 2023 Mar
Determine where daily Switch Hold files will be housed (SFTP site) | bar: 2023 Jan to 2023 Mar
Identify Metering / True IDR (BUSIDDRQ) types | 2023 Feb: Complete
Establish call center support line / phone number | 2023 Feb: Complete
Determine if OGFLT profiles will be available | 2023 Feb: Complete
Define weather moratorium process (Customer Protection) | bar: 2023 Jan to 2023 Mar
Define transaction timelines - Ch 5 | bar: 2023 Jan to 2023 Mar
Define TXSET transaction timing | bar: 2023 Jan to 2023 Mar
Develop TDSP Proration Guidelines | 2023 Feb: Complete
Create and share testing contact information and update FlighTrak | 2023 Mar: Complete
Create TDSP AMS Data Practices table | bar: 2023 Apr to 2023 Jun
Determine Historical usage request process & availability | bar: 2023 Apr to 2023 Jun
Determine if LP&L REP Portal will be created | bar: 2023 Jul to 2023 Sep
Determine process for housing tampering Information | bar: 2023 Jul to 2023 Sep
Finalize Smart Meter Texas agreement | bar: 2023 Jul to 2023 Sep
LP&L RATES
Determine if power factor adjustments will apply | bar: 2023 Jan to 2023 Mar
Identify street lighting / security lighting practices | bar: 2023 Jan to 2023 Mar
Determine if demand ratchet billing will apply | 2023 Mar: Complete
Determine if 4CP assignment will be used | 2023 Mar: Complete
Finalize rate structure | bar: 2023 Jan to 2023 Mar
Determine if transition charges will apply | 2023 Mar: Complete
Create timeline and complete registration of REPs | bar: 2023 Jan to 2023 Mar