## Law Effective June 1
| 2022 | [25 empty] | 2023
V 2023-03-31 | 2022-07-04 |  |  |  | 2022-08-01 |  |  |  |  | 2022-09-05 |  |  |  | 2022-10-03 |  |  |  |  | 2022-11-07 |  |  |  | 2022-12-05 |  |  |  | 2023-01-02 |  |  |  |  | 2023-02-06 |  |  |  | 2023-03-06 |  |  |  | 2023-04-03 |  |  |  | 2023-05-01 |  |  |  |  | 2023-06-05 |  |  |  | 2023-07-03 |  |  |  |  | 2023-08-07 |  |  |  | 2023-09-04 |  |  |  | 2023-10-02 |  |  |  |  | 2023-11-06 |  |  |  | 2023-12-04
 | time axis 2022-07-04 to 2023-12-25
PURA Ch. 40 Dual Billing/POLR | 2022-09-05: Rates Study; 2022-12-05: Draft; 2023-01-02: Pass to Delegation COMPLETE; 2023-02-06: FILED 2/22 HB 2663; 2023-02-27: Budget is normally Passed Don't expect to see progress until budget passes; 2023-03-13: Voted favorably out of committee. Awaiting 1st reading on House Floor.; 2023-04-03: Most bills passed in April; 2023-05-01: GOAL; 2023-05-08: If expected to NOT pass, add language to another bill.; 2023-05-29: END; 2023-06-05: Govenor Normally Signs Bills; 2023-06-19: If 182 Fails to pass 2/3 AND absent a clear designation of ERCOT, we work on a alternative with ERCOT. Else, we cannot move to competition.; 2023-08-28: Bills become law - 9/1 (if not 2/3 approved)
[32 empty] | FILED 2/23 SB 1170 |  |  |  |  | Bus. & Commerce 1st Read 3/9
Utilities Code 182 Customer Confidentiality for MOU | 2022-09-26: POLR / Default REP - RFP Receiving Submissions; 2022-12-05: Draft; 2023-01-02: Pass to Delegation COMPLETE; 2023-02-06: FILED 2/22 HB 2664; 2023-03-13: Voted favorably out of committee. Awaiting 1st reading on House Floor.
[32 empty] | FILED 2/23 SB 1171 |  |  |  |  | Bus. & Commerce 1st Read 3/9
Market Transactions | 2022-07-04: Establish EDI Gateway; 2022-12-05: System Testing; 2023-03-13: Flight Testing March 8 - June 23; 2023-06-26: MUST Send ESI/Load Profile to ERCOT or Customer Choice cannot happen CURRENTLY DUE 6/3: Protocol requires 120 days prior to Opt-in Date of 10/1 Protocol Revision to allow 60 days, then DUE 8/2.; 2023-07-31: Customer Choice - Selection of REPs Aug 2 - Sep 11 Start receiving MOVE-IN orders from REPs ERCOT cannot receive Move-In Transactions greater than 90 day ahead of the move in.; 2023-09-11: Blackout Period Sep 11 - 29 No new market transactions; 2023-10-02: Customers "Move In" to their chosen REP Transition ESI IDs to REPs on their billing cycle day
| System Configuration and Process Changes | [25 empty] | System Configuration | [13 empty] | Create ESI IDs |  | Create MCL and send to REPs |  | REP Welcome Package | [17 empty] | Assign Customers to Default REPs
Chapter 5 | 2023-01-16: Draft Chapter 5 Customer Protection Rules Discretionary Fees; 2023-04-03: Approval EUB - 4/18 CC - 4/25; 2023-06-19: Deadline to file Access Tariff with PUC 7/2
Rates | 2023-01-02: Received Rates Structure; 2023-03-06: Published to Listserv on 3/17 Comments due 3/24; 2023-03-27: To EUB 4/10 City Council 4/11 for approval
pro forma | 2023-01-02: Comments Due 1/9 Complete; 2023-01-23: Response Due 1/23 Complete; 2023-02-06: PUC Staff Review Process Complete; 2023-03-06: PUC Approval Complete Effective May 1st; 2023-04-24: Pro forma Effective May 1st
Transfer Remaining 30% of Customer Load Into ERCOT | 2022-07-04: Develop Switching Plan; 2022-09-05: Modelling; 2022-12-05: Contestation (Currently waiting to be put on PUC Open Meeting); 2023-01-02: Contestation; 2023-01-30: PUC Review; 2023-02-20: PUC Open Meeting Mar. 9th Settlement Approval COMPLETE
[34 empty] | COMPLETE SPS Filed with FERC 2/21 Start 60 day timeline |  | FERC Approves Load Transfer 60 Day Review Process 2/21 - 4/22 | [6 empty] | Texas AG Approves Bond Issuance |  | Bond Process (~30 days) |  |  |  | Bond Issue
[27 empty] | Construction | [19 empty] | Transfer Load to ERCOT On or around June 1st
All Customers must be in ERCOT prior to Retail Competition
60 Days (Aug 2)

## Math
Date we start transitioning customers to REPs | 2023-10-01
Date ERCOT needs data by protocol: 60 days prior | 2023-08-02
Date ERCOT needs data by protocol: 120 days prior | 2023-06-03
Date we start transitioning customers to REPS | 2023-10-01
Date ERCOT needs data w/protocol revision: 60 days prior | 2023-08-02
Last date we transition customers to REPs | 2023-10-31
Earliest we can receive Move-In Transactions: 90 days prior | 2023-08-02
If UC182 passes, but not 2/3 . . . | 2023-09-01
Soonest we can start transition customers (90 days) | 2023-10-31
Soonest we can start transition customers (120 days) | 2023-12-30
SPS Filed with FERC | 2023-02-21
60 day FERC Process | 2023-04-22
Customer Choice Window Opens | 2023-08-02
MCL Due to REPs | 2023-06-03
FERC approves load transfer | 2023-04-23
TX AG Bond Process (10 days) | 2023-05-03