## Slide 1
Project Update
April 13, 2023
Troy Anderson
ERCOT Portfolio Management

## Slide 2
  Recent / Upcoming Project Highlights
  2023 Release Targets
  Additional Project Status Information
  Priority/Rank Options for Revision Requests with Impacts
    None
  Technology Working Group (TWG)
    Next meeting scheduled for 4/27/2023
Location of Revision Request Project Information: http://www.ercot.com/services/projects
Project Update Agenda

## Slide 3: Recent / Upcoming Project Highlights
2023 June Release – R3 – 6/6/2023-6/8/2023 In Flight
  NPRR863 – Creation of ERCOT Contingency Reserve Service (ECRS) and Revisions to Responsive Reserve
  NPRR1085 – Ensuring Continuous Validity of PRC and Dispatch through Timely Changes to Resource Telemetry and COPs
  NPRR1096(b) – Require Sustained Two-Hour Capability for ECRS
  NPRR1148 – Language Cleanup Related to ERCOT Contingency Reserve Service (ECRS)
  OBDRR043 – Related to NPRR1148, Language Cleanup Related to ECRS
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2023 Release Targets – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 1/31 – 2/2 | March 3/28 – 3/30 | June 6/6 – 6/8 | July 7/25 – 7/27 | October 10/3 – 10/5 | December 12/5 – 12/7
NPRR1020(a) |  | ECRS (NPRR863) NPRR1085 NPRR1096(b) NPRR1148 OBDRR043 | SCR789 Ph2 | NPRR945 NPRR962 NPRR1040 NPRR1090 NPRR1112 NPRR1121 NPRR1154 SCR807 SCR816 | Securitization Phase 2A – Maine Invoice and Credit Exposure NPRR1092(b) EMS Upgrade
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
EMS Upgrade Freeze – May 2023 – Jan. 2024
NPRR1020(a) – EPS Metering portion
NPRR1092(b) – Limit RUC Opt-Out Provision
NPRR1096(b) – ECRS portion
TBD | NPRRs: 484,825(b),826,829,841,857,879,885,904,918,930,936,941,963,965,975,987,995,1004,1006,1007,1019,1023,1026,1030,1032,1034,1057, 1077,1105, 1111,1128,1131,1136 SCRs: 799,805,810,813,818,819,822 PGRRs: 066,076,088,091,094,099 Other: OBDRR009,OBDRR017,RRGRR028
E
E
E
E
E
E
NS
NS
E
NS
NS
NS
I
E
E
P
NS
11/15
July
E

## Slide 5: Additional Project Status Information
Revision Request | Description | Project Phase | Additional Detail
NPRR1095 SCR817 SCR823 | Texas SET V5.0 Changes MarkeTrak Validation Revisions Aligning w/TX SET 5.0 ERCOT Mass System “County Name” File Updates | Execution | Expected completion in late 2024
NPRR962 | Publish Approved DC Tie Schedules | Not Started | Approved to start in May 2023
NPRR1004 | Load Distribution Factor Process Update | Not Started | Mid-2023 start candidate
NPRR1006 | Update RT On-Line Reliability Deployment Price Adder Inputs to Match Actual Data | On Hold | Assessing restart date options
NPRR1092 | Limit RUC Opt-Out Provision | Not Started | Approved to start in June/July 2023
NPRR1128 | Allow FFR Procurement up to FFR Limit Without Proration | Not Started | Assessing start date options 2023 candidate
NPRR1131 | Controllable Load Resource Participation in Non-Spin | Not Started | Assessing start date options 2023 candidate
NPRR1136 | Updates to Language Regarding a QSE Moving Ancillary Service Responsibility Between Resources | Not Started | Mid-2023 start candidate
SCR819 NPRR1111 | Improving IRR Control to Manage GTC Stability Limits | Not Started | 2023 candidate
SCR820 | Operator Real-Time Messaging During Emergency | Initiation | Project to start in April 2023 – Go-Live target is TBD
SCR822 | Create Daily Energy Storage Integration Report and Dashboard | Not Started | Evaluating 2023 project start
Red Text: New additions and updates
Page 1 of 2

## Slide 6: Additional Project Status Information
Revision Request | Description | Project Phase | Additional Detail
NPRR1007 NPRR1014 | SCED Postings Gray-boxed in Section 3.2.5(4) Publication of Resource and Load Information | Not Started | Potential implementation of the gray box in this section, specifically the increasing of granularity for SCED disclosure reporting Evaluating a 2023 start
NPRR1164 RRGRR033 | Black Start and Isochronous Control Capable Identification | Not Started | Q2 2023 start candidate for next bundle of RIOO enhancements Still in stakeholder process
RRGRR032 | Related to NPRR1132, Communicate Operating Limitations during Cold and Hot Weather Conditions | Not Started | Q2 2023 start candidate for next bundle of RIOO enhancements
NPRR1153 | ERCOT Fee Schedule Changes | Not Started | Q2 2023 start candidate for next bundle of RIOO enhancements
PGRR103 | Establish Time Limit for Generator Commissioning Following Approval to Synchronize | Not Started | Q2 2023 start candidate for next bundle of RIOO enhancements Still in stakeholder process
Red Text: New additions and updates
Page 2 of 2

## Slide 7: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR1156 | Priority Revision Request Process | N/A | N/A | <$10k O&M, 1-2 weeks Impacted Systems: ERCOT.com No project required
Options for…
PPL Rank Information
Next available 2023 Rank in Business Strategy = 3800
Next available Rank in Regulatory = 360

## Slide 8: Technology Working Group (TWG)
TWG meeting to be held on 4/27/2023