## Sheet1
Market Coordination Meeting (MCT) Meeting Notes / Action Items
MCT Notes / Action Items 09:30 | 2023-03-22
Agenda Item: | Decision / Resolution | Action Items :
Meeting Notes February 15, 2023
See Texas SET Notes from February. MCT and Texas SET were combined.
Deep Dive into new Rejects
ERCOT conducted a discussion on the list of questions. | Answers were given as a result of the discussion. | ERCOT will rename the document to Q & A; added notes to the questions; then will post to the MCT main page.
Review 5.0 Requirements Needing Flight Testing
ERCOT conducted a discussion on updates made to Market Testing requirements. | Scripts will be discussed at the Texas SET meeting.
Identify Examples and Swimlane Updates
ERCOT conducted a discussion on the examples and swimlanes needed for the Texas SET V5.0 upgrade | List of examples
| Inadvertent Gain | ERCOT will create
| Addition of the County Elements to the N4 of the N1=8R Customer address loop. | ERCOT will create
| Addition of the Metered Service Type Segment using M01 House code | ERCOT will create
| CSA | ERCOT will create
| 810_02 26 code for other debits and credits | Centerpoint will create
List of swimlanes
| Inadvertent Gain | ERCOT will create
| CSA | NRG will work with ERCOT to create an additional swimlane using the start and stop dates.
Other Business
No other business was discussed.
Next Meeting-- WebEx Only | 2023-04-19
Attendees F-T-F
Attendees Webex
Ashley B LP&L | Kathy Scott Centerpoint Energy
Bill Snyder AEP | Kim Wall Hansen Technologies
Carole Root AEP | Kyle Patrick NRG
Carolyn Reed Centerpoint Energy | Laura Gomez LP&L
Cassandra Jenkins Centerpoint Energy | Paul Yockey ERCOT
Catherine Meiners ERCOT | Paula Shadle NEC
Daily Smith LP&L | Sam Pak ONCOR
Deb Belin Earth Etch | Sheri Wiegand Vistra
Debra Foster ? | Stephen Wilson Vistra
Diana Rehfeldt TNMP | Toni Bean Centerpoint Energy
Eric Lotter - GridMonitor | Tyler Krueger BDE
Jesse Macias AEP | Viviana Valdez LP&L
Jordan Troublefield ERCOT
Karen Malkey Centerpoint Energy
Kathryn Thurman ERCOT