## Slide 1
Weekly Market Readiness for
ERCOT Contingency Reserve Service (ECRS)
ERCOT staff
April 25, 2023

## Slide 2: Agenda
Key Milestones
Key supporting documentation
Qualification next steps
Communication
Questions

## Slide 3: Milestones for ECRS Implementation
  ECRS Technical Specs- Sept 29, 2022 TWG meeting
  Market Readiness and Qualification Workshop (Monday April 3, 2023)
  Friday April 14, 2023- Deadline for Deadline for QSE Declaration of Resources
  TELEMETRY/ICCP is most important next step (target end of week 4/28)
  Thursday, April 20, 2023- MOTE deployed for QSEs to test
  Tuesday, April 23, 2023- Begin Weekly Market Readiness WebEx meetings
    Scorecards for QSE testing and qualification progress (tbd)
  June 6-8, 2023 Go-Live (first ECRS OD planned for June 10, 2023)

## Slide 4: Market Readiness for ECRS
  Key References (in April 13, 2023 Market Notice):
    ECRS Interface changes: https://www.ercot.com/calendar/09292022-TWG-Meeting-by-Webex
    ECRS Operations and Business explanation
      April 3, 2023 Workshop will be latest revisions- link to meeting
    Sample XML Questions
      XML Sample ECRS Deployment
      03/29/2023 09.03.09 AM QTEST CM-ASM-NOTF AS_TYPE: ECRS, RES_NAME: LD_TEST, DEPLOY_MW: 5.0, BEGIN_TIME: 2023-03-29 09:03:09, END_TIME: 2023-03-29 10:00:00, DURATION: 56.85 mins, ID: 365;
      XML Sample ECRS DAM Award (to be provided in next 2 weeks)
    Updated AS Methodology supporting deployment details
      Note that ERCOT has developed and incorporated the ECRS deployment procedure into the updated AS Methodology documentation on the ERCOT website (ercot.com | Market Information | Day-Ahead Market | Methodology for Determining Minimum Ancillary Service Requirements).
    Scorecards will begin publishing on May 9, 2023 (for activities of May 1-8)
      AS Offer submissions will be scored on ability to submit a single AS Offer into MOTE.
      COP submissions will be scored on ability to submit a single COP into MOTE.
      AS Self-Arrangement submissions will be scored on ability to submit an AS Self- Arrangement into MOTE.
      (see attached population of QSEs)
  Note to TWG yesterday
    EIP specifications document has been updated here https://www.ercot.com/files/docs/2022/05/03/EIP-External-Interfaces-Specification-v1.25.zip
    Sample DAM AS Awards place on April 3, 2023 Workshop link to meeting

## Slide 5: Qualification and Telemetry for ECRS
ERCOT is proceeding through Qualification Requests on a first-in-first-out basis
  Telemetry should be requested by end of week (4/28)
  However, if telemetry not requested and ready, ERCOT will move to next QSE
ERCOT’s ICCP handbook has been updated to include the various telemetry changes that are being put in place to support implementation of ECRS.
Follow normal processes for requesting new ICCP Service Request.
Additional support from ercoticcpsupport@ercot.com

## Slide 6: Communication
Please send all communication through ERCOT Client Services to ensure it is assigned and addressed (ClientServices@ercot.com.).
  MOTE questions will go to IT group
  Qualification questions for Gen-side will go to Operations
  Qualification questions for Load resource will go to Demand-side
  Details of ECRS will go to Operations and/or MarketDesign teams

## Slide 7: Questions
Any Questions?
You can also contact Matt.Mereness@ercot.com