## Sheet1
TX SET Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 2023-04-19
Agenda Item: | Decision / Resolution | Action Items :
Meeting Notes March 22, 2023
No changes were made to the notes |  | The Texas SET vice-Chair will have the notes posted to the March meeting key documents.
Retail Market Subcommittee (RMS) Update
RMS approved or endorsed everything presented for a vote.
ERCOT Updates
Change Control Call 13:30
TXSETCC843: To provide better clarification for the use of reject code SOP the reject name and gray box will be updated | The meeting attendees agreed to hold this until the May meeting then send the change to RMS for approval as a non-emergency for Texas SET V5.0 at the RMS June meeting. These changes will also be added to the redline for the 814_09. ERCOT will review this change for impacts and return with feedback.
TXSETCC844: Remove Reject Reason Code I2M-Invalid Second Move Out | The meeting attendees agreed to hold this change until the May meeting's Change Control Call in order to allow ERCOT time to evaluate any impacts. ERCOT will return with impacts at the next meeting. The earliest this will go to RMS will be the RMS June meeting.
LPL0423 Flight Testing
Market Coordination Team (MCT) Update
ERCOT provided a brief summary of the meeting highlights earlier in the day.
ERCOT reminded the group that the redline review covers transactions 814_01 through 814_ 19 with the exception of the 814_04 and the 814_09 that will be held until the change controls 843 and 844 are vetted through the Market Stakeholder process.
5.0 Test Scripts
ERCOT reviewed the changes made to the scripts. No other changes were made. |  | ERCOT will add the appropriate CON scripts to the smaller notebook; then post to the MCT page. The changed scripts will be incorporate into the script workbook posted on the testing information page under the Texas SET website.
Lubbock Light & Power (LL&P)
Texas SET 814 Implementation Guides -- Redline Review | Texas SET requests that meeting attendees revivew and bring feedback to the May meeting.
ERCOT provided information about new rounds of changes for Retail Market Guide Revision Request (RMGRR) 174 and Nodal Protocol Revision Request (NPRR)1173 that need to be approved in time to make the October go live timeframe for LP&L. | ERCOT reviwed the changes in the NPRR and stated there may be more changes coming depending on questions that will be answered later.
Other Business
ERCOT provided an a Projects update related to the changes to the Retail Application Programming Interphase (API) process. | ERCOT Web Service (EWS) system changes will be included with the changes implemented during the December Release.
Next Meeting-- WebEx Only | 2023-05-17
Attendees F-T-F
Attendees Webex
Bill Snyder AEP | Kathy Scott Centerpoint Energy
Carole Root AEP | Kim Wall Hansen Technologies
Carolyn Reed Centerpoint Energy | Kyle Patrick NRG
Catherine Meiners ERCOT | Laura Gomez LP&L
Cindy Duong Just Energy | Linda Summer Electric
Connie Hermes / South Texas Electric Cooperative (STEC) | Mark Pepdjonovic ESG
Daily Smith LP&L | Monical Jones Centerpoint
Darrell Miller ESG | Olivia Ryan Kraken Tech
Deb Belin Earth Etch | Pam Shaw Principle Staff
Debra AEP | Paul Yockey ERCOT
Diana Rehfeldt TNMP | Paula Shadle NEC
Eric Lotter - GridMonitor | Sam Pak ONCOR
Frank Nunes Vertex One | Sheri Wiegand Vistra
Jeff Chen Centerpoint Energy | Stephen Wilson Vistra
John Schatz TXU Energy | Stev Pliler Vistra
Jordan Troublefield ERCOT | Tyler Krueger BDE
Kathryn Thurman ERCOT