|  |  |  |  |
| --- | --- | --- | --- |
| NPRR Number | [1067](http://www.ercot.com/mktrules/issues/nprr1067) | NPRR Title | Market Entry Qualifications, Continued Participation Requirements, and Credit Risk Assessment |
| Impact Analysis Date | | August 4, 2021 | |
| Estimated Cost/Budgetary Impact | | Between $400k and $600k  Annual Recurring Operations and Maintenance (O&M) Budget Cost: $150k – $180k  See ERCOT Staffing Impacts | |
| Estimated Time Requirements | | Market entry qualifications and continued participation requirements could be implemented 90 days after Public Utility Commission of Texas (PUCT) approval of the Nodal Protocol Revision Request (NPRR).  Non-system changes for the credit risk assessment portion of this NPRR could be implemented 90 days after Public Utility Commission of Texas (PUCT) approval of the NPRR and clarifying accompanying OBDRR.  The timeline for implementing changes to the Credit Monitoring and Management (CMM) System is dependent upon Public Utility Commission of Texas (PUCT) prioritization and approval. Please see the Project Priority List (PPL) for additional information.  Estimated project duration:   22 to 32 months  Passport Schedule Risk Assessment:   Significant Risk to Passport schedule; therefore, ERCOT proposes implementation of system changes as a post-Passport project. | |
| ERCOT Staffing Impacts (across all areas) | | Implementation Labor: 100% ERCOT; 0% Vendor  There will be ongoing operational impacts to the following ERCOT department totaling 2.25 Full-Time Employee (FTEs) to support this NPRR:  • General Counsel (2.00 FTE Effort) • Market Credit (0.25 FTE Effort)  ERCOT has assessed its ability to absorb the ongoing efforts of this NPRR with current staff and concluded the need for one additional FTE in the Legal Department:  \* 2500 hours to review new Qualified Scheduling Entity (QSE) and Congestion Revenue Right Account Holder (CRRAH) applications and perform initial and ongoing reviews of existing QSEs and CRRAHs.   There are additional operational impacts in the first year after implementation that can be absorbed with budgeted staff. | |
| ERCOT Computer System Impacts | | The following ERCOT systems would be impacted:  Credit Monitoring and Management (CMM) 100% | |
| ERCOT Business Function Impacts | | ERCOT will update its business processes to implement this NPRR. | |
| Grid Operations & Practices Impacts | | No impacts to ERCOT grid operations and practices. | |

|  |
| --- |
| Evaluation of Interim Solutions or Alternatives for a More Efficient Implementation |
| None. |

|  |
| --- |
| Comments |
| None. |