## Slide 1
Weekly Market Readiness for
ERCOT Contingency Reserve Service (ECRS)
ERCOT staff
May 9, 2023

## Slide 2: Agenda
Key Milestones
Key supporting documentation
Qualification next steps
Communication
Questions

## Slide 3: Milestones for ECRS Implementation
  ECRS Technical Specs- Sept 29, 2022 TWG meeting
  Market Readiness and Qualification Workshop (Monday April 3, 2023)
  Friday April 14, 2023- Deadline for Deadline for QSE Declaration of Resources
  Thursday, April 20, 2023- MOTE deployed for QSEs to test
  Tuesday, April 23, 2023- Begin Weekly Market Readiness WebEx meetings
  Current activity
    For ECRS QSE qualification, TELEMETRY/ICCP is most important next step
    For all QSEs, scorecards begin for current MOTE activity
  June 6-8, 2023 Go-Live (first ECRS OD planned for June 10, 2023)

## Slide 4: Market Readiness for ECRS
  Key References (in April 13, 2023 Market Notice):
    ECRS Interface changes: https://www.ercot.com/calendar/09292022-TWG-Meeting-by-Webex
    ECRS Operations and Business explanation
      April 3, 2023 Workshop will be latest revisions- link to meeting
    Technical updates:
      Sample XML Questions
        XML Sample ECRS Deployment
          03/29/2023 09.03.09 AM QTEST CM-ASM-NOTF AS_TYPE: ECRS, RES_NAME: LD_TEST, DEPLOY_MW: 5.0, BEGIN_TIME: 2023-03-29 09:03:09, END_TIME: 2023-03-29 10:00:00, DURATION: 56.85 mins, ID: 365;
        XML Sample ECRS DAM Award
          Sample DAM AS Awards place on April 3, 2023 Workshop link to meeting
        EIP specifications document has been updated here https://www.ercot.com/files/docs/2022/05/03/EIP-External-Interfaces-Specification-v1.25.zip
        Extract MODE/CODE details in Market Notice Friday May 5, 2023 (posted with mtg materials)
    Updated AS Methodology supporting deployment details
      Incorporated the ECRS deployment procedure into the updated AS Methodology documentation on the ERCOT website (ercot.com | Market Information | Day-Ahead Market | Methodology for Determining Minimum AS Reqt).
    Scorecards will begin publishing on May 9, 2023 (for activities of May 1-8)
      AS Offer submissions will be scored on ability to submit a single AS Offer into MOTE.
      COP submissions will be scored on ability to submit a single COP into MOTE.
      AS Self-Arrangement submissions will be scored on ability to submit an AS Self- Arrangement into MOTE.
      (see attached population of QSEs)

## Slide 5: Scorecard Details
Important note, MOTE submissions should be OpDay + 2 days to avoid Credit errors in MOTE
Scorecards on follow slides

## Slide 6: Scorecard AS Offers

## Slide 7: Scorecard COP part 1

## Slide 8: COP part 2

## Slide 9: Scorecard AS Self- Arrangement

## Slide 10: Qualification and Telemetry for ECRS
ERCOT’s ICCP handbook was updated to include the various telemetry changes that are being put in place to support implementation of ECRS.
ERCOT is proceeding through Qualification Requests on a first-in-first-out basis
  Telemetry should have been requested by end of week (4/28), but if not then sooner is better.
  If telemetry is not requested and ready, ERCOT will move to next QSE
Follow normal processes for requesting new ICCP Service Request.
Additional support from ercoticcpsupport@ercot.com

## Slide 11: Communication
Please send all communication through ERCOT Client Services to ensure it is assigned and addressed (ClientServices@ercot.com).
  MOTE questions will go to IT group
  Qualification questions for Gen-side will go to Operations
  Qualification questions for Load resource will go to Demand-side
  Details of ECRS will go to Operations and/or MarketDesign teams

## Slide 12: Wrap-up and Questions
Wrap-Up:
  For ECRS QSE qualification, Telemetry/ICCP is most important next step
  For all QSEs, scorecards continue for current MOTE activity this week
    May 15 to be reported at next meeting
    Cumulative, one-and-done scoring on this, not a weekly activity
  Market cutover discussion next week
Open to any and all questions?
You can also contact Matt.Mereness@ercot.com