## Slide 1
Weekly Market Readiness for
ERCOT Contingency Reserve Service (ECRS)
Matt Mereness and other ERCOT staff
May 23, 2023

## Slide 2: Agenda
Key Milestones
Key supporting documentation
Qualification next steps
Communication and Cutover
Questions

## Slide 3: Milestones for ECRS Implementation
  ECRS Technical Specs- Sept 29, 2022 TWG meeting
  Market Readiness and Qualification Workshop (Monday April 3, 2023)
  Friday April 14, 2023- Deadline for Deadline for QSE Declaration of Resources
  Thursday, April 20, 2023- MOTE deployed for QSEs to test
  Tuesday, April 23, 2023- Begin Weekly Market Readiness WebEx meetings
  Current activity
    ECRS QSE qualification in-flight
    For all QSEs, MOTE scorecards in-flight
  June 6-8, 2023 Go-Live (first ECRS OD planned for June 10, 2023)

## Slide 4: Supporting Documentation for ECRS
  Key References (in April 13, 2023 Market Notice):
    ECRS Interface changes: https://www.ercot.com/calendar/09292022-TWG-Meeting-by-Webex
    ECRS Operations and Business explanation
      April 3, 2023 Workshop will be latest revisions- link to meeting
    Technical updates:
      Sample XML Questions
        XML Sample ECRS Deployment
          03/29/2023 09.03.09 AM QTEST CM-ASM-NOTF AS_TYPE: ECRS, RES_NAME: LD_TEST, DEPLOY_MW: 5.0, BEGIN_TIME: 2023-03-29 09:03:09, END_TIME: 2023-03-29 10:00:00, DURATION: 56.85 mins, ID: 365;
        XML Sample ECRS DAM Award
          Sample DAM AS Awards place on April 3, 2023 Workshop link to meeting
        EIP specifications document has been updated here https://www.ercot.com/files/docs/2022/05/03/EIP-External-Interfaces-Specification-v1.25.zip
        Extract MODE/CODE details in Market Notice Friday May 5, 2023
    Updated AS Methodology supporting deployment details
      Incorporated the ECRS deployment procedure into the updated AS Methodology documentation on the ERCOT website (ercot.com | Market Information | Day-Ahead Market | Methodology for Determining Minimum AS Reqt).
    Scorecards will begin publishing on May 9, 2023 (for activities of May 1-8)
      AS Offer submissions will be scored on ability to submit a single AS Offer into MOTE.
      COP submissions will be scored on ability to submit a single COP into MOTE.
      AS Self-Arrangement submissions will be scored on ability to submit an AS Self- Arrangement into MOTE.
      (see attached population of QSEs)

## Slide 5: Scorecard Details
Important note, MOTE submissions should be OpDay + 2 days to avoid Credit errors in MOTE
Scorecards on the following slides…

## Slide 6: Scorecard AS Offers

## Slide 7: Scorecard COP part 1

## Slide 8: COP part 2

## Slide 9: Scorecard AS Self- Arrangement

## Slide 10: Qualification and Telemetry for ECRS
ERCOT’s ICCP handbook was updated to include the various telemetry changes that are being put in place to support implementation of ECRS.
ERCOT is proceeding through Qualification Requests on a first-in-first-out basis
  Telemetry should have been requested by end of week (4/28), but if not then sooner is better.
  If telemetry is not requested and ready, ERCOT will move to next QSE
Follow normal processes for requesting new ICCP Service Request.
Additional support from ercoticcpsupport@ercot.com

## Slide 11: Groupings for RRS and ECRS explanation
Details of Grouping were in April 3 Workshop, but a couple of highlights:
  Groups assignments for Resources only carrying RRS will continue to follow the Day-Ahead group assignments.
  Those Resources with no group assignment and only carrying RRS will continue to be deployed with Group 2.
  For Resources providing ECRS, the Day Ahead group assignment is not used, and groupings will be generated in real-time (based on telemetry).
  QSEs carrying ECRS must deploy NCLRs based on the XML instruction (also true of RRS).
  The column GroupNo will be a Lower-case String, instead of a Number.
    Sample Values: 0, 1a, 1b, 1c, 2, 3, 4

## Slide 12: Communication and Cutover
Please send all communication through ERCOT Client Services to ensure it is assigned and addressed (ClientServices@ercot.com).
  MOTE questions will go to IT group
  Qualification questions for Gen-side will go to Operations
  Qualification questions for Load resource will go to Demand-side
  Details of ECRS will go to Operations and/or MarketDesign teams

## Slide 13: Communication and Cutover
June 8, 2023
  System upgrade will occur the afternoon of June 8th between 3:30-4:00pm
  MPs do not need to take any immediate action following the upgrade.
  After the upgrade ECRS system functionality will be available for OD June 10, 2023
    Note that COP, AS Trades, AS Offers, Self-Arranged AS must only be submitted for OD June 10 or later (not systematically enforced)
June 9, 2023
  Starting at 12:01am Telemetry for On-Hold status can be used (NPRR1085)
  Day-Ahead Market activities include ECRS:
    AS Plan published for DAM OD June 10 will include ECRS values for DAM consideration
    QSEs submit AS Self Arrangements and AS Offers into DAM
    DAM Awards for OD June 10 will include ECRS Awards and should be reflected in COP for OD June 10 for DRUC run.
  After DAM, QSE submits COP updates OD June 10 to include ECRS
June 10, 2023
  First Operating Day with ECRS
  Starting at 12:01am, telemetry should include ECRS values

## Slide 14: Wrap-up and Questions
Questions from last week:
  None
Wrap-Up:
  For ECRS QSE qualification in-flight
  For all QSEs, scorecards continue for current MOTE activity this week
    May 30 to be reported at next meeting
    Cumulative, one-and-done scoring on this, not a weekly activity
  Continue Market cutover discussions
Open to any and all questions?
You can also contact Matt.Mereness@ercot.com