## Overview
Last Updated: 5-19-22 1820
This issues list is meant to include high level descriptions of key issues related to large flexible loads (LFL). Further detail will be fleshed out via discussion at the Large Flexible Load Task Force (LFLTF).
The "policy" category is meant to denote policy issues beyond ERCOT's authority under state law.

## LFLTF Issues List
Category | Issue ID | Merged/ Related Issues | Issue Description | Date Issue was Added | Status | Documents addressing this issue | Owner | Email Address | 23-Jan | 17-Feb | 20-Mar | 12-Apr | Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Allowed Statuses
Interconnection | LFL-1 | LFL-2, LFL-3, LFL-49 | Develop a process for ERCOT tracking and reporting operational and planned large load interconnections. | 2022-04-14 | Addressed in RR Drafts | PGRR | Bill Blevins | Bill.blevins@ercot.com | D | [10 empty] | Awaiting Action from Owner(s)
Interconnection | LFL-3 | LFL-1 | Establish responsible entities for interconnection process oversight, modeling and "ownership/operatorship" of large flexible loads (LFL) in various configurations (stand-alone, co-located with generation, interconnecting TSP as different entity from certificated DSP, etc.). Incorporate any new requirements for the NOMCR process/telemetry requirements | 2022-04-14 | Merged with Another Issue | PGRR, RGRR, ICCP Handbook Revision | AEP, LCRA,TNMP | bagross@aep.com; Bill.Blevins@ercot.com; Andy.Nguyen@LCRA.ORG, | D | [10 empty] | Being Actively Worked
Interconnection | LFL-2 | LFL-48 | Establish requirements for an ERCOT-facilitated large load interconnection process, including size and interconnection timeline thresholds for applicability to Loads. | 2022-04-14 | Merged with Another Issue | PGRR | Oncor, AEP,LCRA, Bill B. | martha.henson@oncor.com; bagross@aep.com; Bill.Blevins@ercot.com; Andy.Nguyen@LCRA.ORG | D | [10 empty] | Evaluated - No Action Needed
Interconnection | LFL-4 |  | Define LFL | 2022-05-17 | Addressed in RR Drafts | NPRR | Floyd, Bob W, Eric G, ONCOR, John Ritch, Bob King | eric@ERICWINTERSGOFF.COM, martha.henson@oncor.com, ebmystic@gmail.com, john.ritch@gexaenergy.com, rking@goodcompanyassociates.com | D | [10 empty] | Addressed in RR Drafts
Interconnection | LFL-5 |  | Define Interruptible Load vs Firm Load | 2022-05-17 | Addressed in RR Drafts | NPRR | Bob W, Ken R. , ONCOR | bob@longhornpwr.com, kenneth.ragsdale@ercot.com, martha.henson@oncor.com | D | [10 empty] | Merged with Another Issue
Interconnection | LFL-6 |  | Long term threshold for LFL | 2022-05-17 | Addressed in RR Drafts | NPRR, PGRR | LCRA, Oncor | Andy.Nguyen@LCRA.ORG, martha.henson@oncor.com | D | [10 empty] | Addressed in CLR Nodal Settlement NPRR
Interconnection / Operations / Planning | LFL-7 |  | Determine how to incorporate LFLs into GTC/GTL study processes. | 2022-04-14 | Addressed in RR Drafts | NPRR, PGRR | Fred H., AEP | shun-hsien.huang@ercot.com , bagross@aep.com
Markets | LFL-8 | LFL-24 | Evaluate telemetry, metering, COP, and other market submission requirements for LFLs a) Any corresponding Business Practice Manual updates | 2022-05-17 | Addressed in RR Drafts | NPRR | Ian Haley | ian.haley@vistracorp.com
Markets | LFL-11 |  | Evaluate the need for rules prohibiting the switching between CLR and non-CLR participation and/or nodal and Load Zone settlement CLR portion addressed in Sai's NPRR, NCLR portion to be included in RRs | 2022-05-17 | Addressed in RR Drafts | NPRR-CLR, PGRR | Eric Goff,Shams S | eric@ERICWINTERSGOFF.COM shams@crescentpower.net
Markets | LFL-12 | LFL-15 | Determine the suitability of new large retail loads to become Controllable Load Resources directed by following basepoints from SCED. a. Propose any required probations for switching between nodal settlement and Load Zone settlement of an individual facility. b. Propose any probations between switching between becoming a Controllable Load Resource and reverting back to only a passively responding load or then back to a CLR. c. Determine required energy and power metering requirements to prohibit arbitrage between node and load zone pricing. d. Determine facility inspection requirements if necessary. | 2022-04-14 | Addressed in RR Drafts | NPRR-CLR, NPRR, PGRR | Dave Maggio Sai Moorty | david.maggio@ercot.com; Sainath.Moorty@ercot.com
Markets | LFL-13 |  | Identify any needs for metering requirements, specifically as it related to nodal vs. Load Zone settlement | 2022-05-17 | Addressed in CLR Nodal Settlement NPRR | NPRR-CLR | Dave Maggio Sai Moorty | david.maggio@ercot.com; Sainath.Moorty@ercot.com
Markets | LFL-14 | LFL-20 | Evaluate the need for any mitigating measure needs to price oscillations or other related concerns due to fast LFL responses | 2022-05-17 | Addressed in RR Drafts | NPRR | Floyd Trefny | ebmystic@gmail.com
Markets | LFL-15 | LFL-21 | Determine if or how LFLs, specifically those modeled as CLRs, should be considered in constraint competitiveness test and Resource mitigation processes | 2022-05-17 | Being Actively Worked |  | Dave Maggio Sai Moorty | david.maggio@ercot.com; Sainath.Moorty@ercot.com
Markets | LFL-18 |  | Evaluate the need for changes in the treatment/modeling of LFLs in the DAM | 2022-05-17 | Addressed in CLR Nodal Settlement NPRR | NPRR-CLR | Eric Goff Sai Moorty | eric@ERICWINTERSGOFF.COM
Markets | LFL-19 |  | If LFLs not required to be CLRs/dispatched by SCED, identify other potential process or tools for deployment of the LFLs | 2022-05-17 | Addressed in RR Drafts | NPRR | Eric Goff Jeff Billo Dave Maggio Sai Moorty | eric@ERICWINTERSGOFF.COM jeff.billo@ercot.com, david.maggio@ercot.com, sai.moorty@ercot.com
Markets | LFL-20 | LFL-14 | Consider the need for any changes to market rules to prevent price oscillations from LFL fast response and demand fluctuations. | 2022-04-14 | Merged with Another Issue |  | Dave Maggio Clayton Greer | Clayton.Greer@morganstanley.com david.maggio@ercot.com
Markets | LFL-21 | LFL-15 | Evaluate what considerations LFLs, particularly those modeled as CLRs, should given in constraint competitiveness and Resource mitigation processes. | 2022-04-14 | Merged with Another Issue |  | Dave Maggio Clayton Greer | Clayton.Greer@morganstanley.com david.maggio@ercot.com
Markets / Operations | LFL-23 | LFL-10 LFL-17 | Consider rules for Ancillary Service awards for large flexible loads (co-located or otherwise). AS awards where BTM LFL and Resources are awarded Evaluate processes for AS and other Resource awards for LFLs, specifically BTM LFLs |  | Addressed in CLR Nodal Settlement NPRR | NPRR-CLR | Clayton Greer, Caitlyn Smith, Jeff Billo,Sai M. Dave Maggio, Spencer Stanton, John Ritch | Clayton.Greer@morganstanley.com, caitlyn.smith@jupiterpower.io, jeff.billo@ercot.com, sai.moorty@ercot.com, david.maggio@ercot.com, spencer.stanton@XXX.com, john.ritch@nextera.com
Markets / Operations | LFL-24 | LFL-8 | Establish telemetry, metering, and other market participant submission (e.g., COP) requirements for LFLs (co-located or otherwise). | 2022-04-14 | Merged with Another Issue | NPRR-CLR | Bill Blevins Dave Maggio Don Blackburn Jim Gant, TNMP | bill.blevins@ercot.com, david.maggio@ercot.com dblackburn@huntenergynetwork.com, jgant@prioritypower.com
Markets / Operations | LFL-25 |  | For LFL that are co-located, identify any changes required within Business Practice Manuals, specifically as it relates to COP submissions and telemetry. | 2022-04-14 | Evaluated - No Action Needed |  | Bill Blevins Dave Maggio Don Blackburn Jim Gant, TNMP | bill.blevins@ercot.com, dblackburn@huntenergynetwork.com; david.maggio@ercot.com jgant@prioritypower.com
Markets / Operations | LFL-26 | LFL-51 | Evaluate rules and process changes that may be necessary for considering LFLs, particularly those modeled as CLRs, in near-term reliability studies, including the Reliability Unit Commitment (RUC) process. | 2022-04-14 | Being Actively Worked |  | Eric Goff Dave Maggio | eric@ERICWINTERSGOFF.COM; david.maggio@ercot.com
Markets / Operations | LFL-28 | LFL-27 | Consider whether LFL-CLR availability for SCED dispatch should be required in all hours. | 2022-04-14 | Addressed in CLR Nodal Settlement NPRR | NPRR-CLR | Greg Thurner, Eric Goff, Floyd T. | greg.thurnher@mp2energy.com; eric@ERICWINTERSGOFF.COM; ebmystic@gmail.com
Markets / Operations | LFL-29 | LFL-56 | Investigate the pros and cons of bit coin mining facilities becoming Controllable Load Resources versus remaining loads that only passively respond to SCED pricing. | 2022-04-14 | Addressed in RR Drafts | NPRR, PGRR | Dave Maggio | david.maggio@ercot.com
Markets / Policy | LFL-30 |  | To the degree LFLs are not a Resource dispatched by SCED or could possibly be considered dispatchable in some way, identify policy issues to refer to the PUCT to affect a rule change that would allow, as an option, nodal settlements of the load and evaluate any downstream impacts or additional changes required if nodal settlement is required or offered. | 2022-04-14 | Evaluated - No Action Needed |  | Dave Maggio | david.maggio@ercot.com
Operations | LFL-31 |  | Consider impacts to Transmission Operator UFLS obligations. | 2022-04-14 | Being Actively Worked | Proposal at May 31 LFLTF | Blake Gross Clayton Greer | bagross@aep.com
Operations | LFL-32 |  | Identify technical requirements for ramp-rate limitations. | 2022-04-14 | Addressed in RR Drafts | NPRR | Clayton Greer Jeff Billo | Clayton.Greer@morganstanley.com, jeff.billo@ercot.com
Operations | LFL-33 |  | Consider the impacts of and need for rules related to self-limiting RAS/CMPs. | 2022-04-14 | Being Actively Worked |  | Eric Goff | eric@ERICWINTERSGOFF.COM
Operations | LFL-34 |  | Consider the requirements for CLR/”Interruptible Load” to be excluded from a TDSPs' EEA3 Firm Load Shed obligations. | 2022-04-14 | Addressed in RR Drafts | NOGRR | Martha Henson | martha.henson@oncor.com | D
Operations | LFL-35 |  | Consider what changes to outage coordination processes are needed to incorporate LFL, including load assumptions for outage coordination studies. | 2022-04-14 | Being Actively Worked |  | Perrin Wall Fred Huang | perrin.wall@CENTERPOINTENERGY.COM
Operations | LFL-36 |  | Determine if and how LFL should be taken into account in the AS methodology, including any site-specific maximum limit. | 2022-04-14 | Evaluated - No Action Needed |  | Dave Maggio | david.maggio@ercot.com
Operations | LFL-37 |  | Consider forecasting impacts of LFL co-locating with Generation Resources. | 2022-04-14 | Merged with Another Issue |  | Eric Goff Jeff Billo | eric@ERICWINTERSGOFF.COM
Operations | LFL-38 |  | To the degree certain LFLs are excluded from UFLS and/or firm load shed obligations, identify any processes necessary for curtailing/deploying those loads. | 2022-04-14 | Addressed in RR Drafts | NPRR, NOGRR | Blake Gross Martha Henson | bagross@aep.com martha.henson@oncor.com
Operations | LFL-39 |  | Consider changes to EEA3 load shed allocation, including re-evaluation of load share calculations and counting behind-the-meter load reductions towards load shed obligations. | 2022-04-14 | Addressed in RR Drafts | NOGRR | Martha Henson | martha.henson@oncor.com | D
Operations | LFL-40 |  | LFL Shed prior to/during EEA | 2022-05-17 | Addressed in RR Drafts | NPRR | Jeff Billo Stephen Solis | jeff.billo@ercot.com; stephen.solis@ercot.com | D
Markets | LFL-9 | LFL-16, LFL-22 | Should SCED be run more frequently after LR deployment | 2022-05-17 | Merged with Another Issue
Markets | LFL-16 | LFL-9, LFL-22 | Study the value of lost load and price diversity of response across different LFLs. Should SCED be run more frequently to address increased response and fluctuations from LFLs Consider adjust energy settlement from current 15-minute process and weighting | 2022-05-17 | Merged with Another Issue
Markets / Operations | LFL-22 | LFL-9, LFL-16 | Using historical data, determine the “value of lost load” for individual facilities reactions to SCED pricing without disclosing the name of the facilities. Determine the variability and price diversity among facilities. By using any diversity in the “value of lost load” between facilities, determine if a faster execution of SCED following a deployment of a Load Resource should be implemented including adjusting the energy settlement from the current 15-minute interval. Can any diversity be used to minimize the effect of load responses on ERCOT system frequency? | 2022-04-14 | Merged with Another Issue
Operations | LFL-41 | LFL-9 LFL-16 LFL-22 | Consider adjusting energy settlement from current 15-minute process and weighting | 2022-05-17 | Being Actively Worked | Discussion at May 31 LFLTF | Clayton Greer, Dave Maggio, Steve, Floyd T, Blake King | clayton.greer@morganstanley.com, david.maggio@ercot.com, Steve@Texasblockchaincouncil.org ebmystic@gmail.com blake.r.king@gmail.com
Operations | LFL-42 |  | Evaluate processes for AS and other Resource awards for LFLs, specifically BTM LFLs | 2022-05-17 | Evaluated - No Action Needed |  | Sai Moorty | sai.moorty@ercot.com
Operations | LFL-43 |  | CLR/Interruptible Load on firm load shed obligations: BTM Load treatment | 2022-05-17 | Addressed in RR Drafts | NOGRR | Martha Henson | martha.henson@oncor.com
Operations | LFL-44 |  | CLR/Interruptible Load on firm load shed obligations: TSP LFL treatment | 2022-05-17 | Addressed in RR Drafts | NOGRR | Martha Henson | martha.henson@oncor.com
Operations / Planning | LFL-45 | LFL-37 | Identify impacts to load forecasting and consider what process changes are necessary to incorporate LFL. | 2022-04-14 | Addressed in RR Drafts | NPRR | Eric Goff Jeff Billo | eric@ERICWINTERSGOFF.COM
Operations / Planning | LFL-46 |  | Consider impact of large flexible loads tripping in light-load conditions. | 2022-04-14 | Addressed in RR Drafts | NOGRR, discussion at May 31 LFLTF | Jeff Billo | jeff.billo@ercot.com
Operations / Planning | LFL-47 |  | Consider voltage control / voltage stability impacts of LFL interval behavior. | 2022-04-14 | Evaluated - No Action Needed |  | Freddy Garcia | freddy.garcia@ercot.com
Planning | LFL-48 | LFL-2 | Determine appropriate milestones for incorporating large loads into planning cases. | 2022-04-14 | Merged with Another Issue | PGRR | CNP, AEP, LCRA, ONCOR, Chris H., TNMP (Tony Hudson) | perrin.wall@CENTERPOINTENERGY.COM, Martha.henson@oncor.com, bagross@aep.com, andy.nguyen@lcra.org, tony.hudson@tnmp.com, CHemschot@tnsk.com | D
Planning | LFL-49 |  | Consider how co-located or Stand-alone LFLs and Resources should be considered in resource adequacy reports, including if they should be classified as Private Use Networks in ERCOT reports. | 2022-04-14 | Addressed in RR Drafts | NPRR | Evan Neel, AEP, Eric Goff, ONCOR | evan.neel@ercot.com, eric@ERICWINTERSGOFF.COM, martha.henson@oncor.com
Planning | LFL-50 |  | RMR considerations for LFL (need to include planning) | 2022-05-17 | Addressed in RR Drafts | PGRR | TBD (Bill B)
Planning | LFL-51 | LFL-26 | Evaluate rules and process changes that may be necessary for considering LFLs, particularly those modeled as CLRs/SCED dispatchable, in near-term reliability studies, including the Reliability Unit Commitment (RUC) process. | 2022-05-17 | Merged with Another Issue |  | Eric Goff, Jeff Billo, Dave M, | eric@ERICWINTERSGOFF.COM jeff.billo@ercot.com, david.maggio@ercot.com
Planning / Policy | LFL-52 |  | Consider whether or not LFLs should be considered "firm load" for the purposes of transmission planning. | 2022-04-14 | Addressed in RR Drafts | PGRR | Eric Goff, ONCOR, AEP, CNP, TNMP, LCRA | eric@ERICWINTERSGOFF.COM, martha.henson@oncor.com, bagross@aep.com, perrin.wall@centerpointenergy.com, tony.hudson@tnmp.com, andy.nguyen@lcra.org | D
Policy | LFL-53 |  | Consider the need to review transmission cost-allocation rules. | 2022-04-14 | Evaluated - No Action Needed
Policy | LFL-54 |  | Consider the need to review rules for the provision of standby service. | 2022-04-14 | Evaluated - No Action Needed
Policy | LFL-55 |  | Consider whether LFLs should be required to register as CLRs. | 2022-04-14 | Addressed in RR Drafts | NPRR, PGRR
Policy | LFL-56 | LFL-29 | Evaluate the pros and cons of LFLs participating in SCED vs. responding passively a) Should LFLs be required to register as CLRs b) Should there be rules requiring CLRs to be available for SCED dispatch c) Evaluate the need for rules prohibiting the switching between CLR and non-CLR participation and/or nodal and Load Zone settlement c) Evaluate need for nodal settlement of LFLs not participating in SCED d) If LFLs not required to be CLRs/dispatched by SCED, identify other potential | 2022-05-17 | Merged with Another Issue