## Slide 1
Weekly Market Readiness for
ERCOT Contingency Reserve Service (ECRS)
Matt Mereness and other ERCOT staff
June 6, 2023

## Slide 2: Agenda
Key Milestones
Key supporting documentation
Qualification next steps
Communication and Cutover
Questions

## Slide 3: Milestones for ECRS Implementation
  ECRS Technical Specs- Sept 29, 2022 TWG meeting
  Market Readiness and Qualification Workshop (Monday April 3, 2023)
  Friday April 14, 2023- Deadline for Deadline for QSE Declaration of Resources
  Thursday, April 20, 2023- MOTE deployed for QSEs to test
  Tuesday, April 23, 2023- Begin Weekly Market Readiness WebEx meetings
  Current activity
    ECRS QSE qualification essentially complete
    For all QSEs, MOTE scorecards discontinue after today
  June 8, 2023 System migration (first ECRS OD plan for June 10, 2023)

## Slide 4: Scorecard AS Offers

## Slide 5: Scorecard COP part 1

## Slide 6: COP part 2

## Slide 7: Scorecard AS Self- Arrangement

## Slide 8: Communication and Cutover
For the Cutover activities only ERCOT has set-up a 7x24 mailbox for supporting ECRS implementation (in addition to usual support channels)
ECRSCutover@ercot.com
This email address will be monitored now and through the weekend from June 8th-12th

## Slide 9: Communication and Cutover
June 8, 2023
  System upgrade will occur the afternoon of June 8th between 3:30-4:00pm
  MPs do not need to take any immediate action following the upgrade.
  After the upgrade ECRS system functionality will be available for OD June 10, 2023
    Note that COP, AS Trades, AS Offers, Self-Arranged AS must only be submitted for OD June 10 or later (not systematically enforced)
June 9, 2023
  Starting at 12:01am Telemetry for On-Hold status can be used (NPRR1085)
  Day-Ahead Market activities include ECRS:
    Considering Day-Ahead Credit for ECRS to leverage historical Non-Spin price as proxy
    AS Plan published for DAM OD June 10 will include ECRS values for DAM consideration
    QSEs submit AS Self Arrangements and AS Offers into DAM
    DAM Awards for OD June 10 will include ECRS Awards and should be reflected in COP for OD June 10 for DRUC run.
  After DAM, QSE submits COP updates OD June 10 to include ECRS
June 10, 2023
  First Operating Day with ECRS
  Starting at 12:01am, telemetry should include ECRS values

## Slide 10: Communication and Cutover
Special note on Group transition
After cutover, grouping assignments for NCLRs with RRS Responsibilities will change FROM Group 1 thru 4 TO Group 2 thru 4.
  Grouping report posted on 06/08 (before cut-over) will still show old grouping logic for RRS for OD June 9th .
  Report will be re-run manually and posted after cutover to show the new group assignments that will be used on OD June 9th for any NCLRs carrying RRS (in the event that there is a deployment).
  There will NOT be any NCLRs with ECRS obligation for OD Jun 9th , so there should not be anything to deploy for Groups 0, 1a, 1b and 1c.
  MPs are expected to respond based on the XML instructions for all NCLR deployments.

## Slide 11: Wrap-up and Questions
Wrap-Up:
  For ECRS QSE qualification is essentially complete
  MOTE scorecards will discontinue after today
  Market cutover issues can be sent to
    ECRSCutover@ercot.com
Open to any and all questions?
THANK YOU FOR THE SUPPORT OVER THE PAST FEW MONTHS!

## Slide 12
Appendix

## Slide 13: Supporting Documentation for ECRS
  Key References (in April 13, 2023 Market Notice):
    ECRS Interface changes: https://www.ercot.com/calendar/09292022-TWG-Meeting-by-Webex
    ECRS Operations and Business explanation
      April 3, 2023 Workshop will be latest revisions- link to meeting
    Technical updates:
      Sample XML Questions
        XML Sample ECRS Deployment
          03/29/2023 09.03.09 AM QTEST CM-ASM-NOTF AS_TYPE: ECRS, RES_NAME: LD_TEST, DEPLOY_MW: 5.0, BEGIN_TIME: 2023-03-29 09:03:09, END_TIME: 2023-03-29 10:00:00, DURATION: 56.85 mins, ID: 365;
        XML Sample ECRS DAM Award
          Sample DAM AS Awards place on April 3, 2023 Workshop link to meeting
        EIP specifications document has been updated here https://www.ercot.com/files/docs/2022/05/03/EIP-External-Interfaces-Specification-v1.25.zip
        Extract MODE/CODE details in Market Notice Friday May 5, 2023
    Updated AS Methodology supporting deployment details
      Incorporated the ECRS deployment procedure into the updated AS Methodology documentation on the ERCOT website (ercot.com | Market Information | Day-Ahead Market | Methodology for Determining Minimum AS Reqt).
    Scorecards will begin publishing on May 9, 2023 (for activities of May 1-8)
      AS Offer submissions will be scored on ability to submit a single AS Offer into MOTE.
      COP submissions will be scored on ability to submit a single COP into MOTE.
      AS Self-Arrangement submissions will be scored on ability to submit an AS Self- Arrangement into MOTE.
      (see attached population of QSEs)

## Slide 14: Groupings for RRS and ECRS explanation
Details of Grouping were in April 3 Workshop, but a couple of highlights:
  Groups assignments for Resources only carrying RRS will continue to follow the Day-Ahead group assignments.
  Those Resources with no group assignment and only carrying RRS will continue to be deployed with Group 2.
  For Resources providing ECRS, the Day Ahead group assignment is not used, and groupings will be generated in real-time (based on telemetry).
  QSEs carrying ECRS must deploy NCLRs based on the XML instruction (also true of RRS).
  The column GroupNo will be a Lower-case String, instead of a Number.
    Sample Values: 0, 1a, 1b, 1c, 2, 3, 4