## Sheet1
Market Coordination Meeting (MCT) Meeting Notes / Action Items
MCT Notes / Action Items 01:00 | 2023-05-17
Agenda Item: | Decision / Resolution | Action Items :
Meeting Notes April 19, 2023
No changes were noted. |  | The notes will be posted to the April 19, 2023 meeting page.
Review 5.0 Updated Requirements v2.5
ERCOT Staff reviewed the updated list and made changes as needed.
Review Texas SET Implementation Guides Redlines (814 series)
ERCOT reviewed the 814_01 thru 814_19 Redlines (exception 814_04 and 09) | No further changes were noted than those already sent to ERCOT from the review.
ERCOT requested a review of the 814_20 thru 814_29 Redlines |  | The meeting attendees will complete the review and send any changes to ERCOT.
V5.0 Example Review
ERCOT reviewed the examples and made changes as needed. | The group was requested take these back to review further; then provide feedback, if any, via email to ERCOT (Kathryn Thurman).
Other Business
Texas SET V5.0 Scripts | ERCOT reviewed the updated Script workbooks. | ERCOT will post the script workbook for the existing CRs to the MCT page. ERCOT will post the script workbook for the new CRs to the Testing page.
Texas SET V5.0 Q & A updates | ERCOT reviewed the updated Q & A Document. | ERCOT will post to the MCT page.
Next Meeting-- WebEx Only | 2023-06-21
Attendees F-T-F
Attendees Webex
Amy Sure Stirland LP&L | Jordan Troublefield ERCOT
Bill Snyder AEP | Kathryn Thurman ERCOT
Carole Root AEP | Kathy Scott Centerpoint Energy
Cassandra Jenkins Centerpoint Energy | Kyle Patrick NRG
Catherine Meiners ERCOT | Laura Gomez LP&L
Daily Smith LP&L | Lee Doehring
Dave Michelsen ERCOT | Pam Shaw Principle Staff
Deb Belin Earth Etch | Paula Shadle NEC
Diana Rehfeldt TNMP | Stephen Wilson Vistra
Eric Lotter - GridMonitor | Tyler Krueger BDE