## Slide 1
Real-Time Co-optimization (RTC) Update
Matt Mereness
TAC
June 27, 2023

## Slide 2: Scope of RTC Program
ERCOT leadership shared update on RTC with Board-RMC Agenda 6
In considering implementation of RTC in the coming years, the proliferation of Batteries needs to be addressed, which is growing to over 14GW in 2025
As RTC will touch almost every major system in ERCOT, battery functionality will be addressed and included with this effort.
Program spans across departments and shared by many VPs with the following scope:
  RTC (NPRR1007-1013)
  Single Model Batteries
  (NPRR1014)
  State of Charge modeling
  in SCED and RUC
  (June market discussion
  and NPRR in July)

## Slide 3: Implementation of RTC
ERCOT has developed an Impact Analysis for a program to deliver:
  RTC (NPRR1007-1013), Single Model Batteries (NPRR1014), State of Charge modeling in SCED and RUC
The overall program will cost approximately $50M, with a go-live sometime in 2026 between major releases of EMS and MMS.
Key delivery areas have been reviewed for major resource risk
  Initial focus: July 2023-April 2024 (project planning phase)
  Per our usual process, a revised cost estimate and timeline is produced when project planning is complete
  Teams are very busy with other critical efforts but most of the RTC planning work can be accommodated within available capacity
  There are areas of concern, but these over-allocations are still being worked on
Key Takeaway
  Primary risk is maintaining staff availability without interruption during this 3+ year effort.

## Slide 4: Next Steps
ERCOT has already initiated the RTC Program Control project
Program is re-starting with business requirements July 1, 2023.
Program will provide regular updates to TAC and begin evaluating the next steps for MP engagement and interfaces.