## Slide 1
Project Update
July 13, 2023
Troy Anderson
ERCOT Portfolio Management

## Slide 2
  Recent / Upcoming Project Highlights
  2023 Release Targets
  2024 Release Targets
  Additional Project Status Information
  Priority/Rank Options for Revision Requests with Impacts
    NPRR1165 – Revisions to Requirements of Providing Audited Financial Statements and Providing Independent Amount
    NPRR1182 – Inclusion of Controllable Load Resources and Energy Storage Resources in the Constraint Competitiveness Test Process
    NPRR1183 – ECEII Definition Clarification and Updates to Posting Rules for Certain Documents without ECEII
  Technology Working Group (TWG)
    Next meeting date is TBD
Location of Revision Request Project Information: http://www.ercot.com/services/projects
Project Update Agenda

## Slide 3: Recent / Upcoming Project Highlights
2023 July Off-Cycle Release – 7/14/2023 In Flight
  SCR789 Phase 2 – Update NMMS Topology Processor to PSS/E 35
2023 July Release – R4 – 7/25/2023-7/27/2023 In Flight
  Securitization Phase 2A – Maine Invoice and Credit Exposure
2023 October Off-Cycle Release – 10/1/2023 In Flight
  NPRR1112 – Elimination of Unsecured Credit Limits
2023 October Release – R5 – 10/3/2023-10/5/2023 In Flight
  NPRR1040 – Compliance Metrics for Ancillary Service Supply Responsibility
  NPRR1154 – Include Alternate Resource in Availability Plan for Firm Fuel Supply Service
  NPRR945 – Net Metering Requirements (not yet started – target go-live likely to move)
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2023 Release Targets – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 1/31 – 2/2 | March 3/28 – 3/30 | June 6/6 – 6/8 | July 7/25 – 7/27 | October 10/3 – 10/5 | December 12/5 – 12/7
NPRR1020(a) | None | ECRS (NPRR863) NPRR903 NPRR992 NPRR1015 NPRR1085 NPRR1096(b) NPRR1148 NOGRR186 NOGRR187 OBDRR043/44 | Securitization Phase 2A – Maine Invoice and Credit Exposure SCR789 Ph2 NPRR1112 | NPRR945 NPRR962 NPRR1040 NPRR1090 NPRR1121 NPRR1154 | NPRR1092(b) SCR807 SCR816 SCR822 EMS Upgrade
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
EMS Upgrade Freeze – July 2023 – Jan. 2024
NPRR1020(a) – EPS Metering portion
NPRR1092(b) – Limit RUC Opt-Out Provision
NPRR1096(b) – ECRS portion
TBD | NPRRs: 484,825(b),826,829,841,857,879,885,904,918,930,936,941,963,965,975,987,995,1004,1006,1007,1019,1023,1026,1030,1032,1034,1057, 1077,1105, 1111,1128,1131,1136 SCRs: 799,805,810,813,818,819 PGRRs: 066,076,088,091,094,099 Other: OBDRR009,OBDRR017,RRGRR028
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
NS
E
E
P
E
E
NS
11/15
7/14
E
E
E
ü
10/1
Move to 2024-R1
Move to 2024-R3

## Slide 5: 2024 Release Targets – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February Dates TBD | March Dates TBD | June Dates TBD | July Dates TBD | October Dates TBD | December Dates TBD
NPRR1092(b) SCR822 |  | NPRR1149 NPRR1121 NPRR1090 NPRR962 |  | TX SET 5.0 NPRR1095 SCR817 SCR823 | 
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
NPRR1092(b) – Limit RUC Opt-Out Provision
I
I
I
I
P
NS
E
E
E
2024 release dates are still being finalized
11/10

## Slide 6: Additional Project Status Information
Revision Request | Description | Project Phase | Additional Detail
SCR820 | Operator Real-Time Messaging During Emergency | Planning | Go-Live target is TBD
NPRR1004 | Load Distribution Factor Process Update | Not Started | Mid-2023 start candidate
NPRR1006 | Update RT On-Line Reliability Deployment Price Adder Inputs to Match Actual Data | On Hold | Assessing restart date options
NPRR1026 | BESTF-7 Self-Limiting Facilities | Not Started | Approved to start in Q3 2023
NPRR1128 | Allow FFR Procurement up to FFR Limit Without Proration | Not Started | Assessing start date options 2023 candidate
NPRR1131 | Controllable Load Resource Participation in Non-Spin | Not Started | Assessing start date options 2023 candidate
NPRR1136 | Updates to Language Regarding a QSE Moving Ancillary Service Responsibility Between Resources | Not Started | ERCOT staff is sponsoring NPRR1189 - will make remaining NPRR1136 language obsolete
SCR819 NPRR1111 | Improving IRR Control to Manage GTC Stability Limits | Not Started | Targeting Q4 2023 start
NPRR1007 NPRR1014 | SCED Postings Gray-boxed in Section 3.2.5(4) Publication of Resource and Load Information | Not Started | Potential implementation of the gray box in this section, specifically the increasing of granularity for SCED disclosure reporting Evaluating a 2023 start
Red Text: New additions and updates
Page 1 of 2

## Slide 7: Additional Project Status Information
Revision Request | Description | Project Phase | Additional Detail
NPRR1002 RRGRR023 | BESTF-5 ESR Single Model Registration and Charging Restrictions in Emergency Conditions | Not Started | Approved for Q3 2023 start
NPRR1164 RRGRR033 | Black Start and Isochronous Control Capable Identification | Not Started | Approved for Q3 2023 start Still in stakeholder process (ROS)
RRGRR032 | Communicate Operating Limitations during Cold and Hot Weather Conditions | Not Started | Approved for Q3 2023 start
NPRR1153 | ERCOT Fee Schedule Changes | Not Started | Approved for Q3 2023 start
PGRR103 | Establish Time Limit for Generator Commissioning Following Approval to Synchronize | Not Started | Approved for Q3 2023 start Still in stakeholder process (Board)
Red Text: New additions and updates
Page 2 of 2

## Slide 8: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR1165 | Revisions to Requirements of Providing Audited Financial Statements and Providing Independent Amount | 2023 | 3800 | $50k-$100k, 5-8 months Impacted System: CMM
NPRR1182 | Inclusion of Controllable Load Resources and Energy Storage Resources in the Constraint Competitiveness Test Process | 2024 | 4030 | $60k-$90k, 5-7 months Impacted System: MMS
NPRR1183 | ECEII Definition Clarification and Updates to Posting Rules for Certain Documents without ECEII | 2024 | 4040 | $50k-$75k, 4-6 months Impacted Systems: ERCOT.com, MIS, data management systems
NPRR1184 | Update to Procedures for Managing Interest on Cash Collateral | TBD | TBD | Need another month to complete IA
Options for…
PPL Rank Information
Next available 2023 Rank in Business Strategy = 3800
Next available 2024 Rank in Business Strategy = 4030
Next available Rank in Regulatory = 370

## Slide 9: Technology Working Group (TWG)
Next TWG meeting date is TBD