## Slide 1
Project Update
August 10, 2023
Troy Anderson
ERCOT Portfolio Management

## Slide 2
  Recent / Upcoming Project Highlights
  2023 Release Targets
  2024 Release Targets
  Additional Project Status Information
  Priority/Rank Recommendations for Revision Requests with Impacts
    NPRR1164 – Black Start and Isochronous Control Capable Identification
    NPRR1171 – Requirements for DGRs and DESRs on Circuits Subject to Load Shedding
    NPRR1186 – Improvements Prior to the RTC+B Project for Better ESR State of Charge Awareness, Accounting, and Monitoring
    NOGRR215 – Limit Use of Remedial Action Schemes
  Technology Working Group (TWG)
    Next meeting date is 8/24/2023
Location of Revision Request Project Information: http://www.ercot.com/services/projects
Project Update Agenda

## Slide 3: Recent / Upcoming Project Highlights
2023 July Release – R4 – 7/25/2023-7/27/2023 Complete
  Securitization Phase 2A – Maine Invoice and Credit Exposure
    First Maine invoices will be produced on 8/9/2023
2023 October Off-Cycle Release – 10/1/2023 In Flight
  NPRR1112 – Elimination of Unsecured Credit Limits
2023 October Release – R5 – 10/3/2023-10/5/2023 In Flight
  NPRR1040 – Compliance Metrics for Ancillary Service Supply Responsibility
  NPRR1154 – Include Alternate Resource in Availability Plan for Firm Fuel Supply Service
2023 October Off-Cycle Release – Date TBD In Flight
  NPRR1026(a) – BESTF-7 Self-Limiting Facilities
    RIOO portion
2023 November Off-Cycle Release – 11/15/2023 In Flight
  EMS Upgrade
2023 December Release – R6 – 12/5/2023-12/7/2023 In Flight
  SCR807 – Increase CRR Transaction Capability
  SCR816 – CRR Auction Bid Credit Enhancement
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2023 Release Targets – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 1/31 – 2/2 | March 3/28 – 3/30 | June 6/6 – 6/8 | July 7/25 – 7/27 | October 10/3 – 10/5 | December 12/5 – 12/7
NPRR1020(a) | None | ECRS (NPRR863) NPRR903 NPRR992 NPRR1015 NPRR1085 NPRR1096(b) NPRR1148 NOGRR186 NOGRR187 OBDRR043/44 | Securitization Phase 2A – Maine Invoice and Credit Exposure SCR789 Ph2 NPRR1112 | NPRR945 NPRR1040 NPRR1154 EMS Upgrade | SCR807 SCR816 NPRR1026(a)
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
EMS Upgrade Freeze – July 2023 – Jan. 2024
NPRR1020(a) – EPS Metering portion
NPRR1026(a) – RIOO portion
NPRR1096(b) – ECRS portion
TBD | NPRRs: 484,825(b),826,829,841,857,879,885,904,918,930,936,941,945,963,965,975,987,995,1004,1006,1007,1019,1023,1030,1032,1034,1057, 1077,1105, 1111,1128,1131,1136 SCRs: 799,805,810,813,818,819 PGRRs: 066,076,088,091,094,099 Other: OBDRR009,OBDRR017,RRGRR028
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
E
E
E
E
E
11/15
7/14
ü
E
ü
10/1
ü
R5 Off-Cycle

## Slide 5: 2024 Release Targets – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February TBD | March TBD | June TBD | July TBD | October TBD | December TBD
NPRR1092(b) NPRR1026(b) SCR822 | NPRR1002 NPRR1153 NPRR1164 PGRR103 RRGRR023 RRGRR032 RRGRR033 | NPRR1149 NPRR1121 NPRR1090 NPRR962 |  | TX SET 5.0 NPRR1095 SCR817 SCR823 RMGRR172 | 
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
NPRR1026(b) – Reporting portion
NPRR1092(b) – Limit RUC Opt-Out Provision
I
I
I
I
P
P
I
E
E
E
E
2024 release dates are still being finalized
11/10
Q1 – RIOO

## Slide 6: Additional Project Status Information
Revision Request | Description | Project Phase | Additional Detail
RTC | NPRR1007-NPRR1014, Single Model, State of Charge | Planning | Project has restarted
SCR820 | Operator Real-Time Messaging During Emergency | Planning | Go-Live target is TBD
NPRR945 | Net Metering Requirements | Not Started | Start delayed due to an internal project dependency
NPRR1004 | Load Distribution Factor Process Update | Not Started | Assessing start date options
NPRR1006 | Update RT On-Line Reliability Deployment Price Adder Inputs to Match Actual Data | On Hold | Assessing restart date options
NPRR1058 | Resource Offer Modernization | Not Started | Assessing start date options
NPRR1128 | Allow FFR Procurement up to FFR Limit Without Proration | Not Started | Assessing start date options
NPRR1131 | Controllable Load Resource Participation in Non-Spin | Not Started | Assessing start date options
SCR805 | Provide Early Access to Certain 60-Day Reports to TSPs Upon Request | Not Started | Assessing start date options
SCR819 NPRR1111 | Improving IRR Control to Manage GTC Stability Limits | Not Started | Targeting Q4 2023 start
NPRR1007 NPRR1014 | SCED Postings Gray-boxed in Section 3.2.5(4) Publication of Resource and Load Information | Not Started | Increasing granularity for SCED disclosure reporting
Red Text: New additions and updates

## Slide 7: Priority / Rank Recommendations for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR1164 | Black Start and Isochronous Control Capable Identification | 2023 | 3810 | $75k-$125k, 6-9 months Impacted System(s): NMMS, EMS, RIOO
NPRR1171 | Requirements for DGRs and DESRs on Circuits Subject to Load Shedding | 2024 | 4050 | $350k-$550k, 9-12 months Impacted System(s): MMS, EMS, RIOO
NPRR1184 | Update to Procedures for Managing Interest on Cash Collateral | TBD | TBD | Need another month to complete IA
NPRR1186 | Improvements Prior to the RTC+B Project for Better ESR State of Charge Awareness, Accounting, and Monitoring | 2023 | 3595 | $500k-$700k, 7-10 months Impacted System(s): MMS, EMS, NMMS
SCR824 | Increase File Size and Quantity Limits for RIOO Attachments | TBD | TBD | Need another month to complete IA
NOGRR215 | Limit Use of Remedial Action Schemes | 2026 | 4700 | $1.0M-$1.5M, 12-18 months Impacted System(s): MMS, EMS, Reporting ROS provided Priority/Rank input
Recommendations for…
PPL Rank Information
Next available 2023 Rank in Business Strategy = 3810
Next available 2024 Rank in Business Strategy = 4050
Next available Rank in Regulatory = 370

## Slide 8: Technology Working Group (TWG)
Next TWG meeting date is 8/24/2023
Agenda is under development
  Likely to include these items (and potentially others)
    Public API and API improvements
    Developer Portal
    WAN provider update
    EMS upgrade update
    NERC Project 2015-09 update
    ESR related ICCP points expectations