## Sheet1
Market Coordination Meeting (MCT) and Texas SET Meeting Notes / Action Items
2023-07-19
Agenda Item: | Decision / Resolution | Action Items :
Meeting Notes June 21, 2023--MCT
No Changes were made to the notes. |  | The Vice-chair will have the meeting notes posted to the May meeting page key documents.
Review Texas SET Implementation Guides Redlines
Feedback on Texas SET Implementation Guide Redlines (650s, 810s, 820s, 824, 867s, 997, T series) | There was a question about the 997 not having TX SET Version numbering like the other guides. It was determined that 997s are not affected by TX SET versioning. It would only update if TX SET updated the ANSI X12 version from 004010. There were no other changes to the redlines. | ERCOT will post the updated redlines and SEF files to the MCT main page.
Other items
ERCOT SCR817 Open Discussion | ERCOT held a discussion regarding the questions answered at the TDTMS meeting yesterday. The Missing Enrollment Transactions validation for Bulk Inserts will be turned to "on". The Unexecutable Reasons dropdown box will remain the same for the new 867 vs AMS LSE data subtype and users can enter reasons in the comments. ERCOT will begin updating the MarkeTrak Users Guide and pass the changes on to the Training group to update the MarkeTrak Modules as well as the instructor led documentation. MCT meeting attendees will access the updated documents on the MCT main page key documents.
Cut Over document for transition to TX SET Version 5.0 timeline and MarkeTrak updates | ERCOT stated that they will begin working on the document to have avaiable beginning next month.
Workshop to discuss the cutover | Texas SET attendees agreed that a workshop would be helpful. This is planned in be held in early 2024.
Will ERCOT complete Validation of Leep Frog Scenarios | ERCOT stated that they do not and a meeting attendee stated that the TDSPs will validate for those | ERCOT will update the Q & A document and repost to the MCT main page key documents
Meeting Notes May 17, 2023--TX SET
No Changes were made to the notes. |  | The Vice-chair will have the meeting notes posted to the May meeting page key documents.
ERCOT Flight Update
ERCOT presented the Flight Update. ERCOT stated that they have sent all the certification letters out. ERCOT also stated that the 11 that did not complete the LP&L test flight will have to test again in the October Test Flight in order to be able to go live when LP&L in early 2024.
TX SET / MCT 2023 Schedule Discussion
The TX SET Chair conducted a discussion related to the rest of the year meeting schedules. | The plan is to combine the MCT and TX SET meetings as needed to avoid attendees having a big space between the meetings and to faciliate the a better use of their time.
Lubbock Power & Light (LP&L) Discussion--if any
No Actions were needed from Texas SET. | It was suggested that groups review the transition / stacking tasks for the cutover.
Other Business
MIS API Update | On the 2nd week of December (9th) a new API, (SOAP) based, will be rolled out. The updates will be avaiable in the test environment a couple of weeks before.
Next Meeting-- WebEx Only | 2023-08-16
Attendees F-T-F
Attendees Webex
Amy Sue Stirland LP&L | Kyle Patrick NRG
Carolyn Reed Centerpoint Energy | Laura Gomez LP&L
Darice Taipalus / TNMP | Lee Doehring Centerpoint Energy
Dave Michelsen ERCOT | Lori Lee Barfield Just Energy
Deb Belin Earth Etch | Mark Pepdjonovic ESG
Dee Lowerre | Monica Jones-Centerpoint Energy
Diana Rehfeldt TNMP | Paul Yockey ERCOT
Elizabeth Baiza LP&L | Paula Shadle NEC
Eric Lotter - GridMonitor | Pryanka Konangi TNMP
Frank Nunes Vertex One | Sam Pak ONCOR
Gary Walcott TNMP | Scarlet Marsh LP&L
Jesse Macias AEP | Sheri Wiegand Vistra
Jordan Troublefield ERCOT | Stephen Wilson Vistra
Kathryn Thurman ERCOT | Toni Bean Centerpoint Energy
Kathy Scott Centerpoint Energy | Viviana Valdez LP&L
Krista Ortiz LP&L | Vrushal Bonde TNMP