## Slide 1
EMS Upgrade Project Update
August 17, 2023
Thinesh Devadhas Mohanadhas
ERCOT Operations

## Slide 2: EMS Upgrade Go-Live Scheduled for November 2023
Closed Loop Testing in EMS 3.3 Environment
  Planned time window between 09/18 – 11/16
  Actual Closed Loop testing dates & duration of closed loops will be communicated in coming weeks
Definitions
  EMS 3.0 – Current EMS environment that is being upgraded
  EMS 3.3 – Upgraded EMS environment
  Cutover – Temporary transfer of control from EMS 3.0 to EMS 3.3 for Closed Loop testing
  Cutback – Return to normal operations using EMS 3.0

## Slide 3: EMS Upgrade Go-Live Scheduled for November 2023
ERCOT Activities for Closed Loop Testing (Duration: 2–4 hours)
  Cutover
    EMS 3.0 systems cutover to EMS 3.3 with a local failover
    Production market systems will be connected to EMS 3.3
  Control room will utilize EMS 3.3 to control ERCOT Grid for Frequency and Congestion Management
  Cutback
    Frequency control and congestion management returns to EMS 3.0
    EMS 3.0 will reconnect to production market systems
Market Impacts During Closed Loop Testing (Duration: 2–4 hours)
  No changes to Telemetry points and ICCP communications
  SCED Base Points, Updated Desired Base Points, portfolio level QSE deployment signals will continue to be sent to MPs on same telemetry points as today
  EMS functionalities continue to remain same between EMS 3.0 and EMS 3.3
  Market Submissions and Reports will not be impacted
  Existing communication channels will be used to communicate with MPs during cutover and cutback activities