## Slide 1
EMS Upgrade Project Update
August 24, 2023

## Slide 2: EMS Upgrade Project Updates
Key Milestones:
  ICCP Upgrade Cutover
  Closed Loop Testing in EMS 3.3 Environment
  Go Live - Scheduled for November 2023
ICCP Upgrade Cutover
  small interruption (around 5 minutes) possible on market participants redundant links
  no action required from market participants.
  9/14 – Cutover TSP Taylor ICCP servers.
    Bastrop links will remain up so no data loss.
  9/18 – Cutover TSP Bastrop ICCP servers.
    Taylor links will remain up so no data loss.
  9/20 - Cutover QSE Taylor ICCP servers.
    Bastrop links will remain up so no data loss.
  9/21-25 - Cutover QSE Bastrop ICCP servers.
    Taylor links will remain up so no data loss.
Closed Loop Testing in EMS 3.3 Environment
  Planned time window between 09/18 – 11/16
  Actual Closed Loop testing dates & duration of closed loops will be communicated in coming weeks

## Slide 3: EMS Upgrade Project Updates
ERCOT Activities for Closed Loop Testing (Duration: 2–4 hours)
  Cutover
    EMS 3.0 systems cutover to EMS 3.3 with a local failover
    Production market systems will be connected to EMS 3.3
  Control room will utilize EMS 3.3 to control ERCOT Grid for Frequency and Congestion Management
  Cutback
    Frequency control and congestion management returns to EMS 3.0
    EMS 3.0 will reconnect to production market systems
Market Impacts During Closed Loop Testing (Duration: 2–4 hours)
  No changes to Telemetry points and ICCP communications
  SCED Base Points, Updated Desired Base Points, portfolio level QSE deployment signals will continue to be sent to MPs on same telemetry points as today
  EMS functionalities continue to remain same between EMS 3.0 and EMS 3.3
  Market Submissions will not be impacted
  Market Reports will have 10-15 minutes down time during cutover and cutback.
  Existing communication channels will be used to communicate with MPs during cutover and cutback activities.