## Slide 1
Resource Integration Topics
Jay Teixeira
ERCOT
Resource Integration Working Group
October 10, 2023

## Slide 2: Quarterly Stability Assessment (QSA)
Planning Guide 5.9
Next Deadline for QSA
If a GINR is not included in QSA, its Initial Synchronization date will be automatically delayed to the next quarter
All-Inclusive Generation Resource Initial Synchronization Date | Last Day for an IE to meet prerequisites as listed in paragraph (4) below | Completion of Quarterly Stability Assessment
Upcoming January, February, March | Prior August 1 | End of October
Upcoming April, May, June | Prior November 1 | End of January
Upcoming July, August, September | Prior February 1 | End of April
Upcoming October, November, December | Prior May 1 | End of July

## Slide 3: Quarterly Stability Assessment (QSA)
Planning Guide 5.9, Quarterly Stability Assessment
Issue’s seen in previous QSA’s
  10 day comment period for FIS
    Needs to be complete before QSA deadline
    TSPs need to plan for it
  Dynamic/PSCAD Model Review
    Dependent on FIS Stability study
    Need to meet PG 6.9 15 to 30 days prior to QSA deadline
PSSE Model Quality Test Required
PSCAD Model Quality Test and Unit Model Validation required
TSAT Model Required – If PSSE model is UDM, then TSAT model should be UDM and should include MQT

## Slide 4: RIOO-IS and RARF
The new release allows entry of resource data into RIOO database rather than use of RARF
Migration of RARF forms to RIOO-IS will not be available
IE/RE may will have to re-enter data into RIOO-IS if in FIS or Planning stage. Those with an PLD in 2023 may continue to use RARF forms.
PLD dates beyond 2023 (even those that slip) will have to re-enter data into RIOO-IS
Screenshot document created to help with RIOO-IS

## Slide 5: PGRR103 Good Cause exception request form
(2) Within 300 days of receiving ERCOT’s approval for Initial Synchronization above 20 MVA of a new or repowered Generation Resource or ESR, a Resource Entity shall ensure the Resource meets the conditions established by ERCOT for commercial operations and shall submit a request to ERCOT to commission the Resource.
In the event a Generation Resource or ESR will be unable to complete all necessary construction and required testing to commence commercial operations and connect reliably to the ERCOT System within the 300 days, the Generation Resource or ESR may request a good cause exception with sufficient detail, and shall notify ERCOT prior to the planned commercial operation date and provide ERCOT with an updated commercial operation date that the Generation Resource or ESR can reasonably expect to commence operations in a reliable manner.
Language added by PGRR103
to Planning Guide 5.5

## Slide 6: AVR and PSS Telemetry requirements
The AVR/PSS Status Points are needed by the ERCOT Operations for Situational Awareness of all the Resources in ERCOT.
Part 2 Synchronization will not be approved until the points are provided..

## Slide 7: Breaker data for FIS stage

## Slide 8: Active RR’s
PGRR103 - Establish Time Limit for Generator Commissioning Following Approval to Synchronize – To be approved by PUCT on Oct 12, 2023?. Nov 1, 2023, effective date
PGRR112 - Dynamic Data Model and Full Interconnection Study (FIS) Deadline for Quarterly Stability Assessment – initial review by ROS on Oct 5, 2023.

## Slide 9: Other contact information
ResourceIntegrationDepartment@ercot.com is distribution list for Resource Integration department
Mailing List
  RESOURCE_INTEGRATION@LISTS.ERCOT.COM

## Slide 10: Questions?
Thank you!

## Slide 14: Node creation and use
Must be entered
To create Node
Must be entered
To create Node
Nodes
Created at
34.5 kV
Click to create
node
August Update: Please use 4 numeric digits for node names
0001
0002
0003
0004

## Slide 15: Date Relationships and how to change them
Use Basic Project Information
Add a Change Request
To Change
Change on Substation Details
Notes: 24INR0813 on ITEST

## Slide 16: Changing Contacts
RE Contact Scheme
Primary Contact
Full Name: I Me Mine
Company: ERCOT RE LLC (RE)
An.emailaddress@att.net
DUNS: 012345673000
P: 5125551234
Ext:
IE Contact Scheme
Primary Contact
Full Name: For You Blue
An.emailaddress@att.net
P: 5125551234
Ext:
Backup Contact
Full Name: I Me Mine
An.emailaddress@att.net
P: 512-5551234
Ext:
To Change from RE Contact Scheme to IE Contact Scheme

## Slide 17: RARF Attestation – Coming Up in September
Most entities could not click “Make an Attestation” button
Cause undetermined at the time
Should be fixed
ERCOT instructed entities to complete Planning Guide Section 8, Attachment A: Declaration of Resource Data Accuracy and attach to RIOO as type “Other”

## Slide 18: Attachments for embedded documents
Renewable Form Tab Name | Files to be include from that tab | Proposed RIOO Attachment Type
Collector System - RENEWABLE | Collection System One Line Diagram – Collector Workbook, One-Line | CollectorSystem
 | Collection System Detailed Model – RAW, SEQ | CollectorSystemModel
Dynamic Data | PSSE Model and MQT VSAT Model and MQT | PSSE MMQT,VSAT MMQT
PSCAD Model | PSCAD Model and MQT | PSCAD MMQT
Inverter Efficiency Curve | Inverter Efficiency Curve | Inverter Curve
Transmission Form Tab Name | Files to be include from that tab | RIOO Attachment Type
One Line | PDF or CAD One Line Diagram | One-Line (existing type)
Transformer Test Data | Transformer Test Data | Test Data
Attach these documents using Basic CR with type “Other” until attachment types are available

## Slide 19: Modifying the Project Details to make corrections that cannot be made in RIOO

## Slide 20: Modifying the Project Details to make corrections that cannot be made in RIOO
Take latest Project Details file, which is an excel spreadsheet and modify the data that cannot be modified in RIOO. Find the tab and modify the data. Re-attach to RIOO as file “Other” and put “_modified” at the end of the filename. “REG_23INR0424_11-04-2022_modified.xlsx”

## Slide 21: TSPs not Creating RIOO Accounts Correctly
Use this document
  https://www.ercot.com/files/docs/2022/01/14/TSP-Sign-Up-for-RIOO-Services.pdf.
Too many TSP employees create IE account because they didn’t use the above document
Takes several days for ERCOT to fix this issue in the database and in auth0
TSP’s and RE’s – never click this tab!
TSP’s and RE’s – start here after USA adds role

## Slide 22: TSPs not Creating RIOO Accounts Correctly
Do not do anything until you receive an email from ERCOT. This may take 20 minutes after the role is added.
Then click the verify email link in the email.
This gives you the RIOO Services log in page. Do not enter an email address or any other username. Click the “Don’t remember your password” link.
The next screen enter your email and another email will be sent to you. Click the “Change my Password” link.
You should get a message that your password has been reset successfully.
TSP’s – GINR_M_OPERATOR only
RE’s – RIOORS_M_OPERATOR only

## Slide 23: TSPs not Creating RIOO Accounts Correctly
Do not do anything until you receive an email from ERCOT. This may take 20 minutes after the role is added.
Then click the verify email link in the email.
This gives you the RIOO Services log in page. Do not enter an email address or any other username. Click the “Don’t remember your password” link.
The next screen enter your email and another email will be sent to you. Click the “Send Email” link.
You should get a message that your password has been reset successfully.
Click the “Don’t remember your password? link

## Slide 24: TSPs not Creating RIOO Accounts Correctly
Do not do anything until you receive an email from ERCOT. This may take 20 minutes after the role is added.
Then click the verify email link in the email.
This gives you the RIOO Services log in page. Do not enter an email address or any other username. Click the “Don’t remember your password” link.
The next screen enter your email and another email will be sent to you. Click the “Send Email” link.
If you do not get the “Password Change Request” email, contact your USA to make sure the email address is correct. Click the “Change my Password” link.
Change your password by entering your new password twice and click the button.
You should get a message that your password has been reset successfully.

## Slide 25: Is Load associated with INR

## Slide 26: Is Load associated with INR
            Not to be checked for
                Aux Load
              Battery charging load

## Slide 27: Load Names for BESS and non-BESS
For non-BESS, one load is required per MPT
Name = “LOAD1”, “LOAD2”, etc.
For each BESS, two loads are required
Name for WSL load = “CHARGE1”, “CHARGE2”, etc.
Name for Aux load, like chillers, = “BESS_AUX1”, “BESS_AUX2”, etc.

## Slide 28: Changes to COD and FIS Restudy
If the COD is changed and the case that would be used to do FIS study based on new COD is 2 case years or more different than original FIS study case year
prior to meeting QSA prerequisites
  Restudy is Needed
  TSP to determine FIS study elements that need to be restudied
  TSP and ERCOT agree
after meeting QSA prerequisites
  Check with TDSP and ERCOT Planning to see if project included in annual planning studies
  Check that no changes to dynamic model has occurred
  If Yes to both then no FIS restudies are required
    Recheck in 1 year OR if COD is delayed further
  If No to either check than FIS restudy needed
    TSP to determine FIS study elements that need to be restudied
    TSP and ERCOT agree
What if subsequent COD changes occur?

## Slide 29: COD Change Example
If the original study had a COD date of 2/2023, the original FIS would use the SSWG 23 Summer Peak case (July 1 is the flip date between 23SUM and 24SUM). If the COD then gets delayed to 2/2024, the 24 Summer Peak case would be used if a study was done. But this is only a difference of 1 SSWG case year, so no restudy would be necessary.
But if the COD gets further delayed until 8/2024, the 25 Summer Peak case would be used. This is a 2 year SSWG case difference (2025 -2023) so a restudy would be necessary.
We use the SSWG cases because they are built for every year for 5 years. I believe the DWG cases are built for 2 year increments, right? If we used the DWG case year difference, the case difference would either be 0 or 2 and possibly trigger too many restudies.

## Slide 30: Small Gen Clarifications
For Small Generation projects, the TDSP should log in to RIOO-IS and enter dates for IA signed date, financial commitment and notice to proceed. This is based on planning guide section 5.4 where this information is provided from the TDSP to ERCOT.
Small Generation System Impact Study (SIS) scope is a determination of the TDSP.
  The SIS scope and necessity of the SIS is a determination of the TDSP.
  ERCOT recommends that, at a minimum, a thermal, voltage, short circuit and flicker analysis are performed.
  ERCOT may inquire as to the reasoning why a TDSP states that a SIS may not be required.
If an affiliated IE or RE submits a less than 10 MW GIM that is behind the same TDSP station as another planned and affiliated GIM then the new less than 10 MW GIM will need to go through the large gen process.
Small generation projects require PSS/E models, PSCAD models, their associated Model Quality Tests and a PSCAD Unit Model Validation.

## Slide 31: Miscellaneous Reminders
Prior to Full Registration, ERCOT requests that the RE reach out to ERCOT at least 30 days prior to the deadline for the desired PLD to allow for calls and edits prior to submittal in RIOO-IS for review. For Full Registration, the desired Production Load Date deadlines can be found in https://www.ercot.com/gridinfo/transmission/opsys-change-schedule. Resource data submitted after 15 days prior to the PLD deadline may not get processed in time to be included in the desired PLD!
Load Resource request must be submitted in RIOO-IS at the same time as the Resource (BESS) full registration data submittal. Resource data will not be processed if the Load Resource Request is missing by the PLD deadline.