## Slide 1
Project Update
October 12, 2023
Troy Anderson
ERCOT Portfolio Management

## Slide 2
  Recent / Upcoming Project Highlights
  Major Projects
  2023 Release Targets
  2024 Release Targets
  Additional Project Status Information
  MPIM / MFA Discussion
  Priority/Rank Recommendations for Revision Requests with Impacts
    NPRR1172 – Fuel Adder Definition, Mitigated Offer Caps, & RUC Clawback
    NPRR1203 – Implementation of Dispatchable Reliability Reserve Service
  Technology Working Group (TWG)
    Next meeting date is TBD
Location of Revision Request Project Information: http://www.ercot.com/services/projects
Project Update Agenda

## Slide 3: Recent / Upcoming Project Highlights
2023 October Off-Cycle Release – 10/1/2023 Complete
  NPRR1112 – Elimination of Unsecured Credit Limits
2023 October Release – R5 – 10/3/2023-10/5/2023 Complete
  NPRR1154 – Include Alternate Resource in Availability Plan for Firm Fuel Supply Service
2023 November Off-Cycle Release – 11/1/2023 In Flight
  LPGRR070 – Discontinuation of Interval Data Recorder (IDR) Meter Weather Sensitivity Process
  NPRR1163 – Related to LPGRR070
  OBDRR048 – Implementation of Operating Reserve Demand Curve (ORDC) Multi-Step Price Floor
2023 November Off-Cycle Release – 11/15/2023 In Flight
  EMS Upgrade
2023 December Release – R6 – 12/5/2023-12/7/2023 In Flight
  SCR807 – Increase CRR Transaction Capability
  SCR816 – CRR Auction Bid Credit Enhancement
  NPRR1026(a) – BESTF-7 Self-Limiting Facilities
    RIOO portion
  NPRR1164 – Black Start and Isochronous Control Capable Identification
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: Major Projects

## Slide 5: 2023 Release Targets – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 1/31 – 2/2 | March 3/28 – 3/30 | June 6/6 – 6/8 | July 7/25 – 7/27 | October 10/3 – 10/5 | December 12/5 – 12/7
NPRR1020(a) | None | ECRS (NPRR863) NPRR903 NPRR992 NPRR1015 NPRR1085 NPRR1096(b) NPRR1148 NOGRR186 NOGRR187 OBDRR043/44 NPRR1135 | Securitization Phase 2A – Maine Invoice and Credit Exposure SCR789 Ph2 NPRR1112 | NPRR1154 LPGRR070 NPRR1163 OBDRR048 EMS Upgrade | SCR807 SCR816 NPRR1026(a) NPRR1164
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
NPRR1020(a) – EPS Metering portion
NPRR1026(a) – SLF – RIOO portion
NPRR1096(b) – ECRS portion
TBD | NPRRs: 484,825(b),826,829,841,857,879,885,904,918,930,936,941,945,963,965,975,987,995,1004,1006,1007,1019,1023,1030,1032,1034,1057, 1077,1105, 1111,1128,1131,1136 SCRs: 799,805,810,818,819 PGRRs: 066,076,088,091,094,099 Other: OBDRR009,OBDRR017,RRGRR028
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
E
E
E
P
P
11/15
7/14
ü
ü
ü
10/1
ü
EMS Upgrade Freeze – July 2023 – Jan. 2024
11/1
6/28
ü

## Slide 6: 2024 Release Targets – Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
January 1/25 | February 2/22 | March 3/28 | April 4/25 | May 5/30 | June 6/27
NPRR1040 NPRR1092(b) SCR822 | NPRR1002 NPRR1153 PGRR103 RRGRR023 RRGRR032 RRGRR033 | NPRR1026(b) |  | NPRR1149 NPRR1121 NPRR1090 NPRR962 NPRR1196 Forecast Presentation Platform | NPRR1149 NPRR1121 NPRR1090 NPRR962
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
R1
R2
R3
R4
R5
R6
NPRR1026(b) – SLF – Reporting portion
NPRR1092(b) – Limit RUC Opt-Out Provision
P
P
P
P
P
E
E
P
P
Q1 – RIOO
P
P
P
P
P
P
P
July 7/25 | August 8/22 | September 9/26 | October 10/24 | TX SET 5.0 11/10 | December 12/11-12/12
 | SCR813 |  |  | NPRR1095 SCR817 SCR823 RMGRR172 | 
R7
R8
R9
R10
R11
E
E
E
E
P

## Slide 7: Additional Project Status Information
Revision Request | Description | Project Phase | Additional Detail
RTC | NPRR1007-NPRR1014, Single Model, State of Charge | Planning | Project has restarted
SCR820 | Operator Real-Time Messaging During Emergency | Planning | Go-Live target is TBD
NPRR945 | Net Metering Requirements | Not Started | Start delayed due to an internal project dependency
NPRR1004 | Load Distribution Factor Process Update | Not Started | ERCOT is aware of interest in getting these implemented The DRRS IA is now complete and has been loaded in the ERCOT portfolio management system. We are now assessing these items for potential inclusion in 2024 project plans.
NPRR1006 | Update RT On-Line Reliability Deployment Price Adder Inputs to Match Actual Data | On Hold | Assessing restart date options
NPRR1058 | Resource Offer Modernization | Not Started | Assessing start date options
NPRR1091 | Changes to Address Market Impacts of Additional Non-Spin Procurement | Not Started | 
NPRR1128 | Allow FFR Procurement up to FFR Limit Without Proration | Not Started | Assessing start date options
NPRR1131 | Controllable Load Resource Participation in Non-Spin | Not Started | Assessing start date options
SCR805 | Provide Early Access to Certain 60-Day Reports to TSPs Upon Request | Not Started | Assessing start date options
SCR819 NPRR1111 | Improving IRR Control to Manage GTC Stability Limits | Not Started | Targeting Q1 2024 start
NPRR1007 NPRR1014 | SCED Postings Gray-boxed in Section 3.2.5(4) Publication of Resource and Load Information | Not Started | Increasing granularity for SCED disclosure reporting
Red Text: New additions and updates

## Slide 8: MPIM / MFA Discussion
Background
  Digital certificates are used to manage Market Participant (MP) access to ERCOT systems
  Entities may register under multiple MP types (LSE, QSE, Resource Entity, etc.) and have multiple registrations of each MP type.
  Users of ERCOT systems are required to have as many digital certificates as instances of their entity’s registration at ERCOT
  Users are often required to use and maintain a large number of digital certificates
ERCOT is planning a series of projects to move beyond digital certificates
  This is expected to result in an access management approach that is greatly simplified compared to the current state
ERCOT expects that a change in access methodology for MPs will require an accompanying set of Revision Requests
  Protocol Sections 2, 16.12, 15.2, 16.15, 19.6, 23 (A, B, E, G, I, J, L, M)
  ERCOT would appreciate Market Participant collaboration in writing the NPRR and any supporting guide revision requests
MPIM = Market Participant Identity Management
MFA = Multi-Factor Authentication

## Slide 9: MPIM / MFA Discussion
ERCOT has identified a set of MPIM projects to be run in sequence
  MPIM Tech Health Upgrade
    Project started in September 2023
    Targeted for completion in mid-2024
  MPIM Redesign for Use of Digital Certificate
    Short project to determine approach/technology for MPIM MFA project
  MPIM MFA
    Implementation project to convert from digital certificates to MFA
    Project start currently targeted for Q4 2024
Timeline
  It would be optimal to have a Revision Request approved through the stakeholder process prior to the start of project #3 above (MPIM MFA)
  Assuming a 4-6 month stakeholder approval timeline, getting Revision Requests submitted in Q2 2024 would meet this timeline
MPIM = Market Participant Identity Management
MFA = Multi-Factor Authentication

## Slide 10: Priority / Rank Recommendations for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR1172 | Fuel Adder Definition, Mitigated Offer Caps, and RUC Clawback | 2024 | 4070 | $45k-$65k, 4-6 months Impacted System(s): MMS, Reporting, MIS, S&B
NPRR1203 | Implementation of Dispatchable Reliability Reserve Service (DRRS) | 2023 | 370 | $1.0M-$1.5M, 12-15 months Regulatory Go-Live required by 12/1/2024 Impacted System(s): MMS, EMS, S&B, Integration, ERCOT.com, MIS, Reporting
Recommendations for…
PPL Rank Information
Next available 2023 Rank in Business Strategy = 3820
Next available 2024 Rank in Business Strategy = 4070
Next available Rank in Regulatory = 370

## Slide 11: Technology Working Group (TWG)
Next TWG meeting date is TBD